Annual Review - Summary Sheet

PROGRAMME TITLE: Zimbabwe Security and Justice Programme (ZSJP)
Country and Region:	Zimbabwe (administered under the HQ programme)
IATI Unique ID:	CSSF-03-000032
HMG Partners (LEAD in bold)	Department for International Development (DFID), Ministry of Defence (MOD)
Total Budget (approved):	ODA: £0.55m			Non-ODA: £0.05m
Budget this FY	ODA: £0.2m			Non-ODA: £0
Spend this FY	ODA: £0.1886m			Non-ODA: £0
Original Programme Start Date: April 2019			Planned End Date: March 2021
Outputs					Score
Dialogue on improving security and justice is inclusive of key stakeholders.					B
Key institutions have greater capacity to improve and scrutinise the performance of the security sector.					B
Research and analysis enable effective engagement and coordination on security sector accountability by UK and Development Partners.					A
Mechanism and staffing in place to drive the project forward tailored to the Zimbabwean operating context and regional experience.					A
Overall output score: B
Outcome Assessment: B
Outcome Score: B		Risk: High (due to major budget reductions in FY20-21)

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	N/A	N/A		N/A		B
Risk Rating - low/medium/high	N/A	N/A	N/A		N/A		Medium
*output/outcome scores
How has the programme changed during this period?			The programme saw a number of budget adjustments over the period. The original budget allocation for FY 2019-20 was £0.4m with £0.2m planned for FY20-21. Given the time needed to start up activities, this balance was reversed, so £0.2m for 2019/20 and £0.4m in 2020/21. The non-ODA 2019/20 budget was returned to the centre.

What support did the UK provide in FY 19/20?
- Support for a peer-to-peer parliamentary assessment to determine how best to support the work of the key committees related to security and justice oversight.
- Completion of an updated political economy analysis on the security and justice sector in order to deepen and widen understanding of dynamics in the system.
- Senior advisory support on policing accountability and to build relationships with Parliament and other security system actors as the foundation for constructive engagement.
- Support to United Nations Office for Project Services (UNOPS) to bring together a small team of Security and Justice experts from Zimbabwe and the region. In March 2020, some of this provision was used in the response to the public safety risks posed by the COVID-19 pandemic.
- Support to the Zimbabwe Council of Churches (ZCC) to engage on issues of security sector transformation. With the start of the COVID-19 pandemic in the region at that time, an additional output was added to enable ZCC to address immediate local safety risks arising from the virus.

Key results for FY 19/20:
- The understanding of key colleagues about the dynamics of power, factionalism and command and control in the Zimbabwean security sector (formal and informal) was improved.
- The experience and expertise in analysing the sector brought together a wider group of experts, although this was brought to an abrupt halt by the start of the COVID19 crisis and accompanying shut down of activities.
- Initial relationship and trust were built with the Speaker and Clerk of Parliament, as well as key committees, on building capacity to exercise their mandate for oversight of the security sector.

Key Lessons
- The importance of starting with as clear as possible an understanding of the informal and formal power structures within the security sector, shared across the mission.
- The importance of dedicated advisory time to follow through on areas of work and maximise benefits (e.g. from historical and peer-to-peer relationships).
- The value of drawing on the guidance of national and sub-national experts when initiating a dialogue process, particularly when concerning deeply sensitive institutions exercising coercive power and control.

Summary of Recommendations for FY 20/21
- Continue to put risk management at the heart of the approach, focusing HMG attention on risk relative to return and mitigation. The risk matrix needs to be updated as soon as possible.
- Sustain, to the extent possible, the ability of the programme to understand, engage and influence, leveraging existing networks (e.g. across church groups) and generating participatory processes on common concerns and invest in Zimbabwean efforts to monitor and record how the relevant institutions respond.
- Ensure that the experiences emerging from ZSJP’s initial implementation, combined with those under Transparency, Responsiveness, Accountability, and Citizen Engagement (TRACE) programme grants which aim to promote constructive dialogue and partnerships between civil society and government. This combination should feed into decisions on the allocation of future FCDO resources and the design of programming.