Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Strengthening Security and Resilience in Sierra Leone and Neighbouring Countries
Country and Region:	Sierra Leone, Guinea and Liberia - Africa
IATI Unique ID:	CSSF-03-000010
HMG Partners / (LEAD in bold)	Ministry of Defence (MOD), Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget:	ODA: £4.175m		Non-ODA: £8.175m
Total Spend:	ODA: £4.349m		Non-ODA: £9.451m
Original Programme Start Date: 24 Feb 2014 (MOU signed)				End Date: 31 March 2020
Outputs					Score
Improved and more inclusive security sector governance.					A
Increased capability, effectiveness and responsiveness of targeted institutions					A
Horton Academy is capable and self-sustaining.					B
International Security Advisory Team (ISAT) access, reputation and influence in the Sierra Leonean security sector is increased.					A
Overall output score A
Outcome Assessment: The programme sought to achieve ‘a capable, accountable and responsive security sector architecture ensuring stability in Sierra Leona through a sub-regional approach’. Over the four-year programme to 31 March 2020 substantial progress was made towards the outcome, but it was not achieved in full. A particular concern outstanding is the financial sustainability of the Sierra Leonean security sector.
Final Outcome Score: A		Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	B	A	A	A	A	B	A	A
Risk Rating - low/medium/high	N/A	High	Medium	Medium	Medium	Medium	Medium	Medium
*output/outcome scores

What support did the UK provide?
- Capacity-building expertise, mentoring and practical advice to key partners via embedded subject matter expert advisers in key security sector institutions.
- Training support to local security actors through the Horton Academy, as well as in technical specifics ranging from ammunition safety to border security and countering the illegal wildlife trade, as well as key cross-cutting issues (Gender, Human Rights and Conflict Sensitivity).

What results did the programme deliver? Will they be sustained?
- Establishment of a coherent and coordinated security sector, led by an Office of National Security that supports the National Security Council. It now coordinates security activities throughout the country, supporting Government of Sierra Leone policy priorities and improving community confidence.
- The programme has led to improved training, partnerships, gender balance, Human Rights standards planning and community policing by the Sierra Leone Police (SLP), building towards becoming the nation’s primary resource for domestic security management.
- Through programme activities the Republic of Sierra Leone Armed Forces (RSLAF) is close to full operating capacity, self-sustaining on recruitment and increasingly self-sustaining on training. It is led by an increasingly educated and professional officer and NCO corps, informed of its obligations by the Sierra Leone Security Sector Review.
- The establishment of Horton Academy as a regional centre of excellence, has trained students from ten of the 14 Economic Community of West African States (ECOWAS) countries and has teaching staff from three (Ghana, Liberia, Nigeria). Sierra Leone authorities have expressed a clear intent to continue to support the Academy.

What lessons have been learned?

- Sustained Sierra Leone-UK military cooperation, including British advisers (military and police) working with senior Sierra Leonean leaders has been key in facilitating trust, cooperation and understanding.
- A balanced security sector is essential. The RSLAF is arguably too successful in the local security sector context – it has, in some instances, become Sierra Leone’s go-to tool. Such programmes should be balanced with wider efforts to avoid overshadowing civilian agencies.
- The RSLAF is large and expensive by regional standards. Technical organisations like ISAT need to keep abreast of such realities and ensure that the capacity of the host economy to afford its security sector is key in planning.
- Partners need to promote local ownership as quickly as realistically possible and develop a regularly reviewed and agreed exit strategy to avoid the host country remaining dependent on external programme support.

Summary of Recommendations for future programmes

- Ensure that programme exit strategy is made clear to all parties linking it to achievement benchmarks.
- Ensure progressive hand-over to local ownership, regularly reviewed to ensure ongoing mutual confidence.
- Ensure a balance of programmes across the Sierra Leonean security sector arms, as well as a balance between capacity building and support which will need to be reviewed regularly.
- Consider future partnerships with international partners with combined civilian / military (CIVMIL) emergency planning and response skills.