Annual Review - Summary Sheet

PROGRAMME TITLE: Caribbean Serious Organised Crime
Country and Region:	Caribbean, Americas
IATI Unique ID:	CSSF-04-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), National Crime Agency (NCA), Home Office (HO) including Immigration Enforcement International (IEI), Crown Prosecution Service (CPS), Department for International Development (DFID), Ministry of Defence (MOD), Criminal Records Office (ACRO)
Total Budget:	ODA: £3,184,372.00			Non-ODA: £1,653,203.00
Budget this FY:	ODA: £3,184,372.00			Non-ODA: £330,000.00
Spend this FY:	ODA: £3,369,830.00			Non-ODA: £316,169.00
Original Programme Start Date: April 2015		Planned End Date: March 2020
Outputs					Score
1.1 Delivery of comprehensive donor mapping exercise to understand gaps and opportunities.					A+
1.2 Delivery of prisoner (including gang members) rehabilitation programme – Jamaica.					A+
2.1 Report and recommendations on investigative journalism on serious and organised crime (SOC) and grand corruption and where the programme should focus for FY20/21.					A+
2.2 Scoping and report from Government Communications Service International (GCSI) on government comms + SOC in the region.					A
3.1 Closedown of pre-existing projects and sustainable transition to external partners and host governments.					A
3.2 Targeted training on SOC and grand corruption for the region’s criminal justice practitioners increases expertise and regional responsiveness to SOC.					A+
3.3 Specialised mentoring and equipment to police forces, which delivers more effective investigations.					B
3.4 Leadership and ethical behaviour training for criminal justice professionals to deliver safer convictions and more accountable leadership (cross-cutting output with sub-outcome 2).					A+
4.1 Funding to the Carter Centre for independent election observers to support free and fair elections in Guyana.					A
4.2 Review of Political Access and Influence (PAI) in the Caribbean Programme					A+
Overall output score					A
Outcome Assessment:
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	B	C	B	C	B	B	A	B
Risk Rating - low/medium/high	Unknown	Unknown	Unknown		Medium			Medium
*output/outcome scores
How has the programme changed during this period?			The programme transitioned in FY19/20, closing the previous programme, scoping activities for the new programme and some work delivering against the new programme structure.

What support did the UK provide in FY 19/20?

CSSF provides funding to improve the ability of Caribbean governments, judiciaries, prosecutors and law enforcement agencies to prevent and disrupt SOC, which impacts both the region and UK. This is done through the provision of expert advisors and technical assistance; HMG-led project delivery; externally procured project delivery and bilateral support to specific governments.

Key results for FY 19/20:

In the period since the last Annual Review the programme has undergone a major transformation, closing down 12 projects and transferring 4 projects to local host governments/regional institution control. The programme has strengthened bilateral and regional institutional relationships, using the HMG SOC strategy. The deployment of a SOC Overseas Network (SOCNET) coordinator and devolved governance has allowed the programme to plan for a more focused and strategic phase of programming in FY 20/21. The transformation has included commissioning a number of independent scoping studies to ensure a sounder evidence based underpins new activity.

Summary of progress and lessons learnt/actions taken since last review
The relationship between HMG departmental operational objectives and wider UK strategic aims can cause a tension for CSSF delivery. This can lead to advocacy that limits ambition to existing activities. More clarity and challenge during the initial discussions on projects would help to avoid this. / For a regional programme, the need for adaptability and agility is key. Local situations can change often across countries, and programmes need to be able to refocus as needed to maintain progress towards their goals. These and individual country projects must be framed within the agreed strategic narrative.

Summary of Recommendations for FY 20/21

- Revise the theory of change to be clear where the CSSF is helping partners address SOC issues and where it is building broader security and justice capacity.
- Focus the “Cross-Border Security Cooperation” on the strengthening of a particular institution(s) and smaller number of individuals rather than a potentially broad set of activities.
- Ensure a strong bilateral UK component to the delivery of “Adapting Criminal Systems in CARISECURE Countries” to maximise the impact of the activity.
- Consider making the case for a standalone “stability” component to address conflict prevention and dispute resolution opportunities across the region.
- Document and share lessons learnt from the Caribbean programme over the previous years to inform design of future regional, cross-HMG programmes.
- Continue to explore how to widen the number of HMG departments and agencies involved in the programme without sacrificing gains in coherence and project management.
- Further revise results framework, removing or reducing the number of outputs associated with internal processes and drawing either for the Political Access and Influence tool or “Outcome Harvesting” to more accurately measure the effect of the CSSF. The current gap between ambition on Outcomes and Outputs has scope to be reduced further.