Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Hurricane Dorian – Crisis Response to the Bahamas
Country and Region:	The Bahamas, Caribbean
IATI Unique ID:	N/A (Non-ODA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MOD)
Total Budget:	ODA: £0m			Non-ODA: £1.5m
Total Spend:	ODA: £0m			Non-ODA: £1.1m
Original Programme Start Date: September 2019		End Date: March 2020
Outputs					Score
Deliver immediate lifesaving assistance.					A+
Deliver enabling support that cannot be met by other actors.					A
Overall output score					A
Outcome Assessment: CSSF support was intended to enable a fast UK effort in The Bahamas, enabling a largely humanitarian support response into a non-ODA country. UK support exceeded expectation in terms of scale, duration and supplies delivered. Balanced against this, there were some activities that UK initiated that did not prove necessary; this reflects some incorrect assumptions about likely needs, some based upon previous responses to Hurricane Irma. Overall, the CSSF response was successful, mobilising quickly, flexibly responding to changing circumstances and the specific needs expressed by the government of The Bahamas.
Final Outcome Score: B			Risk: M

Summary of Programme Performance
Year	2018/19		2019/20*
Programme Score			A	B
Risk Rating - low/medium/high			Medium	Medium
*output/outcome scores

What support did the UK provide?
Hurricane Dorian made landfall on 1st September 2019 over the northern Bahamas as a Category 5 system with sustained windspeeds of up to 180mph and a storm surge of up to 7 metres in the islands of Abaco and Grand Bahama, leaving thousands of people in need of assistance. It is the second strongest hurricane ever recorded in the Atlantic, and the second strongest to make landfall. Extensive damage to property, national infrastructure and communications networks was reported.

The UK, in support of the Government of the Bahamas, provided (based on needs assessments to target assistance to local needs), UK expertise, financial support and life-saving support to the most affected areas. Funding was allocated to support the costs of Royal Fleet Auxillary (RFA) Mounts Bay’s activities in the area, the replenishment of DFID and MoD relief supplies and the costs of deployments to the Bahamas from DFID and its partners. This support included:
- Deployment of five humanitarian and logistics experts to the region.
- Deployment of an Early Recovery Adviser;
- A civil-military coordinator funded and deployed through the United Nations Disaster Assessment and Coordination (UNDAC);
- Funding for a team from the Caribbean Disaster Emergency Management Agency (CDEMA);
- Funding of a team from MapAction;
- Vital supplies from RFA Mounts Bay and replenishment of HMG supplies on RFA Mounts Bay;
- Disaster Victim Identification (DVI) support through the UK National Disaster Victim Identification Unit.
- Use of heavy machinery and technical support to replace critical infrastructure (e.g. Airstrips, communications networks).

What results did the programme deliver?
Working closely with the Government of the Bahamas and other partners, the programme met immediate humanitarian need in the Bahamas, restoring security, critical infrastructure and ensuring the provision of consular assistance. Through the Conflict, Stability and Security Fund (CSSF) the UK delivered support including:

Funding and deployment of 5 humanitarian and logistics experts to the region. The team comprised: 2 Logisticians; 1 Humanitarian Affairs officer; and 1 Humanitarian Advisor.

Funding and deployment of an Early Recovery Adviser to provide support and assistance to the Government of Bahamas for the development and coordination of a Recovery Plan following Hurricane Dorian.

A civil-military coordinator funded and deployed through the United Nations Disaster Assessment and Coordination (UNDAC) as a point of liaison between the humanitarian community and military forces on the ground. Funding was provided directly to Caribbean Disaster Emergency Management Agency (CDEMA) for team deployments over a six-week period to support rapid needs assessments, along with assistance to the national disaster office operations and helping detail loss and damage evaluations over a 6 - week period.

A team from MapAction deployed to work with National Emergency Management Agency (Bahamas) (NEMA), CDEMA and the Pacific Disaster Centre (PDC) on the coordination of incoming assistance, particularly on what different actors were doing and where. This helped developed products on where best to direct efforts.

Disaster Victim Identification (DVI) - UK DVI assistance was offered to the Bahamas. An officer from the National Disaster Victim Identification Unit flew to the Bahamas to carry out a review, and make recommendations, setting out what proportionate assistance the UK could provide in relation to victim identification in The Bahamas.

- Use of heavy machinery and technical support to replace critical infrastructure (e.g. Airstrips, communications networks).
- Provision for further technical and relief support through partners if this was deemed appropriate considering the gaps in the response identified by the field team on the ground.
- RFA Mounts Bays was pre-positioned in the Caribbean in preparation for hurricane season and was the first ship from any nation to arrive on the scene in the wake of Hurricane Dorian. During the ten-day mission, Mounts Bay distributed all of her stores, which included 3,000 ration packs, nearly 100 tonnes of water, over 900 emergency shelter kits, and 1,000 hygiene kits.
Mounts Bay ensured communities on Great Abaco had access to the most basic needs such as food, water, and shelter in the immediate aftermath of the hurricane. The ship’s Wildcat helicopter flew reconnaissance flights to assess damage and located isolated communities in outlying islands in urgent need. The Post in Nassau was also reinforced with OLRT members.
What lessons have been learned?
The hurricane season in the Caribbean is a regular annual event and the UK pre-positions assets to support disaster response requirements, particularly where that may involve the UK’s Overseas Territories in the region. As such, HMG teams are better prepared than is the case for other disaster scenarios, although there are considerable variables such as timing (hurricane season lasts about 5 months) and geography (Caribbean covers 2.7million km2) that make detailed advanced planning difficult.

There are, however, some lessons that can be taken:
Process - FCO and DFID teams responded with commendable speed to seek funding support from the CSSF, using the Rapid Reaction Mechanism (RRM) to ensure minimal delays. Whilst this ensured a swift HMG response, some parts of the CSSF system in Americas Directorate were not engaged as part of that process until it was far advanced, which meant that additional effort was then required to quickly retrofit the programming requirements. Lesson - discussion should be carried out between HMG stakeholders before hurricane season to agree protocols and rules for engagement, saving time and ensuring a smooth HMG response.

Co-ordination – Whilst the response quickly pulled together the key stakeholders in HMG to create a joint action plan, this happened in response to the crisis. Lesson: more communications between FCO and DFID for longer term planning in the region, covering both ODA and non-ODA countries to ensure the right response is generated from pre-existing plans.

Funding – Whilst much of the Caribbean region is open to ODA-funded support, The Bahamas is currently considered a non-ODA country. This meant that RRM funding had to be non-ODA in this case, which subsequently created technical issues for the DFID team leading the response, whose systems are designed to manage ODA funding. Effort and time was thus diverted from the response to manage these issues. It would have been possible to spend at least some of this funding via the FCO Americas team, where non-ODA spend is more common, to reduce stress on the DFID response team. Lesson – consider which department is better able to efficiently handle the finance management during a joint response.

Previous Experience – During the initial response phase, there was a tendency amongst some HMG teams to assume that the UK’s response would be based upon those encountered during Hurricane IRMA, i.e., primarily addressing security issues. Clearly it is sensible to learn from previous, and recent, experiences but this assumption did not match the requirement in The Bahamas, which was primarily humanitarian. Lesson – Prior planning about the likely variety of engagements would allow for a more flexible set of agreed responses.

Fast Response - The UK was one of the first international responders, with the swift arrival of RFA Mounts Bay being a very visible and tangible demonstration of our support to The Bahamas in their hour of need. In these situations, this really matters, and will act as a touchstone during future UK-Bahamas engagement. Lesson – the UK has set in place mechanisms to support swift action, including pre-positioned supplies and CSSF’s RRM; knowing about them, and making prompt use of them, allows the UK to react quickly to crisis, benefitting of those in need and demonstrating the UKs commitment to being a force for good in the world.

Immediately after the crisis the FCO carried out a lesson learning exercise, although this was focussed mainly on the Consular response; there are some cross-over lessons, mainly around preparedness and planning, which also came through during interviews about the CSSF intervention.