Programme Completion Report - Summary Sheet

PROGRAMME TITLE: Colombia/Peru Serious Organised Crime / (Transitioning to Combatting Illicit Economies Programme (LatAm) starting in FY20/21)
Country and Region:	Colombia, Peru, Panama and Venezuela (Latin America)
IATI Unique ID:	CSSF-04-000003
HMG Partners / (LEAD in bold)	National Crime Agency (NCA) and Crown Prosecution Service (CPS) Leadership transitions to Foreign & Commonwealth Office (FCO) leadership during year under review
Total Budget:	ODA: £11,785,400 (programme cycle)			Non-ODA: £0
Budget this FY	ODA: £2.9 million			Non-ODA: £0
Spend this FY	ODA: £2.7 million			Non-ODA: N/A
Original Programme Start Date: April 2015		Planned End Date: March 2020 (Programme concluded)
Outputs					Score
Judicial Training in Complex Cases (Peru and Panama)					A
Improving Regulation of Lawyers (Panama)					A
Enhancing Regional Capacity in Tackling Financial Crime and Corruption (Peru, Panama and Colombia)					B
Analysis of Gender Roles in Latin American Serious and Organised Crime (SOC) Dynamics (Regional)					B
Training to the Fiscalia’s Special Unit Investigating Emblematic Homicides (Colombia)					A
Assistance in Developing Colombian SOC Investigative Capacity (Colombia)					B
Enhancing Police Forensic Analysis Capacity (Peru)					A
Establishing Leadership Strategy in National Police (Peru)					A
Provision of Tactical Training Assistance to Law Enforcement (Peru)					A
Office of Public Integrity Transparency Protocols (Peru)					B
Establishing Civil Society Anti-Corruption Coalition (Venezuela)					A+
Overall output score:					A
Outcome Assessment: / Against a new Monitoring & Evaluation (M&E) process, the programme has largely met outcome ambition for FY19/20. Looking at the programme cycle as a whole (i.e., from 2015-2020) using the new M&E process, allowed for a more rigorous and critical assessment of the degree to which programming met its stated objectives. This also highlighted the negative impact on overall objectives of programme evolutions.
Outcome Score: B			Risk: Medium

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A/B	A	A	B	B	B	A	B
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium		Medium
*output/outcome scores
How has the programme changed during this period?			Prior programming cycle (consisting of CSSF Peru and Colombia SOC Programme) ends and transition occurs to a new programme cycle under FCO leadership: the Combatting Illicit Economies Programme (LatAm) (“CIEP”). / CPS/NCA activity draws to a close and new activity is designed/starts delivery in accordance with newly release HMG regional SOC strategy. / Programme activity continues in Colombia and Peru but also expands to Panama and Venezuela and with increasing ambition to try and achieve a holistic approach in the delivery of HMG’s SOC strategy

What support did the UK provide over the Programme Cycle (2015-2020)?

- Mentoring of key domestic SOC stakeholders by HMG-deployed expertise (NCA and CPS).
- Provision of training to key domestic stakeholders engaged in tackling SOC and with a particular focus on financial crime, corruption, domestic/sexual violence, intelligence collection/handling.
- Needs-analyses and sectoral reviews leading to reform proposals for increased efficiency/effectiveness within regional criminal justice systems.
- Development of policies/protocols to promote increased efficiency/effectiveness within regional criminal justice systems.
- Commercially delivered assistance to particular Peruvian counterparts in the areas of forensics, leadership strategies and transparency measures.
- During a transition year, the Programme’s previous focus on deployed HMG expert mentoring and training design and delivery has continued. In addition, there has been work on alternative delivery mechanisms which will form a part of the new Combatting Illicit Economies Programme. This includes a grant to a non-profit organization which facilitated the establishment of a civil society-driven anti-corruption coalition in Venezuela.

Key Results for Programming Cycle (2015-2020 including the prior financial year))

The CSSF Colombia and Peru SOC Programme pursued outcomes seeking to:
1.) Improve coordination and collaboration within and across regional criminal justice
 Systems.
2.) Increase organisational effectiveness and technical ability in confronting SOC threats (particularly financial crime, narcotics and corruption) and
3.) Increase awareness regionally of SOC dynamics and develop more effective institutional approaches to tackling the dynamics.

This review finds that the programme has achieved its aims in increasing organisational effectiveness in confronting specific SOC threats. It has partially achieved its aims to improve coordination/collaboration within and across regional justice systems; and increasing awareness regionally of SOC dynamics and effectives responses to those dynamics.

Key Lessons Learned for Programming Cycle (2015-2020 - including the prior financial year)

The Programme engaged in a very active ‘lessons learned’ process as programming transitioned to the new CIEP. This required reflection of the whole programme cycle, including: what had worked; what had been less successful; which activity should be continued and which should be transitioned away from.

Previous annual reviews had noted that – whilst individual activity undertaken was rational in and of itself and often demonstrated notable impact – a strategic underpinning to programming was less obvious and it was difficult to identify clearly how the different activities were cohesive across two countries (Colombia and Peru) in forming a logical whole. This was perhaps a reflection of programming developing organically and the difficulty of delivering across different HMG partners. Undoubtedly, this hampered effective monitoring and evaluation and overall programme coherence. Going forward, CSSF activity should be approved with a clearly articulated, strategic underpinning, which sets a direction for the whole programme.

With the benefit of the HMG SOC strategy now for reference, it is also clear that prior programming focused quite narrowly on ‘operationally focused interventions. Evidence suggests a broader approach is more likely to achieve impact. While individual activity was well-conceived and well-executed, knowledge gained through new monitoring and evaluation (M&E) processes, made drawing conclusions on the impact of the overall programming cycle harder. As the recommendations below suggest, efforts should be made to systematize M&E processes across programmes with a stronger strategic underpinning. Collection of evidence demonstrating which interventions have an impact against SOC and which do not should be standard.

As indicated above, prior programming adopted varying M&E approaches through its lifecycle. In latter parts of the programme, it developed a standard results monitoring system for traditional security and justice-style interventions. This may have been more ambitious than the CSSF Colombia and Peru Programme was ever resourced to deliver. The programme dealt in influencing and securing singular access to criminal justice counterparts and thereby promoting niche reform and system adaptation. All evidence is that the programme achieved some considerable success in this regard, but it was not always the standard that the programme was asking itself to be judged against. A better and more realistic M&E strategy could have been established before the programme was approved. Notably, the transition year, which this review covers, has seen a ‘transition results framework’ prepared, providing a closer approximation of the work being undertaken by implementing partners. This work should continue in new programming and could usefully feed into a global discussion on the use of M&E in shaping effective SOC programming.

The prior programming cycle was delivered almost entirely by CPS and NCA but with FCO input increasing through later years. This, in part, grew out of recognition that the programme required a regional management function to ensure programme coherence and that CPS and NCA (the SOC subject matter experts) were not necessarily best placed to provide that. Such a programme management function was in place by financial year 19/20 and has been responsible for driving the transition of programming to the CIEP. SOC programming clearly benefits from a clear separation of – and understanding of the distinct functions of - programme management and subject matter experts/project delivery roles. Particularly when designing SOC interventions, there will be an interest in maintaining close relations with HMG operational partners (whether CSSF resourced or not). But equally, the coherence of the prior SOC programme was undoubtedly complicated by multi-departmental delivery. The new model of a central FCO-led management function bringing in and supporting other HMG SOC activity through programming holds promise as a delivery model going forward.

There are other lessons to be learned about effective delivery models for future programming. The influencing and access of the CPS and NCA experts deployed into the programme was a considerable success and noted in previous annual reviews. CIEP would benefit from this expertise as they seek to develop new programming areas. Also notable is that the deployed expertise achieved more success when working ‘with the grain’ and in pursuing host nation objectives as a route to achieving HMG goals, rather than simply imposing programming solely in pursuit of HMG goals. The programme undoubtedly positioned HMG as a strategic partner of choice in the region, permitting access to regional criminal justice institutions at the highest levels. This seems to have occurred because the UK was viewed as a partner on SOC and related issues rather than adopting a more didactic and self-interested approach to reform.

Where the prior programme sometimes experienced challenge was in securing systematic change at national or regional levels. In part this was because of the many different objectives the programme adopted (at the risk sometimes of spreading itself too thinly). There are also clear limitations in deploying a small number of individual HMG experts to deliver change processes across a large number of countries/the region. Earlier programming was most effective where the influence of deployed HMG expertise was combined with project delivery by a separate implementing partner, increasing the efforts seeking change. This occurred most often in Peru where NCA were able to leverage their prized relationship with criminal justice counterparts to provide bespoke analysis and assessment of necessary reform, while partnered with a commercial delivery partner to deliver the reform package. A proposal for the new CIEP to contract a commercial implementer to partner in a similar way (though across the entire programme) is a logical extension of these principles.

Efforts have been made to approach SOC from a gender perspective through prior programming, but this mainstreaming has been a challenge throughout the programme cycle. In part, this is because of a shortage of gender-based analysis of SOC dynamics generally (and which programme activity this year sought, in part, to address) but too often individual interventions were established in isolation, driven by gender mainstreaming obligations rather than as a goal across programming in and of itself. Future programmes should articulate a much clear gender strategy, explaining how the issue will be approached across all programming.