Annual Review - Summary Sheet

PROGRAMME TITLE: Colombia Peace and Stability Programme (CPSP)
Country and Region:	Colombia, Latin America
IATI Unique ID:	CSSF-04-000002
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £52,900,000 from 2015-16 until 2019-20			Non-ODA: 0
Budget this FY	ODA: £14,170,000			Non-ODA: 0
Spend this FY	ODA: £14,057,568			Non-ODA: 0
Original Programme Start Date: April 2016		Planned End Date: March 2022
Outputs					Score
The central state has enhanced capabilities and opportunities to implement effectively rural components of the Colombia Peace Deal and better contain environmental effects of the transition from war to peace.					A
State security and justice capacities strengthened to deliver transitional justice and deal with spill-over effects of the transition from war to peace.					A
Local actors have the capabilities and opportunities to participate effectively in the implementation of the peace accords and strengthen independent oversight.					A
Overall output score					A
Outcome Assessment:
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	A	A	A	A	A+	A	A
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium		Medium
*output/outcome scores
How has the programme changed during this period? The programme has extended its actions to climate change and conflict issues, which has led to a strengthening of coordination with the Department for Business, Energy and Industrial Strategy (BEIS). Likewise, the programme continues to adapt its actions in accordance with the security dynamics and the impact generated by COVID 19.

What support did the UK provide in FY 19/20?
The Colombia Peace and Stability Programme (CPSP) aims to support the Government of Colombia (GoC) to address the causes and symptoms of violent conflict, thereby sustaining trust in, and progress towards, implementation of the historic peace agreement, signed in 2016 between the GoC and the Fuerzas Armadas Revolucionarias de Colombia (FARC). The programme recognises the central role of the state in ensuring that the peace deal is properly implemented and that the spill-over effects from the transition from war to peace upon the environment and human rights are contained. In addition to working with state actors, the programme also seeks to support the participation of civil society, particularly those most affected by the armed conflict, in the implementation of the peace accords. During 19/20, the programme supported 12 projects totalling £14,057,568, aimed at delivering progress against three intended outputs:

1. The central state has enhanced capabilities and opportunities to effectively implement rural components of the Colombia Peace Deal and better contain environmental effects of the transition from war to peace.
2. State security and justice capacities strengthened to deliver transitional justice and deal with spill-over effects of the transition from war to peace.
3. Local actors have the capabilities and opportunities to participate effectively in the implementation of the peace accords and strengthen independent oversight.

Key results for FY 19/20:
- Through the UN Trust Fund and bilateral projects, the programme has focused its efforts and resources on accelerating the implementation of the peace accord, including supporting the GoC in the implementation of rural development and reintegration programmes and strengthening the participation of communities.
- As a result, more than 220,000 people in PDET (Programas de Desarrollo con Enfoque Territorial) regions have benefited from support to the Territorial Renewal Agency (ART). In addition, 3,500 victims of the conflict have been able to access transitional justice and 40,000 received psycho-social support and reparation measure from the National Victims Unit. The 51 gender indicators peace accord have been continuously monitored in order to promote its implementation, including their alignment with the PDETs.
- Increased synergy with other UK Embassy interventions:
  - International Climate Finance (ICF): the team has supported environmental mainstreaming, which strengthened the capacities of the Territorial Renewal Agency to identify opportunities to invest in renewable energies, green infrastructure, sustainable productive systems and climate change mitigations for PDETs. The team also improved coordination between environment and peace institutions in rural areas affected by conflict and deforestation.
  - Newton Fund: strengthened the coordination on reincorporation of ex-combatants and environment and science projects.
  - Prosperity Fund: the programme supported gender training for GoC institutions that have responsibilities for the peace process implementation.
- Enabling more effective public oversight of the peace agreement – Congress representatives, including from the ruling party, participated in the visits to conflict-affected areas, including FARC reincorporation zones. The visits allowed Congress representatives to improve their understanding of the needs and challenges faced by ex-combatants and the communities, which emphasized and clarified the importance of the Government’s responsibility in the peace process implementation.

Summary of progress and lessons learnt/actions taken since last review
This virtual Annual Review (AR) process confirmed that the programme continues to advance and strengthen the interventions. These accelerate the implementation of the agreement on the ground, as well as strengthening the participation of the communities in the process. The programme has made significant strides in consolidating actions in the area of environment and peace and enabling the adoption of actions. These range from the analysis of the context to the identification of opportunities in rural areas. State capacities have been strengthened to contain environmental effects of the transition from war to peace more effectively. The programme has performed strongly in a challenging year, marked by the COVID-19 Pandemic. Additional challenges ranged from the implementation of lockdown measures to implementation of the peace agreement. The programme has demonstrated its ability to work both bilaterally and multilaterally to support a wide range of stakeholders and partners. It has adapted its project portfolio to the realities of COVID confinements. Following on from the recommendations of the last AR, the team strengthened its results framework to capture the impact of their projects and interventions better. This process was supplemented by central CSSF support on monitoring and evaluation, including the introduction of outcome harvesting tools.

Lessons
Taking a portfolio approach to supporting the peace agreement has allowed the programme to adapt to the context. By adopting a flexible approach to supporting the peace deal in its entirety, rather than specific areas (e.g. transitional justice or rural development), the UK has been able to adapt its offer of support to the GoC and help it overcome obstacles as they emerge. This has allowed the programme to get the most out of relatively small resources, shifting support to where there are opportunities to leverage the Colombian state’s delivery of the peace deal.
- Aligning policy and programming allows messages to be backed by concrete offers of assistance. By retaining flexible funding throughout the year, the Embassy has been able to back up advice on how the GoC might accelerate delivery of the peace accords with quick and tangible support, increasing the state capacity in that area. This was the case for the crossover between peace and the environment, gender and communications.
- Investing in new approaches to monitoring and evaluation offer a better way to plan and hold the programme accountable. With central support, the programme team developed a new method of capturing how the UK is supporting the peace process and how to measure the impact of CSSF. They did so using tools such as outcome harvesting, actor mapping and taking a portfolio approach. By sharing these approaches with partners, the programme has strengthened how other development actors measure their support to the peace deal in Colombia.
- Investing in cross-embassy work can lead to win-wins for multiple HMG objectives. The programme team has continued to work closely with colleagues delivering International Climate Finance programmes in support of UK climate change objectives. This has led to innovative programming addressing the nexus of peace, deforestation and biodiversity. This meets both UK objectives regarding peace and those around the forthcoming Conference of the Parties (COP) 26.
- Investing staff time and resources in multilateral trust funds has enabled the CSSF to deliver at scale, with a small team. The UN Trust Fund for Colombia continues to be a model of global good practice on “post-conflict” funding mechanisms. The programme team has invested considerable effort in ensuring that the Trust Fund has strong monitoring and evaluation mechanisms and is a forum for donors, Government and the UN system to discuss priorities in peace implementation. It is a powerful complement to bespoke bilateral activity by enabling the UK to deliver tangible benefits to conflict-affected communities.
- Covid-19 has had a negative impact upon peace process implementation, but the GoC has sought to mitigate this. The Colombian state reacted quickly to Covid-19, imposing strict lockdown measures in March 2020. However, the pandemic has inevitably disrupted delivery of some aspects of the peace accords, whilst also allowing contributing to a deterioration of security dynamics in rural areas. Continued commitment of the Colombian state, society and the international community to peace will be needed to ensure that the deal remains on track.

Summary of Recommendations for FY 20/21
- Review the theory of change in the light of security challenges thrown up by Covid-19 and use the portfolio approach to assess where UK support will have maximum impact;
- Given the continued threats to human rights caused by armed actors, explore how to deepen cross-embassy collaboration to support more effective state action to improve the prevention and protection response and mechanisms.
- Strengthen the links with the regional CSSF Combatting Illicit Economies Programme (CIEP) by bringing the oversight of CIEP activities solely taking place in Colombia under the management of the CPSP team;
- Conduct a stocktake on the impact of the funding being provided to the Organisation of the American States;
- Finalise the design of a new results framework and theory of change that is based upon outcome harvesting.
- Roll-out training on outcome harvesting to all implementing partners to ensure that new monitoring and evaluation methodologies take full effect.