Annual Review - Summary Sheet

PROGRAMME TITLE: Counter-Terrorism Programmes Fund (CTPF): Strand 4 Programme
Country and Region:	MULTI-REGION
IATI Unique ID:	CSSF-01-000015
HMG Partners / (LEAD in bold)	CONTEST Unit Home Office (HO), Department of Transport (DFT) Aviation and Maritime Security, Home Office (HO), Foreign and Commonwealth Office (FCO), Joint Overseas Protect and Prepare Team (JOPP), Ministry of Defence (MOD)
Total Budget:	Financial information below Fund level is redacted for security reasons. Fund-level financial information can be found on the Portfolio Summary sheet.
Budget this FY
Spend this FY
Original Programme Start Date: 1 April 2019		Planned End Date: 31 March 2020
Outcome Score: B		Risk: Medium
Output score: B

Summary of Programme Performance
(Programme performance for previous years was analysed for the CTPF as a whole – prior scores refer to CTPF as a totality, there is no dedicated score for Strand 4 in Financial Year 19/20.)

Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score		B	B		B		B
Risk Rating - low/medium/high	-	-	High		High		High
*output/outcome scores

What support did the UK provide in FY 19/20?
The UK’s Counter-Terrorism Strategy (CONTEST) aims to “Reduce the risk to the UK and its citizens and interests overseas from terrorism, so that people can go about their lives freely and with confidence”. The goal of the Counter-Terrorism Programmes Fund (CTPF) is to use targeted programming interventions to support the overseas element of this strategy.

Strand 4 ‘Protect and Prepare’ is one of four strands under the CTPF to support delivery of the overseas elements of CONTEST in 2019/20. It consisted of eight projects working in 40 priority countries worldwide.

Strand 4 projects were broadly grouped as follows:

Department for Transport (DfT) - ASSET (Aviation Security Strategic Engagement & Training) - A capacity development programme that provided training, equipment and regulatory support to countries where aviation-related vulnerabilities had been identified. The programme also aimed to support overarching international improvement initiatives for aviation security, including through the International Civil Aviation Organization’s (ICAO). The Aviation Security Programme delivered a wide range of capacity building training at airports in priority countries and provided Explosive Trace Detection equipment where this was judged to be a priority. The Aviation Security network also continued to engage extensively across priority countries to build effective relationships and common understanding of the risks to international travel.

DfT - MSSET (Maritime Security Strategic Engagement & Training) - A programme which aimed to mitigate the risk of terrorism against British ships, crew and passengers at commercial ports in priority countries and help secure the international maritime domain against acts of terrorism. The Maritime Security programme is relatively new so a large focus of its work in 2019/20 was to build relationships to enable effective partner engagement in priority countries and to undertake baseline assessments of port facility capabilities at key locations.

Joint Overseas Protect and Prepare (JOPP) - Programming to help governments and other key institutions to strengthen capacity to provide protective security in overseas locations and respond to terrorist attacks when they occur. JOPP delivered a range of capacity building in priority countries, both on ‘Protect’ issues (including security planning and awareness, physical and technical security measures, personnel and people security) and on ‘Prepare’ issues (crisis management structures, first response, and interoperability between responder agencies).

Summary of recommendations

Gender sensitivity should be incorporated consistently across the programme, building on the good practice seen in some areas.

Closely monitor the impact of C-19 on future programming and develop mitigation strategies for this, including arrangements for remote training.

Maintain commitment to relationship-building in-country, using these links to help navigate potential hurdles and provide greater visibility of impact.

Maintain focus on sustainability through train-the-trainer work.

Build on the value for money (VFM) successes achieved by working with allied donors and explore expanding formal donor coordination in countries with shared donor interests.