Annual Review - Summary Sheet

PROGRAMME TITLE: Counter-Terrorism Programmes Fund (CTPF)
Country and Region:	Multi-region
IATI Unique ID:	CSSF-01-000014
HMG Partners / (LEAD in bold)	CONTEST Unit, Joint Intelligence Organisation (JIO), Joint Terrorism Analysis Centre (JTAC), Defence Intelligence (DI), Defence Science and Technology Laboratory (DSTL), National Security Research Group (NSRG), Counter Terrorism Analysis and Insight (CTAI), Foreign & Commonwealth Office (FCO), Home Office (HO), Ministry of Defence (MOD), Department for International Development (DFID), British Council, Cabinet Office (CO)
Total Budget:	ODA: £31,459,960		Non-ODA: £14,457,195
Budget this FY	ODA: £31,459,960		Non-ODA: £14,457,195
Spend this FY	ODA: £30,564,940		Non-ODA: £14,523,838
Original Programme Start Date: 01/04/2017		Planned End Date: 31/03/2020
Outcome Score: B		Risk: Medium

Summary of Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score			B	B	A	B	B
Risk Rating - low/medium/high			High		High	High	Medium
*output/outcome scores

What support did the UK provide in FY 19/20?
The UK’s Counter-Terrorism Strategy (CONTEST) aims to “Reduce the risk to the UK and its citizens and interests overseas from terrorism, so that people can go about their lives freely and with confidence”. The goal of the Counter Terrorism Programmes Fund (CTPF) is to use targeted programming interventions to support the overseas element of this strategy.

The CTPF was initially established as a single Programme consisting of a wide range of projects to address terrorist threats overseas. In 2018/19, having grown in size, it was restructured into four ‘strands’, aligned to the four ‘P’s; Prevent, Pursue, Protect and Prepare; set out in CONTEST. The CTPF delivered activity across all Strands in 2019/20, in challenging, hazardous and uncertain environments worldwide.

In the course of the 20219/20 Annual Review of the CTPF, a substantive review has been undertaken of each of the strands:

- Strand 1 (Research, Information and Communications Unit (RICU) and Counter Daesh Communications Cell (CDCC),
- Strand 2/3 (Pursue), and
- Strand 4 (Joint Overseas Protect and Prepare, Aviation Security and Maritime Security)

The review also considered performance under the cross-cutting Enablers Programme, and across the Fund overall.

The strand-level reviews set out recommendations to be considered and implemented throughout the next financial year.