Annual Review - Summary Sheet

PROGRAMME TITLE: Counter-Terrorism Programmes Fund (CTPF): Strand 1 Programme
Country and Region:	MULTI-REGION
IATI Unique ID:	CSSF-01-000015
HMG Partners / (LEAD in bold)	CONTEST Unit, Home Office (HO), Foreign and Commonwealth Office (FCO), British Council, Ministry of Defence (MOD), Cabinet Office (CO)
Total Budget:	Financial information below Fund-level is redacted for security reasons. Fund-level financial information can be found on the Portfolio Summary sheet.
Budget this FY
Spend this FY
Original Programme Start Date: 01/04/2019		Planned End Date: 31/03/2020
Outcome Score: A		Risk: High
Output score: A

Summary of Programme Performance
(Programme performance for previous years was analysed for the CTPF as a whole – prior scores refer to CTPF as a totality, there is no dedicated score for Strand 1 before Financial Year 19/20).

Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	B	B		B		A
Risk Rating - low/medium/high	N/A	N/A	N/A		High		High
*output/outcome scores

What support did the UK provide in FY 19/20?

The UK’s Counter-Terrorism Strategy (CONTEST) aims to “Reduce the risk to the UK and its citizens and interests overseas from terrorism, so that people can go about their lives freely and with confidence”. The goal of the Counter-Terrorism Programmes Fund (CTPF) is to use targeted programming interventions to support the overseas element of this strategy.

Strand 1 Prevent - was the second largest of four strands within the CTPF in 2019/20. Its primary purpose was to reduce terrorist threats to the UK by reducing the causes of radicalisation, thereby diverting people from becoming terrorists or supporting related activity.

Delivery of the Strand 1 programme consisted of three complementary elements, which delivered thirteen interlinked projects:

- Funding for the Counter Daesh Comms Cell (CDCC) - the strategic communications arm of the Global Coalition against Daesh, focused on countering Daesh communications and providing a counter-narrative to terrorist propaganda.
- Funding for Research, Information and Communications Unit (RICU) International (now Prevent and RICU International) - focused on building understanding and capability on ‘Prevent’ issues and Countering Violent Extremism (CVE).
- Small-scale Countering Violent Extremism (CVE) projects - targeted at specific priority countries in North Africa, Middle East and Asia.

Summary of recommendations

- Continue to move reporting away from descriptions of activity towards capturing results achieved.
- Consider how the successful implementation of conflict and gender sensitivity approaches in some areas of the programme can be extended.
- Continue monitoring the impact of C-19 on future programming and develop risk tracking and mitigation strategies for this as well as other ‘black swan’ events.

- Continue to build on the Value for Money (VfM) successes achieved by working with other donors and undertake stakeholder mapping, which will aid sustainability planning.
- Continue to develop pilot programming in uncertain environments, with adequate consideration of risk.
- Programme staff should undergo additional commercial training to better understand commercial risks and potential mitigations.