Annual Review - Summary Sheet

PROGRAMME TITLE: Counter-Terrorism Programmes Fund (CTPF): Strand 2/3 Programme
Country and Region:	Multi-region
IATI Unique ID:	CSSF-01-000015
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), CONTEST Unit, Stabilisation Unit, Counter Terrorism Fund (SO15), Her Majesty’s Prison and Probation Service (HMPPS), Crown Prosecution Service (CPS), Joint Terrorism Analysis Centre (JTAC), Ministry of Defence (MOD)
Total Budget:	Financial information below Fund-level is redacted for security reasons. Fund-level financial information can be found on the Portfolio Summary sheet.
Budget this FY
Spend this FY
Original Programme Start Date: 01/04/2019		Planned End Date: 31/03/2020
Outcome Score: B		Risk: High
Overall output score: B

Summary of Programme Performance
Programme performance for previous years was analysed for CTPF as a whole – prior scores refer to CTPF as a totality, there is no dedicated score for strands 2 and 3 prior to Financial Year 19/20.

Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score		B	B	B	A	B	B	B
Risk Rating - low/medium/high			High		High	High	High	High
*output/outcome scores

What support did the UK provide in FY 19/20?
The UK’s Counter-Terrorism Strategy (CONTEST) aims to “Reduce the risk to the UK and its citizens and interests overseas from terrorism, so that people can go about their lives freely and with confidence”. The goal of the Counter-Terrorism Programmes Fund (CTPF) is to use targeted programming interventions to support the overseas element of this strategy.

The Strand 2 and 3 programme ‘Pursue’ was the largest of four strands delivered under the Counter-Terrorism Programmes Fund (CTPF) in 2019/20. It delivered 32 projects, working across 20 different countries, to support the following outcomes for CONTEST:

Strand 2: Reduce terrorist capability, by reducing terrorist groups’ access to personnel, including foreign fighters, vulnerable communities and individuals. Reducing terrorists’ ability to exploit virtual and real environments, including for dissemination of propaganda.

Strand 3: Illuminating and disrupting planned attacks by: building overt capability of key overseas partners to investigate and disrupt terrorist plots; Building capability of key overseas partners to conduct evidence-based prosecution; and improving overseas partners’ capacity to share overt investigatory information and evidence with UK authorities.

Interventions were categorised as follows:

- Targeted capability work in priority countries strengthening key Counter-Terrorism (CT) units and capabilities in partner governments – including CT investigation, detention, prosecution and judicial capacity, and terrorist threat assessment.
- Justice and Human Rights Pathways that work with host governments to develop a capable, sustainable, legal, and human-rights compliant Criminal Justice system resulting in an end-to-end pathway of investigations, prosecutions, trials and detentions.
- Funding for ODA-eligible activity carried out by Counter-Terrorism Police Liaison Officers.

Summary of recommendations

Increase level of training and support on finance provided to staff working on Strand 2/3 projects.

Strengthen risk management approaches due to the increased uncertainty created by COVID-19.

Develop core Programme and Project Management (PPM) capability. This should include rotating programme managers through the Introduction to CSSF Programme Management course.

Deepen contextual analysis by further use of regular technical assessments of conflict dynamics in fragile and conflict affected states.

Ensure teams overseas and in London are familiar with and adhering to updated governance structures to ensure prompt reporting.