Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Commonwealth 18-20 Fund: Fairness Programme
Country and Region:	Commonwealth
IATI Unique ID:	CSSF-01-000012
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department of Health and Social Care (DHSC)
Total Budget:	ODA: £19.5M		Non-ODA: £0
Total Spend:	ODA: £18.9M		Non-ODA: £0
Original Programme Start Date: April 2018		End Date: March 2020
Outputs					Score
Member states’ capacity to deliver on their commitments to create a fairer, more sustainable, prosperous, and secure future for their citizens is strengthened.					A
The Commonwealth increases practical solidarity and enhances cooperation between member states.					B
Overall output score					A
Outcome: Member states take new political, operational or legislative actions to deliver on their Commonwealth Heads of Government Meeting (CHOGM) 2018 commitments / Outcome Assessment: Evidence shows that member states have taken action to increase fairness making use of increased capacity, including significant steps towards legislative change, and there is a strong likelihood that they will do more, bringing sustained change that represents significant progress.
Final Outcome Score (Member state actions): A				Risk: Moderate
Outcome Assessment (Member States increase mutual support and coordination in international and regional organisations): / There is evidence of Commonwealth networks being strengthened through five of the ten projects which is likely to contribute to increased mutual support and coordination.
Final Outcome Score (Member state coordination): B

Summary of Programme Performance
Year	2018/19*		2019/20*
Programme Score	A	A	A	A
Risk Rating - low/medium/high	Medium		Medium

What support did the UK provide?
The Fairness programme was a group of 10 projects, with total funding of £19.25M. These programmes were as follows:
1. Building Fairer, More Equal and More Inclusive Commonwealth Societies (£5.6M)
2. Commonwealth Partnership for Democracy (£3.7M)
3. Improving Work Opportunities for Young People in the Commonwealth (£1.7M)
4. Time to Change Global (£1M)
5. Pacific Commonwealth Equality Project (£1.8M)
6. Commonwealth Electoral Observations (£1.8M)
7. Women Mediators across the Commonwealth Network (£2.4M)
8. Supporting Small States’ engagement with the multilateral human rights system
9. Commonwealth Forum of National Human Rights Institutions (£0.5M)

The support provided by these programmes varied in theme and mechanism of delivery. This included capacity building for institutions and civil society groups, conducting research, delivering knowledge sharing platforms, and training and mentoring individuals. The programmes were delivered in different geographies, but all aimed to strengthen institutions, civil society, and accountability mechanisms that promote and protect democracy, anti-discrimination movements, peacebuilding, human rights, and the rule of law.

What results did the programme deliver? Will they be sustained?
Almost all the planned activities in the second year of delivery were not overly affected by delays to the start of some projects experienced in the first year. Cancellation of several events in the final month of the programme were due to national responses to Covid-19. As much of the activity was capacity building, the majority of intended outcomes were not expected before March 2020. Nevertheless, all the projects delivered significant results, and in most cases significant outcomes can be expected over the longer term. Most of these will rely on continued funding, but, in some cases, they will be self-sustaining as a result of strengthened networks and legislative change. The most significant results include:
- Building Fairer, More Equal and More Inclusive Commonwealth Societies – New legislation was developed on domestic violence, harassment and discrimination in four Commonwealth countries. This is likely to have lasting benefits as well as providing a benchmark for other countries to follow. A group of over 30 experienced legal experts on equality and justice from the Commonwealth was established and has a strong internal momentum. An open access, online research database has been established with over 700 reports, policy papers and briefing notes relating to legal reform, women’s rights, LGBT rights and gender-based violence. Ten original research papers were also produced with analysis and recommendations to support reform in Commonwealth countries on a wide range of issues.
- Commonwealth Partnership for Democracy (CP4D) – at an international level, CP4D supported the updating of the Commonwealth Parliamentary Association Recommended Benchmarks for Democratic Legislatures (known as the Benchmarks) aligned with UN Sustainable Development Goal 16, and supported 12 parliaments to self-assess against the Benchmarks. This has built momentum towards further reforms and is likely to have a lasting impact. At a country level CP4D supported, for example, the enactment of legislation to include persons with disabilities in three Kenyan counties, training for new MPs in Sierra Leone on disability inclusion, and training for 3,000 student leaders in Ghana on parliamentary ethics and practices.
- Improving Work Opportunities for Young People in the Commonwealth (I-Work) – The I-Work project aimed to improve the employment prospects of young people, including those from disadvantaged backgrounds, by piloting and introducing new approaches to employer-led skills development. Technical assistance projects were implemented in four countries, supported at the highest levels of local and national government, and through engaging hundreds of stakeholders, employers and practitioners. In Ghana, the project focused on the development of a revised apprenticeship policy and accompanying implementation support. In South Africa, online digital guidelines for the delivery of apprenticeships were created. In Malaysia, intelligence gathered from the manufacturing sector shaped the creation of guidance for employers and training institutions. While in India, the project focused on the training of those in advisory roles in the apprenticeship system.
- Time to Change Global (TTC) – TTC ran pilot mental health campaigns to tackle the stigma and discrimination associated with mental health conditions in India, Kenya, Ghana, Nigeria and Uganda, trialling a concept that had been successful in the UK. By the end of 2019, over 100 Champions had been trained, and 3,422 social contact conversations were recorded between July and September 2019. In Nigeria, nine Champions received spokesperson training to support them in sharing their stories via media platforms. In Accra, Ghana, project coordinators worked in partnership with their local NGO partner, the Mental Health Society of Ghana, and the Mental Health Authority of Ghana to launch the ‘It Could Be You’ social marketing campaign. There is potential for this model to be applied more widely, drawing on the lessons learned.
- Pacific Commonwealth Equality Project (PCEP) – This project has accelerated progress on human rights in the targeted island states: nine countries have either strengthened their national human rights institutions or taken steps to establish them, while strengthening relationships and human rights networks across the region, including non-Commonwealth countries. A communications strategy started to shift perceptions on human rights, away from being a foreign imposed agenda and towards a culturally relevant concept. Young people involved in the project increased their awareness and advocacy for human rights. The Geneva-based UN Committee on the Rights of the Child held an extraordinary outreach event in Samoa in March 2020. During the event the committee heard directly from over 100 children and helped generate much greater public awareness and understanding of child rights. Progress has been made on a long-term change agenda which will require sustained engagement.
- Commonwealth Electoral Observations – The Commonwealth Secretariat (ComSec) provided election observation missions to eight countries, supported by project funding. Countries that have since undertaken reforms addressing recommendations from the Commonwealth Observer Group include Nigeria (improved regulations and guidelines for the conduct of elections) and Solomon Islands (enhanced electoral management bodies’ capacity and voting procedures). These reforms provide some evidence of the value to member states of ComSec electoral observations. Further observations will require continued funding. This work has been a core function of ComSec over several decades.
- Women Mediators in the Commonwealth (WMC) – A new network has been established, which represents a significant and sustainable achievement of the UK’s tenure as Chair-in-Office. Although it was a donor-initiated network, it has been taken up enthusiastically and now has 46 members, diverse in geography, age and experience. The desire of the members to take ownership through the steering group bodes well for its sustainability. Support networks were also established by members in Pakistan and Nigeria, which were unexpected additional outcomes. A ‘grassroots’ component had successes at a local level, but with little crossover with the network-building stream. There is some evidence of increased or strengthened participation of women in peace processes, although it is early for this to happen, and more tracking is needed as the network continues.
- Supporting Small States’ engagement with the multilateral human rights system – Nine Commonwealth small states have been able to increase participation in human rights mechanisms (fulfilling treaty body reporting obligations) with assistance from the Human Rights Advisers. Malawi is now up to date with its Universal Periodic Review. Guyana, Malawi, Sierra Leone, Solomon Islands and Vanuatu have increased their engagement in the Human Rights Council. Three HRC briefing sessions enabled all Commonwealth states to share information on HR initiatives and plan a Joint Commonwealth Statement on technical assistance at HRC42 (led by UK as Chair-in-office). Small states directly supported by the Human Rights Advisers - Vanuatu, Solomon Islands, Sierra Leone and Guyana - delivered 11 statements, compared to six statements at HRC40, and one statement at HRC41. Although progress has been made, future outcomes will depend on further funding.
- Commonwealth Forum of National Human Rights Institutions (NHRIs) – During the UK’s period as Chair-in-Office, the UK’s Equality and Human Rights Commission (EHRC) has chaired the Commonwealth Forum for National Human Rights Institutions. It helped build a more effective network of NHRIs across the Commonwealth and strengthened and developed NHRIs through peer-to-peer learning and by sharing expertise, including through a study tour of the UK by 12 Pacific Island country representatives. The Forum also developed an online learning product on LGBT rights, which was supported by the UN Independent Expert on Sexual Orientation and Gender Identity Rights. Progress was also made in establishing a permanent secretariat for the Forum, with a focus on governance, funding and legal staus. A permanent secretariat would help place the Forum on a more sustainable footing.

In closing the Fairness programme, the results of these projects will not be lost. In a number of instances, the implementing partners are looking to continue the projects through other funding mechanisms. Where projects are not continuing in any way, the lessons learned from this work will be carried forward by the implementing partners and applied to any future work.

What lessons have been learned?
- Grouping work on mental health, women and girls' rights and youth employment into a single Fairness programme meant that programme conversations have been heavily focused on process whilst conversations about the wider context and goals were done at the individual project level. In this context, strategic discussions at a programme level were challenging and are better held within the framework of the UK’s broader Commonwealth Strategy.
- A common theme in conversation with implementers was the challenge of delivering outcomes within a two-year timeframe, which in most cases was then considerably curtailed by finance and recruitment challenges. A longer timeframe for projects would allow for a more flexible and adaptive approach to programming, increase the likelihood of achieving lasting impact, and better value for money.
- The programme would have benefitted from an inception phase to agree approaches to reporting requirements and cross-cutting priorities such as gender, conflict sensitivity and monitoring value for money.
- Expert networks work best when administered according to mutually agreed goals, and with substantial diplomatic support for their deployment. This allows them to develop their own internal momentum and direction which is essential for sustainability.
- There is risk when contracting new consortia, as successful delivery depends on strong working relationships. During procurement, evidence should be sought of an existing working relationship, or of clear complementarity between the partners and of a mechanism for resolving internal disputes without having to escalate challenges to HMG.