Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Commonwealth 18-20 Fund: Prosperity Programme
Country and Region:	Commonwealth
IATI Unique ID:	CSSF-01-000010
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for International Development (DFID), Department for Education (DFE), Her Majesty’s Revenue and Customs (HMRC)
Total Budget:	ODA: £19.8m			Non-ODA: £0
Total Spend:	ODA: £19.4m			Non-ODA: £0
Original Programme Start Date: 01 April 2018		End Date: 31 March 2020
Outputs					Score
Member states’ capacity to deliver on their commitments to create a fairer, more sustainable, prosperous, and secure future for their citizens is strengthened.					A
The Commonwealth increases practical solidarity and enhances cooperation between member states.					B
Overall output score					A
Outcome: Member states take new political, operational or legislative actions to deliver on their Commonwealth Heads of Government Meeting (CHOGM) 2018 commitments / Outcome Assessment: The programme has delivered a broad range of capacity building support, with targets mostly met or very likely to be met through future funding. These have led to a number of actions by governments or relevant multilaterals that will show delivery of CHOGM commitments towards lowering the cost of trade. There have also been some tools set up to facilitate inter-Commonwealth communication and peer-to-peer learning, but it is too early to say whether these will prove sustainable in the long term.
Final Outcome Score: A			Risk: Medium

Year	2016/17	2017/18	2018/19*		2019/20*
Programme Score	N/A	N/A	A	A	A	A
Risk Rating - low/medium/high	N/A	N/A	Medium	Medium	Medium	Medium
*output/outcome scores

What support did the UK provide?
Through this programme, the UK provided funding to support delivery of commitments made by member states at CHOGM in 2018. A mix of Non-Governmental Organisations (NGOs), private sector consultants and multilateral bodies were contracted to provide expert assistance to help increase the capacity of targeted member states to deliver the following projects.
- Commonwealth Standards Network (DFID). The British Standards Institute (BSI) have set up a network of regulatory bodies to drive up consistent standards and thus economic and export performance (£5m).
- SheTrades (DFID). Providing support to Women Owned Businesses (WOB) with the aim of helping them to grow into companies that can export (£6.9m)
- Trade Facilitation (HMRC). Addressing barriers to cross-border trade by helping developing countries to implement the World Trade Organisation (WTO) Trade Facilitation Agreement (£3m).
- Supporting Small States to engage with the multilateral trading system – Trade Advisers (£0.5M)
- Queen Elizabeth Commonwealth Scholars (DfE). Funding masters scholarships for Commonwealth students at Commonwealth universities (£5m).

What results did the programme deliver? Will they be sustained?
The programme has delivered a broad range of outcomes and built capacity to deliver CHOGM 2018 commitments across the Commonwealth. Highlights and considerations for sustainability for each project include:
Commonwealth Standards Network (CSN): Five technical assistance programmes focused on building capacity of National Standards Bodies across the Commonwealth. For example, in Uganda this technical assistance has provided help for small scale agriculture producers on storing and transportation techniques leading to an increase in produce quality, allowing farmers to sell at higher prices and reduce waste. Forty-nine (of 53) Commonwealth countries signed up to the network, with a digital platform launched to encourage peer to peer learning. However, the platform will need continued support until it becomes self-sustaining, both in terms of business model and content generation. In addition, more time will be needed for the impact of the targeted technical assistance to be properly evaluated. To this end, a further £2.5m of UK funding was announced at a Commonwealth Trade Ministers Meeting in October 2019.

- SheTrades: Support was provided to over 3,000 WOB, connecting them to international markets and investment opportunities, creating over 3,300 jobs and generating £19m in sales for the businesses supported. In Ghana, the cabinet will review recommendations on how to mainstream gender into their Micro, Small and Medium Enterprises Plan. In Bangladesh and Kenya, ten private sector companies committed to reviewing their procurement and supplier policies through a gender lens. However, the cumulative effect on the business environment for WOB cannot be properly assessed until these changes have time to take effect. The programme initially aimed to generate £28m of additional exports from WOBs but more time is needed for business leads to translate into actual exports. In addition, the programme included the roll out of an online platform (SheTrades Outlook) to promote co-operation between WOBs; its impact could not be assessed in this review.
- Trade Facilitation: Tailored Trade Facilitation Agreement (TFA) implementation roadmaps were developed in eleven Commonwealth countries (Antigua and Barbuda; Bangladesh; Belize; eSwatini; Guyana; Lesotho; Malawi; Rwanda; Sierra Leone; Tonga; and Zambia). In November 2019, a National Trade Facilitation Roadmap was launched in Zambia. This provides a framework for a five-year reform programme that is designed to improve regulation, generate more efficient customs procedures and reduce the cost of doing business and trade.

Supporting Small States to engage with the multilateral trading system – The Trade Advisers have helped Commonwealth Small States to better monitor WTO workstreams, interpret WTO rules for their own domestic contexts, and understand the implications of WTO negotiations for their national economies. Support provided by the Advisers covered not just traditional areas of WTO work (e.g. tariffs and agriculture) but also new areas such as investment, intellectual property, anti-dumping and countervailing measures, trade and climate change. Although progress has been made, future outcomes will depend on further funding.

Queen Elizabeth Commonwealth Scholarships (QECS): Scholarship programmes were expanded, with universities in three additional countries (Malaysia, Namibia and Zambia) hosting scholars. Seventeen universities offered discounted schemes and 26 new scholarships were supported. The impact of these scholarships will only be felt once scholars have completed their studies and are in positions to help deliver CHOGM commitments and leverage cross-Commonwealth networks. This will be tracked by the DfE and FCO.
What lessons have been learned?
Much of the activity for this programme has clear alignment with the DFID Trade for Development and Department for International Trade objectives. The three projects (excepting scholarships) combine well to address barriers at strategic (CSN), tactical (Trade Facilitation) and operational (SheTrades) levels. The programme team recognised, however, more could have been done to use the FCO network to give the programme more visibility.

Programmes like this are better focused on reducing barriers to trade in general. The barriers and problems identified and tackled are not unique to the Commonwealth, and therefore work on promoting intra-Commonwealth should complement and be coherent with the UK’s wider global trade policy.

The UK should work with other donors and the Commonwealth Secretarait to explore how programmes and their results and achievements can become more sustainable and, in the longer-term, self-sustaining.

Further evaluation of the programme and its outcomes is recommended ahead of the next CHOGM to assess their effectiveness and impact.