Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Commonwealth 18-20 Fund: Security Programme
Country and Region:	Commonwealth
IATI Unique ID:	CSSF-01-000011
HMG Partners / (LEAD in bold)	Home Office (HO), Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £13M			Non-ODA: £0
Total Spend:	ODA: £8,810,711			Non-ODA: £0
Original Programme Start Date: 1 April 2018		End Date: 31 March 2020
Outputs					Score
The Commonwealth increases practical solidarity and enhances cooperation between Member states					B
Governments have increased capacity and understanding of their security needs and good practice they could apply					A
Overall output score					A
Outcome Assessment: The programme has contributed strongly to its expected outcome across all three Commonwealth Heads of Government Meeting (CHOGM) 2018 security thematic areas: cyber security, modern slavery and online child sexual exploitation. The programme supported member states and regional and international networks to enhance their capacity and skills to address and respond to these security issues. The programme struggled with programme management challenges related to short implementation time frame and individual project compliance, but successfully maintained line of sight to deliver against the CHOGM 2018 commitments.
Final Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	-	-	-	-	B	A	A	A
Risk Rating - low/medium/high					Medium	Medium	Medium	Medium
*output/outcome scores

What support did the UK provide?
£5.5M of funding for 15 cyber security projects that build cyber security capacity in low- and middle-income Commonwealth countries in line with the Commonwealth Cyber Declaration - implemented through FCO.

£2.4M of funding for two projects that support Commonwealth member states to tackle modern slavery and trafficking, principally through improved law enforcement, criminal justice responses, and legislative reform - implemented through Home Office.

£1.1M to tackle Online Child Sexual Exploitation (OCSE) by strengthening regional and national capacities in Africa and Sri Lanka - implemented through Home Office.

What results did the programme deliver? Will they be sustained?
The Cyber Security Programme in partnership with the World Bank completed national cyber security capacity reviews for seven countries: Gambia, Mauritius, Lesotho, Botswana, Namibia, Sri Lanka and Nigeria, helping the Commonwealth make progress towards its goal of all countries completing a review by CHOGM 2020. These reviews will help countries to inform national strategies and prioritise investments.
- In Latin America and Caribbean Commonwealth countries, UK funding has enabled the creation of online safety websites, specifically supporting vulnerable groups in society, that attracted almost 500,000 hits. Additionally, offline advertising reached more than one million people.
- In collaboration with Singapore’s Cyber Security Agency (CSA) the Commonwealth Cyber Security project convened a network of experts from 40 Commonwealth member states to establish a national cyber security response team (nCSIRT) . The network aims to enhance capacities of member states through shared knowledge for better detecting and mitigating cyber attacks.
- The Modern Slavery project implemented by Commonwealth Parliamentary Association (CPA) UK reached out to over 100 parliamentarians and parliamentary officials across Commonwealth member states providing practical advice to develop and strengthen modern slavery legislation across their jurisdictions. A network of 32 parliamentary champions across the Commonwealth committed to sharing information and advancing modern slavery-related legislation. Support was also provided to parliamentarians in Nigeria and Uganda to strengthen and advocate the passing of new/amended anti-slavery legislation. This project was commended in the 2019 US Trafficking in Persons Report for using a tailored approach to each country’s needs and capacity.
- The Anti-Human Trafficking project implemented by the United Nations Office on Drugs and Crime (UNODC) supported Malawi to establish District Committees against Trafficking in Persons in Michinji and Phalombe. The Committees coordinate identification of victims and investigations in border areas significantly affected by human trafficking flows. The project also supported Malawi to adopt four landmark regulations developed jointly by the Government of Malawi and UNODC: the Prevention of Exploitative Labour Recruitment Regulations; Standard Operating Procedures and National Referral Mechanism to the Trafficking in Persons Act; the Trafficking in Persons Fund Disbursement Regulations; and the Witness Protection Regulation. In Zambia, an updated National Action Plan was adopted at the Annual Review meeting of the Inter-Ministerial Committee on Human trafficking of 2019 and is now in force.
- The African Union (AU) Commission brought together Commonwealth and other AU member states across Africa to enhance policy and institutional response against Online Child Sexual Exploitation (OCSE). Nineteen countries including 12 Commonwealth member states have signed up to the WePROTECT Global Alliance (WPGA) to implement the Model National Response (MNR) against OCSE.
- The Tackling OCSE project in Sri Lanka, implemented by ECPAT (End Child Prostitution in Asian Tourism) Sri Lanka, developed and introduced a national training curriculum to raise awareness and enhance skills among youth for safer online activity and experience. Sri Lanka’s National Youth Services Council (NYSC) adapted the training curriculum into a wider training programme conducted annually by the NYSC.

What lessons have been learned?

The Commonwealth 18 – 20 Fund was set up to deliver commitments made at the April 2018 CHOGM. As this programme was brought into the CSSF at a later stage, projects were subsequently adapted to comply with CSSF programme management rules and guidelines. One significant consequence was that many of the CSSF requirements on the format and content of reporting and cross-cutting priorities such as gender and conflict sensitivity were unfamiliar to both lead departments and implementing partners. Progress was made throughout the year on reporting compliance, although remained weak on the cross-cutting thematic issues. The programme would have benefitted from an inception phase to set-up project compliance before commencing implementation.

The programme had a much stronger focus on achieving its outcome as compared to the first year. All projects were slow to start but, after overcoming problems related to initial set-up, the overall programme picked up significant pace in second year of implementation.

The objective on cooperation between members states was slow to gain traction, though it was more apparent in projects with specific networking components, such as Cyber Security and OCSE in Africa.

Customised plans with partner parliaments proved to be an effective approach as these recognised and accounted for different needs and cultural contexts, which was fundamental for designing the right support for each legislature. Strong and trusted relationships were also key for successful project delivery.

Project stakeholders benefited from peer learning and hearing from counterparts in similar contexts, in addition to working with experts from within the Commonwealth and beyond. This was an important consideration in the design of learning workshops.

In the context of the COVID-19 pandemic, support on cyber security and preventing online child sexual exploitation become more relevant as the online presence of children and youth typically increased during lockdowns. The achievements of, and momentum built by, this programme present good opportunities for the UK and others to continue working on issues around modern slavery, cyber security and online child sexual exploitation.