Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Commonwealth 18-20 Fund: Sustainability Programme
Country and Region:	Commonwealth
IATI Unique ID:	CSSF-01-000013
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for Environment, Food and Rural Affairs (DEFRA), Department for International Development (DFID)
Total Budget:	ODA: £29.1M			Non-ODA: £0
Total Spend:	ODA: £28.4M			Non-ODA: £0
Original Programme Start Date: April 2018		End Date: March 2020
Outputs					Score
Member states’ capacity to deliver on their commitments to create a fairer, more sustainable, prosperous, and secure future for their citizens is strengthened					A
The Commonwealth increases practical solidarity and enhances cooperation between Member states					B
Overall output score					A
Outcome: Member states take new political, operational or legislative actions to deliver on their Commonwealth Heads Of Government Meeting 2018 commitments / Outcome Assessment: / The programme has delivered a broad range of capacity building support, with outputs having led to a number of actions by governments or relevant multilaterals that show delivery of Commonwealth commitments towards a more sustainable future. The evidence that this has led to an increase in mutual support and co-operation is less clear and will need to be assessed over time and after further Commonwealth meetings have take place.
Final Outcome Score: A			Risk: Moderate

Summary of Programme Performance
Year	2017/18*		2018/19*		2019/2020*
Programme Score	N/A	N/A	A	A	A	A
Risk Rating - low/medium/high	N/A	N/A	Medium	Medium	Medium	Medium
*output/outcome scores

What support did the UK provide?
Through the Sustainability Programme, the UK made £29.1M available to support delivery of commitments made by member states at the Commonwealth Heads of Government Meeting (CHOGM) in 2018. A mix of NGOs, private sector consultants and multilateral bodies were contracted to provide expert assistance to help increase the capacity of targeted member states to deliver the following projects:
- Disaster Risk Finance (DRF) (DFID). World Bank technical assistance to strengthen the financial preparedness of Small Island Developing States (SIDS) in the Caribbean ahead of natural disasters (£2.3m).
- Eliminating Blinding Trachoma (DFID). Implementing the World Health Organisation (WHO) strategy to treat trachoma, a disease of the eye caused by bacterial infection that can lead to a condition called trichiasis (£7m)
- Digital Identity (DFID). Addressing the digital gender gap in seven Commonwealth countries and working with mobile operators to bridge those gaps (£0.7m).
- Pacific Nationally Determined Contributions (NDC) Hub (FCO). Creating a hub of technical excellence in Fiji that will support Pacific Islands to tackle climate change (£1.1m)
- Commonwealth Marine Economies (FCO). Support for 17 Small Island Developing States (SIDS) to develop sustainable, diverse marine economies (£12.1m).
- Commonwealth Litter Programme (DEFRA). Developing Marine Litter Reduction Action Plans for four Commonwealth member states (£5.9m).
What results did the programme deliver? Will they be sustained?
The programme has delivered a broad range of outcomes and built capacity to deliver CHOGM 2018 commitments across the Commonwealth. Highlights and considerations for sustainability for each project include:

Disaster Risk Finance. Four countries carried out assessments of their disaster risk financing strategies, with Jamaica moving forward to implement an actual instrument. Jamaica secured $16m as a grant from the UK and German Global Risk Financing Facility (GRIF) to contribute to payments for premiums on a new catastrophe bond (like insurance) which would provide financial cover for the Jamaican government, paying out when natural disasters hit the island and providing cash for rapid response and rebuilding. Unfortunately, COVID-19 and its effect on the financial markets caued a delay but the bond is scheduled to launch in advance of the 2021 hurricane season. FCDO will continue to support technical assistance in the region.

- Blinding Trachoma. Today there are 9.8m people at risk of infection in Nigeria and 120,000 active cases, with numbers expected to fall dramatically during 2020 (pre-Covid 19 forecast). This programme has contributed to providing 8.3 million treatments through drug administration to reduce the prevalence of Trachoma, whilst managing 27,400 cases of trichiasis and promoting behaviour change to reduce risk of the disease spreading. Elimination of trachoma in Nigeria is close, delivering on a major CHOGM 2018 commitment.
- Digital Identity. In Nigeria, a mobile operator developed an economic ID product to verify small business identity and increase trust with customers, suppliers and service providers, enabling them to access credit. In Zambia, the government has stated its intention to partner with mobile operators to digitise their civil registration system. The knowledge gained from these achievements will enable them to support other countries. Research conducted in seven countries identified barriers to economic participation for women that can be bridged by digital solutions. FCDO has incorporated lessons from this project into its strategic partnership with the project partner, GSMA.

NDC Hub. The Hub was formally launched in 2019 and has successfully positioned itself as the leading initiative on climate change in the Pacific, providing a platform for members to talk with a unified voice on the international stage. Workplans for nine Commonwealth member states in the Pacific were agreed to enhance their NDCs. The Hub has regional ownership, with countries recognising the need to drive the Hub activity. Communication efforts and knowledge sharing have enhanced the visibility of the Hub in the region and with international partners. Phase two of the hub will be funded by Germany. This will cover development and implementation of NDCs, implementing the workplans agreed with UK funding.

Commonwealth Marine Economies (CME). Through the provision of key equipment and capacity building programmes, 13 nations now have the ability to undertake seabed mapping, monitor ocean acidification and sea level rise, or collect tidal data. For example, in Kiribati, the mapping of 32 islands and atolls has not only enabled safe navigation for maritime trade but has catalysed a £30 million World Bank/Asian Development Bank infrastructure project. In St Lucia, work on aquaculture has stimulated the creation of an industry to sustainably farm spiny lobsters. Draft bespoke national Maritime Economy Plans have been shared with Antigua and Barbuda, Belize, Fiji, Grenada, Guyana, Papua New Guinea, Tonga, and Tuvalu. These will assess existing maritime economies and identify opportunities for and obstacles to development, which those countries can use to drive economic growth and alleviate poverty. These plans are expected to ensure the CME Programme leaves a lasting legacy by helping nations to chart a sustainable course towards prosperity for their people and protection of their ocean.

Commonwealth Litter Programme (CLiP). Following support delivered through CLiP, including development of marine litter action plans , setting up micro-plastic laboratories and providing training for local scientists, Commonwealth countries have taken strong action on plastic pollution. For example, CLiP-generated evidence supported Vanuatu in banning six types of single use plastic, and the Belize government in passing legislation prohibiting the use of a range of single use plastics and Styrofoam items. Programming will continue, eventually moving to a DEFRA baseline from 2021/22.

What lessons have been learned?
- Elements of this programme contributed to DFID and Prosperity Fund programmes. This created duplicate reporting requirements. It would be more efficient to have a single funding source for each of these projects, potentially transferring budget to a single department or fund.
- When working with implementers who are new to CSSF, the requirements for monitoring and evaluation (particularly designing a theory of change and results framework), value for money, and gender and conflict sensitivity, should all be highlighted at the start and potential capacity deficits identified and addressed.
- Grouping work on health, climate change, economic inclusion and oceans into a single sustainability programme meant that programme conversations became heavily focused on process whilst conversations about the wider context and goals were done at the individual project level. In this context, strategic discussions at a programme level were challenging and are better held within the framework of the UK’s broader Commonwealth Strategy.
- CLIP has benefitted from very clear policy direction that flowed directly from CHOGM and the creation of the Commonwealth Clean Ocean Alliance. This meant delivery of outcomes aligned with commitments made at CHOGM, facilitated by the fact that the implementer (Cefas) is an arm's length body of DEFRA, enabling greater policy direction.
- There is considerable overlap between work on oceans and climate change, but within this programme the goals were made distinct enough to require separate projects and avoid duplicative work.