Annual Review - Summary Sheet

PROGRAMME TITLE: Ukraine Programme
Country and Region:	Ukraine, Eastern Europe
IATI Unique ID:	CSSF-05-000004
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MOD), National Crime Agency (NCA), Her Majesty’s Revenue and Customs (HMRC)
Total Budget:	ODA: £13,993,347			Non-ODA: £3,830,000
Budget this FY	ODA: £13,993,347			Non-ODA: £3,830,000
Spend this FY	ODA: £13,535,307			Non-ODA: £3,734,137
Programme Start Date: 1 April 2019		Planned End Date: 31 March 2020
Outputs					Score
Conflict programme outputs					A
Rule of law programme outputs					A
Special defence adviser outputs					A
Overall output score					A
Outcome Assessment: The Ukraine programme delivered mostly strong results across its outcomes for the 19-20 year, supported by good efforts to review and adjust the programme around very fluid contextual factors over the year. Due to restrictions caused by COVID-19, this review was light-touch and desk-based. It looked at all outcome-level results and progress and made a summary assessment at output level against performance overall.
Outcome Score: A			Risk: Medium/High

Summary of Programme Performance
Year	2015/ 16	2016/ 17	2017/18*		2018/19*		2019/20*
Programme Score	B	B	B	B	A	A	A	A
Risk Rating - low/medium/ high		Medium	Medium	Medium	Medium	Medium	Medium/ High	Medium/ High
*output/outcome scores
How has the programme changed during this period?			With the arrival of a new Ambassador during the year, a strategic review process was undertaken in large part to ensure the programme aligned with shared UK and Ukrainian interests. The results of this began to be implemented during the year: the focusing of the programme portfolio on priority areas, leading to some programmes being phased out. This also adjusted programme governance structures and processes with the introduction of post programmes and strategy groups, and cross-cutting groups focused on areas such as gender and Women, Peace and Security (WPS).

What support did the UK provide in FY 19/20?
- CSSF continued to support the UK’s objective to ensure a united, stable, sovereign and resilient Ukraine. This was the third and final year of the Ukraine CSSF programme in its current form.
- In financial year 2019/20, the UK government provided over £37m of support across different funding streams focused on seven priority areas: anti-corruption; governance and reform; communications; education and culture; conflict, stability and security; human rights; and humanitarian.
- The programme built on previous years’ support to help Ukraine create an accountable and prosperous state, with a government able to make essential reforms, building its resilience to external aggression and destabilisation and supported by a united international community.
Following the establishment of a new Ukrainian government, the programme adapted to political developments, flexing support to meet ministerial requests for increased support on strategic communications and its wide-ranging package of reforms.

Key results for FY 19/20:

The programme:

- Increased the number of shelters for victims of domestic abuse across Ukraine and funded legal aid training to secure the first conviction of Domestic Violence perpetrators in Ukraine. The UK continues to be the largest donor in combating Gender Based Violence (GBV).
- Improved access to pensions and social benefits for Internally Displaced Persons (IDPs). Over 390,000 children were registered as Conflict Affected Children enabling them to receive state benefits.
- Trained over 160 government and civil society representatives in dialogue facilitation and funded the first conference on national mediation and dialogue initiatives in Ukraine for Government and civil society experts.
- Saved the UK taxpayer approximately £130-150 million through successful operations against Serious and Organised Crime (SOC).
- Improved the ability of Ukraine’s Cyber Police to detect and prevent crime.
- Continued to build the resilience of the Ukrainian Armed Forces through the Operation Orbital non-combat training mission.
- This financial year was also marked by NATO recognition of the success in reforming the Ministry of Defence’s Internal Audit Department.
- Funded the start-up of a lifesaving veterans’ suicide prevention hotline and established a support network to signpost critical health and employment services for veterans and their families.
- Surpassed land mine clearance targets and led international lobbying on humanitarian mine action, which prevented backsliding on the Mine Action Law.
- Provided Strategic Communications support to the Ukrainian Ministry of Foreign Affairs and established a communications team within the Cabinet of Ministers to produce high quality communication messaging and combat disinformation.
- Contributed towards strengthened public trust in the democratic process by financing the second largest contingent of international monitors for the 2019 Presidential and parliamentary elections.

Key Lessons
Improved strategic focus was required: At the end of the year, new governance arrangements in the Embassy were trialled to ensure better delivery of UK objectives in Ukraine through programmes. A monthly Post Projects Board chaired by the Deputy Head of Mission considers project approvals and programme management issues.  A Post Strategy Board, chaired by the Head of Mission, sets strategic objectives for the whole mission to work towards. In addition, thematic Delivery Groups were established to co-ordinate activity across all FCO teams and other government Departments represented at post.  This approach has been expanded into a new integrated delivery system in the following year.
- Greater integration of CSSF and Good Governance Fund (GGF) resulted in more effective programming. An integrated CSSF and GGF finance process was developed to improve financial risk management and mitigation at a portfolio level.  In addition, a revised approach to risk was established across Ukraine programmes to enable more detailed tracking at both the project and portfolio level.  Risks are now discussed on a quarterly basis at the Post Projects Board with severe or changing risks escalated to the Post Strategy Board. This approach improved risk mitigation and was tested under pressure during the COVID-19 pandemic.
- Cross-Embassy working groups can improve deliver of cross-cutting priorities. The Gender Equality Working Group is a good example of this approach which has secured cross Embassy buy in and raised awareness (and confidence) amongst colleagues to discuss gender equality issues.  Currently every section of the Embassy is represented within the Gender Working Group which has resulted in a more efficient approach to gender equality in the Embassy.
- Early engagement with FCO’s Portfolio Management Office ensured efficient procurement of novel programme ideas. CSSF worked closely with the FCO’s portfolio management office (PMO) and commercial colleagues to produce procurement guidance for implementing partners, clearly setting out processes.
- A revised tendering process improved the quality of applications for funding from potential implementers. This year, CSSF Ukraine ran its first Call for Bids, developing a tracker and assessment matrix to improve future tenders.  Holding joint fund implementer events, taking time to explain UK policy objectives and working, improved the quality of applications from local non-governmental organisations (NGOs).

Summary of Recommendations for FY 20/21

1. Results Framework: The programme level results framework must be maintained and completed, especially at year end, to show the totality of delivery against intended targets.
2. Value for Money (VFM): VFM assessments should capture the value of work that influences the views and behaviours of stakeholders. The team should seek to ensure that where projects receive funds from different funding pots there is no requirement to complete multiple financial and progress reports.
3. Human Rights: Human Rights promotion and do no harm should be a more prominent feature in the design, delivery and reporting of projects.
4. Cross cutting issues: Both conflict and gender considerations are central to the Ukraine CSSF agenda. Both would benefit from better monitoring at the project level using conflict-sensitivity monitoring tools and gender mainstreaming indicators.
5. Influence, engagement and secondary benefits: The benefits of influencing and engagement activity were not fully captured, assessed, understood, used and responded to. The CSSF programme team should work with central teams to develop use of available tools to measure the impact they are having and ensure increased impact in future programmes.