Annual Review - Summary Sheet

PROGRAMME TITLE: Good Governance Fund
Country and Region:		Armenia, Bosnia and Herzegovina, Georgia, Moldova, North Macedonia, Serbia and Ukraine
IATI Unique ID:		GB-1-205101, GB-GOV-1-300251, GB-1-205093
HMG Partners / (LEAD in bold)		Department for International Development (DFID), Foreign & Commonwealth Office (FCO)
Total Budget:		ODA: £180m			Non-ODA: n/a
Budget this FY		ODA: £37.5m			Non-ODA: n/a
Spend this FY		ODA: £36.8m			Non-ODA: n/a
Original Programme Start Date: FY 2016/17				Planned End Date: September 2021
	Outputs					Score
International Financial Institutions, Multilateral and other donor projects	Output 1.2 IFI interventions that support reform of tax systems and improvements to the business environment in partner countries					A
	Output 1.3 Interventions that support rule of law and democratic accountability					A+
	Output 1.4 Interventions that support public finance management reform and anti-corruption measures in partner countries					A
Managed Fund	Output 2.1 Well targeted, adaptive technical assistance provided by Managed Fund projects to support growth, governance and accountability. The Managed Fund employs an adaptive approach through sharing learning and knowledge from the programme on an ongoing basis and scaling up projects where traction is being gained.					A
Strategic Support Fund	Output 3.1 SSF Interventions that support liberalisation in partner countries					A+
	Output 3.3 SSF Interventions that support rule of law and democratic accountability					A+
	Output 3.4 SSF Interventions that support public finance management reform and anti-corruption measures in partner countries					A+
	Output 3.5 SSF Interventions that support the strengthening independent media and strategic communications in partner countries					A
Average Output Score					A
Outcome Assessment: Programme meeting expectations
Outcome Score: A			Risk: Major

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score		A	A-B		A		A
Risk Rating - low/medium/high		High	High		High		High
*output/outcome scores
How has the programme changed during this period?			Objectives and programme set-up substantially unchanged

What support did the UK provide in FY 19/20?

The Good Governance Fund (GGF) provided technical assistance in Armenia, Bosnia and Herzegovina, Georgia, Moldova, North Macedonia, Serbia, and Ukraine. Assistance was in support of governance and economic reform in areas of: liberalisation and modernisation of key growth sectors; reform of tax systems and improvements to the business environment; strengthening rule of law and democratic accountability; public finance management reform and anti-corruption; strengthening independent media and strategic communications. Support was provided through three strands, namely: Strand I supported activities with International Financial Institutions (IFIs), multilateral and other donors; Strand II a demand-led managed fund, largely responding to needs identified by government counterparts; and Strand III a Strategic Support Fund (SSF), usually supporting small initiatives by non-governmental organisations.

Key results for FY 19/20:
The Good Governance Fund delivered 115 projects during this reporting period, some of which are on-going. The following is a sample of key outcome results:
- The Women in Politics project in Armenia trained close to 400 women during pre-electoral activities, with 18 women being elected to Local Office (60% of supported candidate women running in elections), despite cultural resistance to female leadership in many communities.
- The Local Investment-Friendly Environment project in Bosnia and Herzegovina facilitated the adoption of all necessary legislation for a “one-stop-shop” for business registration and online registration in the Republika Srpska (Serbia) contributed to increasing the number of registered businesses by 15%, increasing the competitiveness of the private sector by reducing costs for businesses (by $5.5m) and to $50m investment generated.
- Support to Public Administration Reform in Georgia led to the strengthening of the policy making process and introduced a “whole of government approach” in national level policy development and coordination. Over 1,600 civil servants were trained in different disciplines, and uptake of e-governance platforms increased the number of citizens using e-services from 154,396 in 2018 to 305,168 in 2019.
- The Media Enabling Democracy, Inclusion and Accountability project in Moldova helped create a more independent and professional media sector that is more resilient to political and financial pressures. Key results are all supported media outlets increasing their online audience reach, variably from 15% to 560%, and achieving important business milestones like net positive cash balance and an increase in paying subscribers.
- The work on resolving non-performing loans (NPL) in financial institutions in Serbia led to a reduction of the NPL ratio from over 20% in 2015 to less than 5% to date, generated an inflow of over €11m (£9.4m) to the state budget and prepared the way for a further estimated €90m (£76.9m) inflow in 2020.
- GGF projects in North Macedonia unlocked a large-scale European Union (EU) intervention to support implementation of a new organic budget law, while GGF-supported deliverables in the justice sector have been used by the EU to support capacity building and are expected to be used by the government in the EU accession negotiations.
- The labour code reform project in Ukraine successfully responded with agility and discretion to the new government’s needs to design holistic, inclusive reforms to the Labour Code. These should help deliver a more flexible and competitive labour market which attracts external investments, reduces informal employment, stimulates job creation and facilitates economic growth.

Across the board, the GGF has delivered its mission, delivering smart and impactful project results in all three strands, often working with synergy across strands and opportunistically at pace with sometimes politically volatile contexts. This is evident in how Posts have responded rapidly with agility to support governments’ reform priorities in response to EU accession criteria in North Macedonia and Serbia. Additionally, this was demonstrated in Ukraine, where a reform-minded but inexperienced government’s need for immediate assistance was met. The GGF has also used a myriad of approaches and vehicles shaped by need and context. For example, the GGF works with IFIs in Bosnia and Herzegovina to promote economic growth whilst linking these activities to SSF projects that offer direct access to the centre of a government presiding over a “captured state” phenomenon with near-gridlocked political institutions. This volatility of the political context, and the impending COVID-19 crisis, have stalled progress in some countries such as Moldova, and projects, for example in Armenia. In response, GGF teams and implementing partners have flexed, adjusted or paused projects where needed. In Moldova, the GGF team identified areas subject to less political interference and where there is greater political commitment and ownership of reforms within selected public sector agencies. In Armenia, the implementing partner of an SSF project clearly used the COVID-19 crisis as an opportunity to build back better, while quickly adjusting to the situation by introducing online courses and online platforms to access international markets. Looking ahead, COVID-19 will have a massive and long-lasting impact on economies so economic resilience and reforms will be critical. The GGF should pivot smartly to support governments to prepare and overcome the economic consequences of the crisis, spearhead rapid digitisation of public services, and respond to requests for more transparency and accountability from the citizens.

The operating mechanisms of the GGF have strengthened since the last review but challenges which hamper delivery remain. Risk management improved with systematic, regular and periodic review of risks by colleagues at embassies and Joint Unit, and established processes were impacted through staff turnover. While the overall quality of monitoring and evaluation (M&E) arrangements has improved, the quality of the project results frameworks is variable. Strand II operations were impacted by procedures around commercial procurement causing uncertainty, and impacting future planning.

Key Lessons
- Strong integration of GGF with the political work of embassies supports a strategic approach to programming, effective risk management, and effective political action by Embassy helps to reinforce programme objectives or overcome obstacles when needed.
- Gender equality and social inclusion (GESI) needs to be considered from project scoping and design onwards in order to ensure effective integration. Strategies that have helped to strengthen gender mainstreaming include (sectoral) gender analysis to identify concrete entry points for interventions, Senior Management leadership at Post on gender, and Gender Champions at Post.
- All GGF staff should be fully familiar with the strengths and limitations of different IFI partners,
- More joint funded programmes with other donors working in GGF target countries under Strand I may help to reduce the management load on the GGF team.
- Working with non-political independent institutions, trusted partners and civil society organisations can help to navigate periods of political uncertainty and change.
- The extent to which synergies exist between delivery strands varies across country portfolios.
- Close cooperation and engagement between GGF teams in neighbouring countries on Theory of Change (ToC) review and sharing of experience contributes to mutual learning.
- The COVID-19 crisis has revealed potential niches for interventions: supporting public authorities to overcome the economic consequences of the crises, rapid digitisation of public services, requests by citizens for more transparency and accountability.

Summary of Recommendations for FY 20/21
- With support of the independent Monitoring, Evaluation and Learning (MEL) provider, invest in the development of adaptive country results frameworks, that integrate Value for Money (VfM) and gender-sensitive indicators, to help aggregate results and monitor medium-term change, and explore the possibility of introducing common indicators/ metrics.
- Explore additional means to create synergies and collaboration across GGF strands, and alignment and synergy with other HMG programmes, so that all strands and their implementing partners can coordinate to deliver country objectives as laid out in the country ToC.
- Strengthen and clarify GGF minimum standards for all delivery strands covering VfM, GESI, M&E, and reporting. Use of independent MEL provider to offer capacity building support.
- Continue to invest in building GGF team capacity on GESI to ensure all team members are comfortable challenging partners/ counterparts on gender and disability inclusion.
- Value for money (VFM) of the programme and resulting VFM training to be explored.
- Exploration of systematic and effective risk management with all implementing partners, including. “Refresher” training on risk monitoring and risk management, where applicable.
- Set up additional mechanisms for sharing country level lessons (including those generated as part of MEL work), to include the key findings of Governance and Economic Network meetings and ensure that learning is integrated into new programming.
- Review which projects completed under the current phase of GGF require further monitoring and/or follow-up (e.g. to advocate for recommendations to be reflected in legislation) and agree who will be responsible for this follow-up.