Annual Review - Summary Sheet

PROGRAMME TITLE: Western Balkans CSSF Serious and Organised Crime (SOC) Programme
Country and Region:	Western Balkans (WB) – Albania, Bosnia and Herzegovina (BiH), Kosovo, Montenegro, North Macedonia, and Serbia
IATI Unique ID:	CSSF-10-000004
HMG Partners / (LEAD in bold)	Home Office (HO), HM Revenue and Customs (HMRC), National Crime Agency (NCA), Crown Prosecution Service (CPS), Foreign & Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget :	ODA: £6,500,000			Non-ODA: N/A
Budget this FY	ODA: £6,500,000			Non-ODA: N/A
Spend this FY	ODA: £6,393,000			Non-ODA: N/A
Original Programme Start Date: April 2019		Planned End Date: March 2022
Outputs					Score
Capacity/capability developed to mitigate the threats of serious and organised crime (Pursue and Protect)					B
Intelligence gathering and sharing mechanisms developed (Pursue and Protect)					B
Criminal justice & law enforcement system enhancements supported (Pursue and Protect)					B
Knowledge and decision-making supported (Prepare)					B
Overall output score: B					B
Outcome Assessment: Positive activity at project-level is not consistently or coherently captured to meet the ambition of the Programme. Rationalization of either outcome-level ambition or improved coherence of output-level activity required for programme to reach potential.
Outcome Score: B			Risk: M

Year	19/20	20/21	21/22	22/23	24/25
Programme Score	B/B	-	-	-	-
Risk Rating - low/medium/high	Medium	-	-	-	-
*output/outcome scores
How has the programme changed during this period?			2019/20 was the first year in which the Western Balkans CSSF SOC programme was a standalone programme instead of operating as a strand within the broader Western Balkans CSSF programme.

What support did the UK provide in FY19/20?

The majority of programme activity consisted of bilateral engagement, seeking to improve regional criminal justice systems and through the deployment of HMG operational experts to engage in mentoring/training and proposing system reform. The Home Office (HO) also ran a bespoke project to deter individuals from involvement in SOC. The programme dedicated some funds to multilaterals (e.g. UN agencies), and promoted regional systems designed to tackle SOC (e.g. the Small Arm and Light Weapons multi-partner Trust Fund). There was also some support provided to civil society and not-for-profit organizations, seeking to increase knowledge of and evidence relating to SOC dynamics in the region.

2019/20 was the first year in which the WB SOC Programme ran as a standalone Programme.

Key results for FY 19/20:
- An innovative Albania Prevent pilot project commenced in Albania. The first activity under the pilot engaged over 4,220 students in eight schools in targeted areas in North Albania, paving the way to assist the Government of Albania to design and deliver a context-specific SOC Divert Educational Toolkit.
- Support to the Berlin Process Security Commitments Steering Group (SCSG) including monitoring of the country-specific Western Balkans Anti-Corruption Pledges, and support to civil society through the establishment of a Balkans Observatory (a platform that connects and empowers civil society actors across the Western Balkans).
- Delivered the SCSG Conference in Sofia, which focused on key HMG SOC priorities (illicit finance and corruption, irregular migration and illegal weapons trafficking), and secured consensus for the next phase of development of the Illicit Finance and Anti-Corruption Roadmap.
- Support to Phase 2 of the Global Initiative against Transnational Organised Crime (GI–TOC) Western Balkans Civil Society Observatory. In-depth research was conducted resulting in two major regional reports on SOC and corruption.
- Successful growth of the GI-TOC Regional Network to 32 civil society members and the successful launch of the Anti-Corruption Assessment in Vienna. The regional network is a source of knowledge on SOC and a platform for exchanging expertise to strengthen civil society through networking and knowledge-building activities.
- Successfully delivered the Wilton Park Conference on Tackling Organised Crime in the Western Balkans. This brought together Western Balkans governments, civil society, the media, academia, law enforcement and the European Commission, to apply pressure and make recommendations for further reforms.
- Law enforcement and prosecution capacities in the region saw improved institutional performance as a result of HMG engagement.
- Firearms Focal Points (FFPs) are now in place in WB countries (apart from BiH) as a direct result of National Ballistics Intelligence Service (NABIS)-funded mentoring and support, and will be key to supporting the WB6 with their international Ballistics Forensics accreditation aspirations.
- Commitment was secured at UK/Albanian senior and ministerial levels for a multi-year project, intended to strengthen, modernise, and reform the Albanian Justice System’s Forensics Science and Crime Scene Investigation capacity.

Key Lessons
- Further improvements to Monitoring & Evaluation (M&E) systems are necessary. These need to be fed into refreshed programme documentation, and more clearly linked to project activity to rationalise strategic programming ambition.
- The engagement of a Gender Advisor has led to a marked improvement in gender mainstreaming ambition across the programme. Further work is still required to systematise an approach and meet this ambition.
- Comparable work is required still around conflict sensitivity.
- Covid 19 – the programme and projects had to rapidly adapt their delivery to the developing global pandemic and restrictions on travel and delivery in Q4 19/20. The impact of Covid-19 affected the implementation of some projects, with key workshops and training sessions curtailed or postponed.
- Learning from Covid-19 has highlighted the need for SOC project teams to balance the resource required to deliver ongoing activities on a virtual basis, whilst planning for further activities to be as adaptive as possible within-year.
- It would be useful to explore whether adaptive programming and adaptive management can be incorporated into the SOC programme delivery model in FY 20/21.

Summary of Recommendations for FY 20/21 and FY 21/22
1. At the moment, the programme aspires to deliver broadscale system reform and upstream transformation mitigating SOC threats across the whole WB region. However, project-level activity is not set up to achieve this ambition, whether in its strategic focus or its geographic range. The programme needs to decide either to align programme ambition with current - predominantly operationally focused – project activity OR, to abandon some elements of the current programme in preference of project activity more likely to achieve the heightened strategic ambition.
2. Deciding on reducing programme ambition in preference of maintaining the current project level status quo would require an assessment of all project level activity in light of whether it can truly deliver against the minimum standards of programme management. Where those standards cannot be met, project-level activity should be discontinued.
3. Deciding on increasing programme ambition would require a careful analysis of where the programme can genuinely add value to a complex and often saturated international donor space. Emphasis should be placed on assessing what other pre-existing programming interventions (and whether HMG or other international actors) tackle SOC dynamics in region, with the programme then moving to fill gaps in the current donor response. In doing so, the programme should also avoid duplicating activity.
4. The programme needs to increase local – as opposed to remote and UK-based - ownership of activity, and ensure it is genuinely responsive to the needs of regional Embassies in tackling the SOC threat, and according to the particular context of each country in region. Thought should be given to expanding programme team capacity (a mix of locally engaged and UK-based staff) in the region to achieve this.
5. Increased Embassy oversight and ownership combined with a better alignment of project activity with overarching strategy, would assist in clarifying why and where activity is delivered most usefully. This would help the programme to achieve it’s regional ambition of encouraging the different countries in the region to collaborate more effectively in tackling SOC
6. The current governance structure risks confusing policy and programming imperatives, and should be reviewed to create two distinct and separate approval processes.
7. Subject to determining where the programme would like to focus future ambition, current M&E processes will need to be reworked to ensure the project-level activity being undertaken feeds a series of reduced, more realistic and coherent programming outcomes. Reasonable levels of access to programme activity must be permitted to the M&E specialist resources within the programme/portfolio to ensure this. Where it is not, the project level activity will be unable to be measured accurately and leading to a presumption it is not ultimately appropriate programme activity at all.
8. A gender and conflict-sensitivity analysis should be completed for the programme, and to underwrite all project consideration and approval. Recognizing this is a labour-intensive task, the programme team should focus initially on pulling out key principles of how SOC and gender/conflict interact in the WB, and use those principles to inform project design. Thereafter, the programme team can move to more sustained analysis and treatment of these cross-cutting themes.
9. Establish a programme-level asset register.