Annual Review - Summary Sheet

PROGRAMME TITLE: Westerns Balkans Stability CSSF Programme
Country and Region:	Western Balkans: Albania, Bosnia-Herzegovina (BiH), Kosovo, Montenegro, North Macedonia and Serbia.
IATI Unique ID:	CSSF-10-000002
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £18.4m			Non-ODA:
Budget this FY	ODA: £18.4m			Non-ODA:
Spend this FY	ODA: £15.8m			Non-ODA:
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
Capacity developed to support institutional reform and strengthen democracy;					A
Strengthened democratic governance supported;					A
Enhanced resilience to violent extremism supported;					A
Justice institutions and rule of law supported;					B
Community cohesion and enhanced positive peace supported					B
Knowledge and Learning					B
Overall output score					A
Outcome Assessment: Insufficient evidence to demonstrate likely contribution to outcome.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	B	A	A	B	A	B	A	B
Risk Rating - low/medium/high	Low/ / Medium	Medium/ / Low	Medium		Medium		Medium
*output/outcome scores
How has the programme changed during this period?			Following FY 18/19 AR, the programme has revised its Theory of Change (ToC) and adopted a more balanced approach on regional vs bilateral projects and on supply vs demand-side for governance.

What support did the UK provide in FY 19/20?

The Stability programme consists of a wide portfolio of projects seeking to deliver against a complex and ambitious set of objectives. The programme directly contributes to nine of the twenty-six National Security Council (NSC) strategy sub-objectives.

The programme aims to address the priority drivers of instability in the region and in specific country contexts. The drivers of instability across the region are persistent and complex, manifesting differently in each country, and have intensified during the COVID-19 (C19) crisis. This may accelerate negative trends. The Joint Analysis of Conflict and Stability acknowledges that “any concerted attempt to address one or two of the conflict drivers will not succeed in isolation; the entire system needs addressing if a lasting positive peace is to be established.” In order to address these issues effectively, the programme has adopted a multi-pronged approach.

To contribute to a more stable and resilient Western Balkans region, the programme sought to improve the capacity and response by the Government and relevant agencies in the region. To achieve this, the programme portfolio has sought to support: (i) Capacity of relevant government institutions to support institutional reform and strengthen democracy; (ii) System enhancements, policies and mechanisms to strengthen democratic governance; (iii) System enhancements, policies and mechanisms to enhance resilience to violent extremism; (iv) Systems enhancements, policies and mechanisms to strengthen justice institutions and rule of law; (v) Community cohesion and enhanced positive peace and (vi) Knowledge and decision-making.

In FY2019/20, the programme implemented £18.4m worth of projects, across all six countries, via a mix of 41 separate multi-country and bilateral projects on nine thematic areas: Democracy, Governance, Transitional Justice, Preventing Sexual Violence in Conflict Initiative (PSVI), Social inclusion, Rule of Law, Kosovo-Serbia relations, Preventing and Countering Violent Extremism (P/CVE) and Education.

Having a broad range of projects made it difficult to articulate what change the programme sought to deliver. The programme team acknowledged that “Stability” is at risk of being interpreted too broadly. This has also made it difficult to monitor results and measure progress against delivering NSC strategy objectives.

In order to address these issues, the programme undertook a transitional period which started in FY18/19 and continued throughout FY 19/20 and culminated with the reformulation in June 2020 of the theory of change.

Key results for FY 19/20:

- The decision to establish the Parliamentary Budget Office (PBO) as a Special Unit in the Assembly through an amendment to the Law on Assembly in North Macedonia is a major milestone towards sustaining improvements in financial scrutiny. This confirms the project assumption that political will to improve parliamentary performance in this area is present, and that capacity support is the right approach.
- In Serbia the Westminster Foundation for Democracy (WFD) supported the diaspora platform ‘Returning Point’ by funding research on the cost of youth emigration, which was then included in the proposal of the government’s Strategy on Economic Migration of the Republic of Serbia. In addition, WFD supported Popular Democracy workshops in more than 100 schools around the country, which raised the awareness of some 2,700 first-time voters on democracy and civic values.
- Enhanced resistance to violent extremism projects has reportedly increased inter and intra-community cohesion (North Macedonia), reduced vulnerability of youth to violent extremism (BiH), integrated returnees (Kosovo), and supported institutional responses in Kosovo – enabling the country to receive the most returnees of anywhere in the world. An internal review of all HMG Preventing/Countering Violent Extremism interventions from Oct 2019 has praised the community-level work of the International Organization for Migration (IOM) project, and has found “increasingly strong evidence that the work IOM and others do at the community level is effective at preventing (violent/not-yet-violent) extremism within communities”.
- Kosovo - The project “Strengthening the judicial system in Kosovo” implemented by Axiom monitored and analysed the forthcoming Court President’s selection process for vacancies within the Basic Courts of Gjakova & Peja. In addition, the Kosovo Prosecutorial Council (KPC) approved and adopted one of the most important Regulations on Appointment of Chief Prosecutors and Chief State Prosecutor with the project’s recommendations accepted.
- BiH - The project “Seeking Care, Support and Justice for Survivors of Conflict Related Sexual Violence (CRSV) in Bosnia and Herzegovina” implemented by United Nations Population Fund (UNFPA), institutionalised Standard Operating Procedures within 13 public health centres allowing information exchange and referral for Gender Based Violence and Conflict Related Sexual Violence survivors. It also trained professionals (social welfare centres, centres for mental health, survivors’ associations) on a sensitive approach to CRSV survivors in 10 cantons.
- “Strengthening good governance, transparency and accountability of Kosovo institutions” successfully oversaw the recruitment of 30 top civil servants in various state institutions. The project successfully managed to leverage role of civil society in monitoring public recruitment processes, and combined with diplomatic pressure from the embassy, yielded positive results. A review carried out by Stabilisation Unit found that the project increased citizens’ confidence in the transparency of recruitment processes in the civil service. There is also evidence that performance in some departments has improved following the competitive and meritocratic hiring of their directors.

Key Lessons

In FY 2019/20 the programme team recognised that, in order to meet the NSC strategy ambition, the Stability programme had to be reconceptualised to be more focused, targeted and specific about the interventions it makes and the systemic change it seeks to bring about. The team also acknowledged the need to include a further process of understanding, prioritising and adapting to the emergent risks and opportunities brought on by C19.

Key changes to the programme for 2020/21 include:

A new Conceptual Framework that situates the problem around two unvirtuous and interrelated circles: ‘Societal division’ and the discourse that surrounds it, and ‘State and society’ and the interactions between them.

The programme will now deliver through two strands: ‘Resilience’ that will address societal division and build resilience to the risks of violent conflict; and ‘Democracy and Justice’ that will improve the democratic system and increase citizen engagement.

A new Theory of Change that articulates “how” we expect to deliver the change necessary to meet NSC objectives.

The 19/20 Annual Review (AR) team recognise that significant work has been done in FYs 19/20 and 20/21 to refine and focus the programme. However, there is still much work to do. The new Theory of Change did not bring any significant improvements to the overall Results Framework (RF), which has remained unchanged since last revision in December 2018. The programme did develop a new monitoring framework with narrative reports for each project and room to insert project level indicators. The aim of this was to aggregate these reports and indicators to present an overall assessment against an output. However only the narrative element of the framework worked as planned. The 2019/20 AR report pointed out that the lack of data collection for the outcome indicators, as well as the vague formulation of output indicators and the absence of yearly milestones impeded an evidence-based monitoring of progress. Like the 2019/20 AR, the team for this AR scored progress on the outcome and outputs without being able to rely on measurable benchmarks. A Value for Money (VfM) methodology prepared by the programme team, while worthwhile for its capacity to provide rich information on a number of metrics, did not provide milestones and benchmarks for measuring progress.

Summary of Recommendations for FY 20/21

- Exit strategies and sustainability plans should be developed at the onset of each project;
- Projects should entail a co-funding from the host government;
- The programme should develop a menu of common indicators at outcome level for the overall portfolio;
- The programme should ensure regular data collection with baseline and endline surveys at country-level;
- The programme should ensure that reporting is streamlined and lessons learned are properly shared;
- Strategic communication has to be embedded in all initiatives in order to make the issues relevant to the public and to boost demand side for good governance;
- The programme should adopt a more proactive approach in providing human resources and for planned staff turnover;
- The programme should carry a comprehensive stakeholder mapping (both donors and main implementing partners) to get a more granular understanding of who is doing what in each sector where HMG is engaged;
- The programme should more clearly spell out the potential gains from projects that do not directly contribute to the overall theory of change, but that are still part of the programme portfolio (e.g. the 21st Century project implemented by the British Council) because they are deemed to bring political access and increase HMG influence;
- Programme at times need to challenge broad policies to understand where programme effort will help push forward a policy issue and which areas would require other levers besides programmes.