Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Iraq Programme
Country and Region:	Iraq, Middle East and North Africa
IATI Unique ID:	CSSF-06-000029
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Budget:	ODA: £58.34m			Non-ODA: £1.4m
Total Spend:	ODA: £54.94m			Non-ODA: £0.68m
Original Programme Start Date: April 2019		End Date: September 2020
Outputs
Damaged critical infrastructure rehabilitated and jobs created in areas liberated from Daesh					B
Security Sector Reform agenda in Kurdistan Regional Government and Government of Iraq supported through technical assistance and advice to Office of the National Security Advisor and Ministry of Peshmerga Affairs					B
Government institutions supported to better understand and respond to citizens needs on basic services, security and justice					A
Civil society and target communities empowered and enabled to advocate for their needs from government, and appraise government delivery					B
Produce evaluations and learning documents to inform policy and programmes					B
Overall output score					B
Outcome Assessment: The programme is assessed to have performed well given the challenging context and the breadth and ambition of the programme. Not all outcome indicators were met, partly due to a deterioration in the operating environment in the final quarter of the 2019-20 financial year, and overly ambitious outcome statements. The forthcoming multi-year programme will offer an opportunity to apply lessons from the past three years, including more realistic outcome measures.
Final Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Iraq Programme**	N/A	N/A	N/A	N/A	B	B	B	B
Risk Rating - low/medium/high	N/A	N/A	High		High		High
*output/outcome scores
**During FY18/19, a single programme was created through merging the previous two CSSF programmes.

What support did the UK provide?

In 2019-20, the UK provided:

- Funding to the UN’s Facility for Stabilisation, supporting returns and reintegration of those displaced by Daesh;
- An adviser to the Ministry of Peshmerga Affairs in Erbil and another to the Office of the National Security Adviser in Baghdad to facilitate a shared security sector reform agenda;
- National polling on public perceptions across Iraq;
- Financial support to the UN Investigative Team to promote accountability for crimes committed by Daesh;
- Support to community-level Local Peace Committees in Kirkuk;
- Funding to a UN-led regional gender programme.

What results did the programme deliver? Will they be sustained?:

- The UK’s funding to the UN Facility for Stabilisation has contributed to the significant reconstruction efforts in liberated areas, which has helped to facilitate the return of more than four million people internally displaced by Daesh.
- Local Peace Committees (LPCs) identified and responded to a range of local conflict drivers. One initiative worked to engage security actors and to improve coordination between LPCs and governorate-level authorities to streamline returns of internally displaced people (IDPs). As a result, a number of families who had been unable to return home due to perceived affiliation to Daesh, did return in this period.
- CSSF supported the development of Iraqi sub-national government institutions planning and strategy papers (including the Basra Five Year Strategy, and the Anbar Strategic Plan).
- CSSF projects helped to address a range of grievances in camps for IDPs ranging from successfully lobbying for increasing drinking water supplies, to helping IDPs register and receive humanitarian aid.

What lessons have been learned?

- Strategic impact can be greater if inter-project opportunities for coordination are regularly assessed and encouraged (where outcomes and outputs can be complementary).
- The third-party Monitoring, Evaluation and Learning budget was underutilised in the period in question, which the team can utilise to enable independent scrutiny in locations inaccessible to the CSSF team.
- Early exploration of longer-term funding sources would enable the CSSF to scale-up impactful projects.