Annual Review - Summary Sheet

PROGRAMME TITLE: Syria: Future Syria Programme
Country and Region:	Syria, Middle East and North Africa
IATI Unique ID:	CSSF-06-000030
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £2.5m			Non-ODA: £0
Budget this FY	ODA: £2.5m			Non-ODA: £0
Spend this FY	ODA: £3.49m			Non-ODA: £0
Original Programme Start Date: April 2019		Planned End Date: March 2022
Outputs					Score
CSSF supported mechanisms monitor and document Human Rights (HR)/International Humanitarian Law (IHL) crimes and abuses (including sexual and gender-based violence) and pass to higher authorities and other users					A
Civil Society Organisations (CSOs) operate and increase their capacity and institutional strength					A
Relationships built between Syrian/regional/ international CSOs, activists and women networks					A
Overall output score					A
Outcome Assessment: Evidence indicates the Future Syria programme has achieved, or is on course to achieve, the majority of its outcome level objectives in spite of significant challenges in the first year of a three-year programme.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	N/A	N/A	N/A	N/A	N/A	A	B
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	N/A	N/A	High
*output/outcome scores
How has the programme changed during this period?			The programme has largely delivered according to plan in this Financial Year, up to the last quarter where the emerging Covid-19 pandemic began to cause significant disruption. Although much of the Syria programme is already delivered remotely due to security constraints, planned face-to-face project activity had to be cancelled or moved online at short notice and implementing partners and HMG staff were unable to travel due to Covid-19 restrictions. Implementing partners were with time, largely able to adapt. HMG programme staff secured no cost extensions for three projects to ensure they were able to deliver planned activity despite Covid-19 disruption.

What support did the UK provide in FY 19/20?

Under the Future Syria Programme, the UK worked in four main areas:
- Improving the prospects for justice and accountability, including future transitional justice, for war crimes and human rights abuses committed in Syria by documenting violations and supporting victims of abuse, including sexual and gender based violence;
- Capacity building support to increase confidence and strength of moderate, non-sectarian, local level civil society organisations across Syria;
- Women’s empowerment in Syria, increasing women’s meaningful representation and participation in decision-making processes, including conflict prevention and peacebuilding at community and national levels.

Key results for FY 19/20:

- Expanded cooperation between CSSF implementing partner, Commission for International Justice and Accountability (CIJA), and UN investigative bodies (International Impartial and Independent Mechanism for Syria (IIIM) and UN Investigative Team to Promote Accountability for Crimes Committed by Da’esh/ISIL (UNITAD)) and domestic law enforcement agencies. This resulted in:
  - An extended MoU formalising the technical assistance CIJA provides to the IIIM and providing IIIM and UNITAD with full access to relevant CIJA evidence;
  - An expanded network of CIJA operational partners in Western jurisdictions (32 agencies in 13 countries) with CIJA providing assistance to 14 ongoing investigations concerning Syrian Regime and Da’esh suspects;
- Provision of evidentiary materials to Dutch prosecutors in the first war crimes conviction within a Western jurisdiction of a former Daesh member, and assistance to the trial of a former Syrian Regime official in a German court.
- Implementing partner Synergy for Justice provided strategic advice and mentoring to Syrian downstream partner Lawyers and Doctors for Human Rights (LDHR), resulting in significantly improved organisational and operational capability and, ultimately, sustainability.

Key Lessons

- HMG project managers invested a large proportion of resources in supporting implementing partners through a particularly difficult year. Partners valued this close engagement, demonstrating the importance of supplementing funding with programme expertise to achieve impact in such a complex and contested environment. However, providing this level of support is time consuming; without sufficient staff capacity, it impacted staff resilience.
- Heads of Programme should not be responsible for project-management of individual projects to ensure that there is sufficient management resource for complex and high-risk programming issues.

Summary of Recommendations for FY 20/21

1. Theories of Change and Results Frameworks are forward-looking tools that should support programme management and development, rather than focusing solely on what has happened in the past. They can only fulfil their potential if they are kept up to date and evolve to reflect reality. These tools should be owned and engaged with at a senior level and be embedded in how the programme team works with the Strategy Board, Implementing Partners (IPs) and across HMG.
2. In an environment as unpredictable as Syria, the Future Syria programme should consider using adaptive results frameworks that measure both if and how the programme adapts and assess the impact of that adaptation on programme outcomes and impacts.
3. Some projects have experienced compressed delivery times following programmatic delays or changes in context and all have had to adapt to Covid-19 restrictions. The programme team should consider planning a mid-programme evaluation, allowing time for adjustments to bed in and Monitoring and Evaluation (M&E) processes to be revised, to guide next stages of the interventions.