Annual Review - Summary Sheet

PROGRAMME TITLE: Egypt Programme
Country and Region:	Egypt, Middle East and North Africa
IATI Unique ID:	CSSF-06-000002
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £41.55m			Non-ODA: £0.75m
Budget this FY	ODA: £13.65m			Non-ODA: £0.35m
Spend this FY	ODA: £5.82m			Non-ODA: £0.18m
Original Programme Start Date: April 2016		Planned End Date: March 2021
Outputs					Score
Social Development: Improved Government capacity to target Takaful & Karama (Social Protection) services					A
Social Development: Improved Government capacity to apply International Humanitarian Law					A
Social Development: Direct service provision to vulnerable individuals (migrants and victims of Gender Based Violence)					A+
Social Development: A high quality Women Peace and Security National Action Plan is produced					B
Economic Development: Government of Egypt (GoE) reform of key sectors to increase competition, expand investment and remove supply bottlenecks					A
Economic Development: GoE bringing reforms to improve its fiscal position					A
Economic Development: GoE improved transparency					B
Economic Development: Government stakeholders are engaging with Egyptian Centre for Economic Studies (ECES) research and evidence					A
Economic Development: Accelerated businesses are attracting investment and creating jobs					A+
Education: Ministry of Education and Technical Education (MoETE) implements the modernisation of the school curriculum					B
Education: Educators & schools in North Sinai and surrounding governorates are prepared to implement the new curriculum					A
Education: Improved physical and mental health support within school settings					A
Overall output score					A
Outcome Assessment: The programme has performed well in what was both a transition year by design and a challenging Q4 due to Covid-19. The majority of Outputs were met and so scored As.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	B	A	A	B	B	A	A
Risk Rating - low/medium/high	Medium/ High	Medium/High	Medium/High		Medium/High		Medium
*output/outcome scores
How has the programme changed during this period?			2019-20 was designated a transition year to conduct a stability assessment and shape a narrower focus in 2020-21, which is in place. The new programme is due to focus on Economic justice, Sinai Development, and Human Rights.

What support did the UK provide in FY 19/20?

1. Inclusive Economic growth: aiding key policy reforms with technical assistance, and directly stimulating job growth.
2. Social protection and development: reinforcing the use of evidence in targeting welfare provision, supporting migrants and vulnerable populations and promoting the women, peace and security agenda.
3. Education reform: rewriting early years’ curriculum frameworks, supplying schools and training teachers to implement a modernised education system and providing integrated support services to children.

Key results for FY 19/20:

1. Amendments to the Public Procurement Law and Pension Law.
2. Modernisation of the Oil and Gas sector, helping to catalyse the £20bn Foreign Direct Investment that Egypt’s oil and gas industry has received over the past three years.
3. Direct creation of 443 full time jobs and indirect creation of 10,150, in start-ups which raised $9m financing and over $3.8m in revenue. 34 of these new businesses are female-led.
4. Improved accuracy of GDP growth estimates, through the Egyptian Centre for Economic Studies.
5. Supporting the Takaful & Karama social protection scheme, with a proxy means testing tool used to redirect funds towards £2,540,988 eligible beneficiaries, 2,236,069 of which are female-headed households.
6. Psychosocial, legal and medical services provided to 11,512 vulnerable migrants.
7. Modernisation of early years education through pre-primary and primary age curricula frameworks, life skills and citizenship education frameworks and teacher training guides.
8. President Sisi’s promotion of the Women, Peace and Security agenda at the UK-sponsored Women Peace and Security session of the African Union’s December 2019 Aswan Forum.
9. Provision of supplies and training to 550 schools and their teachers, in North and South Sinai and Ismailia, to deliver a modernised curriculum.
10. Health support through training of 617 members of school Health and Environment Committees and providing 192 children (56%F) with psychosocial, legal, financial and/or educational services.

Key Lessons

1. Programme coherence improved but further work is needed to join up the programme strands.
2. Sustaining strong context analysis is crucial to shape well-targeted programming and enable conflict sensitivity. Articulating standards for cross-cutting issues would support consistent application.
3. Flexibility and adaptability in programme design and the CSSF Results Framework enabled responsiveness to political and contextual shifts.
4. Implementing partner capacity to build good relationships with GoE has been critical to shape reforms and sustain access.
5. The Results Framework’s coherence improved but it requires further strengthening, especially impact indicators.
6. Building a budget for monitoring and evaluation into project design is crucial for ensuring projects are able to evidence that they are responding effectively to the objectives.

Summary of Recommendations for FY 20/21

1. Ensure that a holistic view of HMG’s development priorities and approach in Egypt is captured in HMG’s future country plan/strategy for Egypt.
2. Invest in sustaining strong context monitoring and analysis.
3. Develop standards for cross-cutting themes for British Embassy Cairo and implementing partners’ application and continue to promote partner conflict sensitivity capacity.
4. Plan how the programme can remain agile next year around any partnership shifts.
5. Consider how civil society support and engagement might be increased.
6. Further develop the Results Framework and Theory of Change to improve coherence and better reflect and track the contribution of Outcomes to Impact.
7. Identify learning priorities to help optimise the programme.
8. Develop a Safeguarding framework to apply across the CSSF.
9. Proactively engage partners on any implications of the creation of the FCDO.