Annual Review - Summary Sheet
PROGRAMME TITLE: Algeria Programme
Country and Region:	Algeria, Middle East and North Africa
IATI Unique ID:	CSSF-06-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £21.2m			Non-ODA: £0
Budget this FY	ODA: £8m			Non-ODA: £0
Spend this FY	ODA: £5.41m			Non-ODA: £0
Original Programme Start Date: April 2016		Planned End Date: March 2022
Outputs					Score
Increased opportunities generated by North Africa Good Governance Fund (NAGGF) to influence others.					A
Algerian institutions are supported to deliver macro-economic reforms.					C
Algerian institutions are supported to improve youth economic empowerment.					B
Algerian state institutions supported to become more inclusive in their work.					A
Increased capability of comms/media professionals in Algerian institutions to produce more inclusive media and communications products.					B
Overall output score					B
Outcome Assessment: Outcomes partially achieved in all areas.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	B	A	B	A	B	B	B
Risk Rating - low/medium/high	N/A	Medium	Medium		Medium		Medium
*output/outcome scores
How has the programme changed during this period?			Increased work on macro-economic change affecting marginalised groups and reducing government subsidies on key products. / Bolstering employment-focused programming through two new projects with wider geographical coverage to reduce marginalisation. / Focussing education programming to improve the quality of teaching in the classroom.

What support did the UK provide in FY 2019/20?
The UK support provided in FY 2019/20 aimed to enhance the drivers of Algeria’s stability and prosperity. It targeted three main areas:
1. Economic diversification, youth employment and education: the UK continued to provide support for strategic “top-down” economic reform in Algeria. In addition, it supported young people to access future economic opportunities through improvements to the quality of teaching in classrooms at secondary school level. Employability of graduates was also addressed via strengthened cooperation between universities and employment providers, along with improved support to young entrepreneurs and micro, small and medium enterprises (MSMEs).
2. Political inclusivity and media: the UK continued its work with Parliament to strengthen its citizen engagement and improve the administrative infrastructure which supports a successful parliament. It supported Algerian media to improve journalism standards and better respond to the needs of Algeria’s large youth population.
3. Governance: UK support focused on strengthening Algerian institutions’ ability to safeguard human rights. This is focussed on work with the office of the Child Protection Commissioner and prison reforms.
Key results for FY 2019/20:
- Commenced work with World Bank Group to diversify the economy, reduce subsidies on key products and ultimately aid reduced reliance on Foreign Exchange reserves.
- Provision of improved services to women and youth who come into contact with the law. Support to the office of the Child Protection Commissioner and the child protection helpline which has received more than 500,000 calls.
- Programme successfully supported economic diversification, focusing on youth and female entrepreneurship, through targeted training and new and innovative business plans being realised, of which 40% are female led.
- All Newly Qualified Teachers (NQTs) now receive training incorporating materials co-created through UK programming, so far totalling over 100,000 NQTs. Student performance baselined in FY 2019/20 to measure improvements in the year ahead with a more focussed programme.
Key Lessons
- Timeframes to commence projects should not be underestimated. Financial arrangements and the time taken to build teams, even for experienced implementers, has been more challenging than anticipated.
- All implementing partners showed an ability to adapt to challenging circumstances in year. However, some required more time than others to do so. Building in adaptability is important to flex up and flex down programming according to immediate or shorter term needs as well as contextual changes in country.
Summary of Recommendations for FY 2020/21
- Continue the integrated HMG approach to programming and provide opportunities to challenge assumptions.
- Ensure recommendations from reviews in 2020 are taken forward and consider a more regular mechanism for monitoring stability.
- Ensure that planned work on cross cutting themes such as gender, value for money and conflict sensitivity are taken forward.
- Focus on monitoring and evaluation of existing work, including projects which have closed, to check progress towards outcomes, sustainability and any lessons learned for future programming.