Annual Review - Summary Sheet

PROGRAMME TITLE: Libya Programme
Country and Region:	Libya, Middle East and North Africa
IATI Unique ID:	CSSF-06-000006
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget :	ODA: £38.3m			Non-ODA: £0.2m
Budget this FY	ODA: £16m			Non-ODA: £0
Spend this FY	ODA: £8.48m			Non-ODA: £0.07m
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
The threat of explosive remnants of war in municipalities is decreased through clearance and increased awareness.					A
Priority basic service and economic infrastructure in municipalities are restored and/or improved.					B
Communities have mechanisms for effective conflict management.					A
Target Libyan entrepreneurs, including women, are provided with microfinance, business support, and/or training.					A
The institutional and/or technical capabilities are improved of select civil society organisations, economic institutions, political parties, and alternative media platforms.					A+
Overall output score					A
Outcome Assessment: the programme has demonstrated a clear contribution towards the four stated outcomes of recovery, social cohesion, economic opportunity and supporting inclusive change which are all in line with the theory of change and UK’s political, security and economic objectives in Libya.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	A	A	B	A	A	A	A
Risk Rating - low/medium/high	High	High	Medium		Medium		Medium
*output/outcome scores
How has the programme changed during this period?			The programme has implemented recommendations from the previous annual review on strategic focus, risk, conflict sensitivity and monitoring, evaluation and learning. It has also adapted in response to conflict dynamics and COVID-19.

What support did the UK provide in FY 19/20?

The UK’s Conflict, Stability and Security Fund (CSSF) programme in Libya supported projects across the four programme outcomes of recovery, social cohesion, economic opportunity and supporting inclusive change. This included 15 different projects, managed by 13 different implementing partners, both multilateral and bilateral, including United Nations agencies, the World Bank, Civil Society Organisations (CSOs), and international government agencies such as USAID and Expertise France. The projects contributed to results in mine action, local stabilisation, community conflict resolution, public financial management reform, microfinance, opportunities for entrepreneurs, independent media, civil society capacity, and women’s empowerment and political participation.

Key results for FY 19/20:

- Mine Action activities in Sirte led to the first ever Land Release Certificate in Libya, a significant step for the Libyan Mine Action Centre (LibMac). Clearance work enabled other CSSF funded actors to carry out restoration of basic services encouraging the return of displaced people.
- Five peace-building and social cohesion initiatives launched in nine different municipalities through UK grants to local Social Peace Partnerships (SPPs).
- The creation of Libya’s first ever micro-finance facility, offering credit to micro-entrepreneurs. The programme also supported the entrepreneurship ecosystem in Tripoli establishing a training/co-working space with FabLab, and delivering training for 57 entrepreneurs, including 27 women.
- More than 850 women were trained by CSO partners, including workshops on citizenship, leadership, entrepreneurial skills building, legal rights, conflict mediation and peacebuilding. Eight CSO partners jointly developed a national advocacy campaign shifting the perception of women in Libya, and generating wide engagement from government, media, businesses and schools.
- Continued development of a social media platform which reached close to one million Libyans, approx. 40% women, with high quality, objective news content.

Key Lessons

1. Importance of realistic contingency planning based on scenarios, agreed across HMG and shared with implementers. This helps to draw out expertise and invites constructive challenge against plans and their underlying assumptions.
2. Results Framework milestones need to be regularly reviewed, with consistent disaggregation of data by gender and geography.
3. Gender specific analysis is an essential element of programme design for any Women, Peace and Security (WPS) initiative to ensure ambition is realistic and achievable.
4. Building local committees that are inclusive of women and represent the broad spectrum of local constituencies can be crucial for effective crisis response: SPPs utilised their skill and networks to lead early efforts to respond to COVID-19 in many municipalities. Where SPPs were not leaders, they have been used by local authorities as a platform for disseminating information, raising awareness, and mobilising communities and CSOs for community action.
5. The mine action project with Danish Demining Group in Benghazi faced many challenges and missed many of its targets. To learn from this, the programme commissioned a third-party monitoring review which recommended the importance of: building strong relationships with the key stakeholders; allocating the appropriate human resources to the project; adopting longer project timelines; and allocating more time to the inception phase.
6. Importance of flexible funding and partnerships, able to utilise expertise from other contexts during rapid crisis response: COVID-19 required El Kul to quickly adjust both its editorial strategy as well as business development activities to respond to changing realities. This succeeded both thanks to BBC Media Action’s expertise in dealing with health emergencies and quick absorption of rapid research conducted by other actors.

Summary of Recommendations for FY 20/21

- Conduct regular (minimum twice a year) updates of conflict analysis and scenario planning through the Joint Analysis of Conflict and Stability Working Group. Gender analysis and COVID-19 impact should be integrated throughout and linked to specific programme adaptation and COVID-19 response plans.
- Increase cross embassy and North Africa Joint Unit collaboration between political and programming teams to better leverage and communicate CSSF programme in line with UK objectives.
- Maintain flexible funding to support UN led political process but crucially retain focus on enabling environment for inclusive and sustainable political settlement. Continue to clearly articulate rationale for this approach, including centrality to UK objectives.
- Establish greater coherence and collaboration across projects to amplify programme level impact.
- Hold implementing partners’ day(s) and three targeted thematic or geographic sessions with selected partners allowing space for discussing strategic goals and networking, providing training on cross-cutting themes and reporting, gathering feedback and learnings and helping partners understand how their projects fit within the wider programme and UK objectives.
- Prioritise communicating project level results and wider programme impact to Libyan stakeholders, other donors and across Her Majesty’s Government.
- A dedicated Monitoring, Evaluation and Learning adviser should be provided by North Africa Joint Unit (NAJU) to improve Results Frameworks, Political Access and Influence measurement and Value For Money indicators.
- A senior gender adviser (or Deployable Civilian Expert) should be provided by NAJU to work with the gender lead and support dedicated gender analysis to update the cross-embassy gender strategy and shape programme design, indicators and audits.
- Closely monitor overall risk rating, including at Country Boards, and work with partners to implement conflict sensitivity risk assessments and gendered conflict sensitivity trackers, and adapt to the impact of COVID-19.