# Annual Review - Summary Sheet

PROGRAMME TITLE: Middle East Peace Process (MEPP)
Country and Region:	Occupied Palestinian Territories (OPTs), Middle East and North Africa
IATI Unique ID:	CSSF-06-000023
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Ministry of Defence (MOD), Department for International Development (DFID)
Total Budget :	ODA: £38.3m			Non-ODA: £2.5m
Budget this FY	ODA: £8.03m			Non-ODA: £0.5m
Spend this FY	ODA: £9.42m			Non-ODA: £0.37m
Original Programme Start Date: April 2019		Planned End Date: March 2022
Outputs					Score
Improved capability, accountability, sustainability and inclusivity of the Palestinian Authority Security Forces (PASF).					B
Effective legal assistance provided to Palestinians at risk of displacement in the West Bank and East Jerusalem.					B
Key infrastructure, particularly electricity provision, constructed in isolated parts of the West Bank’s ‘Area C’, to facilitate continued Palestinian presence on their land.					A
Positive perceptions of, and strengthened support for, the two-state solution (2SS) amongst key religious and other relevant constituencies.					B
Organisations that advocate for the 2SS able to continue their work.					B
Closer links between the West Bank and Gaza built at the societal level, to facilitate later successful political reconciliation.					C
Palestinian women’s ability to achieve leadership positions in Palestinian society enhanced.					A
Overall output score					B
Outcome Assessment: In FY 2019/20, the CSSF programme contributed to cross-HMG objectives on the MEPP. Tangible successes were achieved in challenging circumstances, particularly given the impact of COVID-19. The programme continues to provide demonstrable support for the UK’s position on achieving a 2SS and continues to make a difference to the lives of Palestinians. However, the prospects for a return to formal MEPP negotiations are limited and there are continued considerable challenges to the 2SS and therefore the fundamental basis of the programme. These external forces make success at the output level, where projects are well designed and well delivered, difficult to translate into success at the outcome level.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	A	A	B	A	B	B	B
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium		Medium
*output/outcome scores
How has the programme changed during this period? FY 2019/20 was the first year of a new three-year programme. Overall objectives were similar to the previous MEPP programme however, projects were streamlined and grouped more logically into the three outcome pillars. Pillar 1 had a project terminated due to supplier issues, Pillar 2 had a change in implementer for a key project and Pillar 3 had projects terminated due to lack of local expertise and underperformance of suppliers. This has all impacted delivery. Delivery under Pillar 1 has been strongest and the implementer has worked hard to action previous recommendations in a way which is sensitive to CSSF requirements. The results framework underpinning the programme has also changed over the period, following technical input from Monitoring and Evaluation (M&E) experts. Staffing changes were also introduced with a new Deputy Head of Programmes taking the lead on M&E, and sharing oversight with the Head of Programmes.

What support did the UK provide in FY 19/20?
- Support to the Palestinian Security Sector including: capacity building to improve accountable, joint decision-making in Palestinian Authority (PA) institutions; community policing events to engage with citizens on issues of concern; development and delivery of leadership courses and human resources management plans; and support to civil society to improve accountability and sustainability of the security sector.
- Mitigating the impact of the conflict on the most vulnerable, support to sustain Palestinian presence and identity in key areas of the West Bank and to uphold International Law.
- Pursuing the political conditions which support progress towards resolution of the Israeli-Palestinian conflict through engaging with key constituencies in Israel and the OPTs and enhancing Palestinian women’s ability to achieve leadership positions.

Key results for FY 2019/20:
- Capacity-building support delivered to 3,624 Palestinian Authority Security Forces (PASF) personnel, including 630 women (17%) and 1,592 people under 35 (44%).
- PA’s national Command & Control capability increased and a UK funded Communication & Information System was used to complete a training exercise across eight-governorates.
- The percentage of Palestinians able to remain on their land in the short-term remained high at around 99% (note that this falls to around 50% once cases are fully resolved).
- 125 communities continued to be provided with emergency assistance, such as cash transfers and rehabilitation of shelters, with an estimated 27,000 beneficiaries over the course of the year.
- 58 households in three vulnerable communities (about 350 individuals) West Bank’s ‘Area C’ had renewable energy systems (solar panels) installed.
- 90 community figures from diverse communities (49 women, 41 men) gained knowledge and understanding of conflict dynamics through educational seminars and dialogues.
- Advocacy around the exclusion of women from decision-making positions led to a change in practice, positively affecting policewomen and a research paper provided analysis on the military service law which will underpin year 2 activities.

Key Lessons

- The importance of our implementers having local presence, knowledge and relationships in the context of politically sensitive MEPP projects cannot be stressed enough, and more emphasis should have been placed on this from the beginning of procurement of new projects, particularly given the presence of strong local Non-Governmental Organisations (NGOs).
- The results framework must be seen as a living document that must constantly adapt and evolve as projects progress and lessons are learnt, rather than something static that is only revisited during the annual review process.
- Fostering an environment where the programme team and implementing partners can share knowledge and learning in an open and inclusive way is crucial to a successful programme.

Summary of Recommendations for FY 20/21

- The results framework requires further strengthening, in particular at outcome level. A Monitoring, Learning and Evaluation plan should be developed.
- There should be continued strengthening of gender and value for money across the programme.