Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria: Early Recovery and Civil Protection Programme (ERCP)
Country and Region:	Syria, Middle East and North Africa
IATI Unique ID:	CSSF-06-000031
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £6.94m			Non-ODA: £0
Total Spend:	ODA: £2.82m			Non-ODA: £0
Original Programme Start Date: April 2019		End Date: March 2020
Outputs					Score
Syria Civil Defence (SCD) maintains current operating capability in areas of operation and improves technical operational capacity					C
SCD as an organisation increases its sustainability and accountability					C
Sentry Early Warning is maintained and expanded					A
Enhanced HMG understanding of the drivers of instability and extremism in NE Syria, and challenges to reintegration					B
Overall output score					C
Outcome Assessment: The programme has achieved notable successes in a difficult and dynamic environment. However, the mid-year termination of funding to SCD via Mayday Rescue severely limited outcomes of the ERCP programme’s primary activity. As is recognised as part of the programme lessons learning, the results framework as a whole did not keep pace with changes in the programme’s design and implementation; this restricted the evidence base against which other activities could be scored.
Final Outcome Score: C			Risk: High

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*	2018/19*	2019/20*
Programme Score	N/A				C	C
Risk Rating - low/medium/high	N/A				High
*output/outcome scores

The FY 2019/20 CSSF Syria portfolio was designed through a comprehensive Zero-Based Review process. Given the uncertainty of the conflict trajectory, the FY 2019/20 ERCP Programme was designed as a flexible, one year programme to deliver immediate HMG priorities: contributing to early recovery and service delivery activities in areas liberated from Daesh and filling crucial gaps in the humanitarian response by providing emergency civil protection, first response and service delivery activity.

What support did the UK provide?

Following significant flex during the programme year, the UK provided:
- Support to civilian protection via the SCD and Sentry Early Warning System;
- A better understanding of the drivers of instability and extremism in North East Syria, and challenges to reintegration

What results did the programme deliver? Will they be sustained?

The ERCP programme has faced challenges on multiple fronts: a change in the operating environment following the territorial defeat of Daesh in Spring 2019 generating a much higher number of displaced people than expected; the changing conflict dynamics in NE Syria in October 2019; the collapse of the implementing partner through which support to the SCD was provided; operational challenges and uncertainty as a result of changing conflict dynamics in NE Syria; commercial restrictions precluding backdated UK support to US-led early recovery work in NE Syria, once the political situation allowed UK support to resume; and difficulties in procuring and conducting third party monitoring. In this context it is of note that most of the activities of the ERCP programme have continued to be delivered, albeit without UK support in the latter half of the year in the case of SCD.

The programme's low scores at output and outcome level reflect both termination of support to SCD via Mayday Rescue, and weaknesses in the results framework which have not been adapted to monitor the relevant indicators for other implementing partners. SCD itself has proved remarkably resilient, in part thanks to the support of other members of its International Donor Group, but its work in the second half of the year cannot be attributed to the UK’s support. The Sentry Early Warning System provided alerts for 77% of airstrikes and expanded its operating capability. Research into the drivers of instability and extremism in NE Syria produced a firm evidence base and recommendations to inform future programming.

It is difficult to assess sustainability of programming in the Syrian context given continued uncertainty about conflict dynamics and the likely demand for services and ability to operate. Future programming should acknowledge this, and HMG’s responsibility to its partners to put plans for exit or sustainability in place and communicate these clearly.

What lessons have been learned?

The Programme Completion Review has identified lessons relevant to programming in a conflict environment.

- Be prepared for unpredictability and shock in conflict environments. Programme staff levels had been reduced in line with outcomes of the Zero-Based Review process, leaving very little resilience in the team to manage projects’ adaptations to changes in the conflict.
- Protracted conflict presents challenges for defining end states, sustainability, and how CSSF can responsibly close out support in response to policy shifts and contextual changes. CSSF should consider ways of supporting implementing partners in situations where no other channels of support are available.
- Notwithstanding the 5% cap on staffing costs, complex, high risk programmes should be provided with sufficient management resource. In particular, Heads of Programme should not be responsible for managing individual projects.
- Some of the programme activity, such as the research activity, demonstrated the benefit of CSSF programmes being able to respond quickly and appropriately to opportunities and needs. This approach should continue.
- When planning future scoping studies in conflict environments, weigh up the benefits of regular, smaller, more tactical studies versus larger, longer projects that may lose relevance. Ensuring appropriate scope and timescales of research in a fast-moving context like Syria may result in more timely, actionable conflict analysis and better support programme design and implementation.