Annual Review - Summary Sheet

PROGRAMME TITLE: Lebanon: Community Stability Programme (CSP)
Country and Region:	Lebanon, Middle East and North Africa
IATI Unique ID:	CSSF-06-000020
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget:	ODA: £9.32m			Non-ODA: £0
Budget this FY	ODA: £9.32m			Non-ODA: £0
Spend this FY	ODA: £9.29m			Non-ODA: £0
Original Programme Start Date: April 2019		Planned End Date: March 2022
Outputs					Score
Strengthened institutional capacity to identify, plan and deliver inclusive livelihoods					A
Increased community (including women) and local/sub-national government inclusive coordination on livelihoods					C
Strengthened institutional capacity to design, plan and deliver inclusive priority resource services					A
Increased community (including women) and local/sub-national government inclusive coordination on services					B
Strengthened institutional and community capacity (including women) to foster dialogue and address sources of tension/conflict					A
National, local, and social media engaged in defusing tensions in conflict-affected communities					A+
Overall output score					A
Outcome Assessment: The Community Stability Programme (CSP) is a logical evolution of previous Conflict, Stability and Security Fund (CSSF) stabilisation work in Lebanon. In this first year of a three-year programme, the UK’s implementing partners proved adaptable throughout multiple political, economic and, latterly, Covid-19 crises. Although sometimes delayed due to the pandemic, there is clear evidence that output and outcome targets are on track to be met. The UK now needs to be clear on the level of ambition of its stability work in Lebanon, recognising a rapidly deteriorating social stability context, and respond accordingly.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*	2019/20*
Programme Score	N/A	N/A	N/A	N/A	A	B
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	Medium
*output/outcome scores

What support did the UK provide in FY 19/20?
The Community Stability Programme (CSP) aims to foster stability in the most conflict-vulnerable communities in Lebanon by addressing causes of tension and promoting peacebuilding amongst and between Lebanese, refugees, and local / sub-national and national authorities. It supports five complementary projects: the Lebanese Host Community Support Project (LHSP), an innovative blend of CSSF and DFID support to community-led stability projects via Mechanisms for Stability and Resilience (MSR); and IJMAA, a local governance project addressing conflict around services as an entry point for wider community peacebuilding; a peacebuilding communications project promoting local champions and emphasising pro-peace narratives; support to the Tensions Monitoring System (TMS) (which offers an understanding of tensions from the perspective of local government); and a rapid response World Health Organisation (WHO) COVID-19 project.

Key results for FY 19/20
This review year was one of extreme flux in Lebanon. Despite some delays in procurement and project initiation, outputs directly attributable to the CSP include the production of regular independent research-based reports on community tensions; initiating the MSR in 30 new locations; training 24 community champions and 41 local mediators; equipping ten municipal police units to conduct capacity assessments; initiating dialogue platforms in nine communities; building the capacity of 19 community-based organisations to engage with municipal government; and increasing the COVID-19 readiness of public hospitals.

Key Lessons
- All LHSP projects have shown a willingness to adapt to the multiple crises facing Lebanon, and in response to changing drivers of instability. Such changes should be (and have been) actively tested against the programme Theory of Change (ToC), recognising that the alignment of individual projects and activities can change over the course of a multi-year programme.
- One of the CSSF’s strengths is its willingness to provide technical as well as financial support to its implementing partners, for example engaging with TMS on research tools and with the LHSP on its mechanisms to build stability resilience. Implementers contrast this with the funds only approach of other donors, and it should continue.
- CSSF programme teams cannot, by their nature, hold expertise in every thematic area. Easy and regular access to subject matter experts beyond regular advisory roles, such as communications practices or survey design, will increase the effectiveness and impact of projects and programmes.

Summary of Recommendations for FY 20/21
- Consider a formal refresh of the analysis of Lebanon’s stability landscape, perhaps as part of an updated Joint Analysis of Conflict and Stability review and revise the ToC assumptions for FY 20/21 to reflect the changing stability context.
- Evaluate whether to introduce an Embassy-wide stability tracker to inform programme development and support assessments.
- In the absence of in-country gender advisory support during the review period, commission a gender audit to assess project performance to date and inform future programming.
- Review the Results Framework (RF) indicators and targets to ensure they are sufficiently stretching, timely, context-appropriate and aligned with adaptations in programme design and delivery. Consider including an indicator of programme adaptation and flexibility. Record changes to the RF within the same document.
- Formally move the TMS from the CSSF M&E budget into the CSSF programme budget, and formally integrate it into CSP management structures too (e.g. incorporate an indicator of TMS performance into the CSP programme results framework and require quarterly reporting).
- Given the pace of change in the context within which the CSP is operating, ensure changes in the risk register are tracked within the document.
- Continue to actively consider what is the end state for CSSF support to the LHSP, how this is changing in the context of Lebanon’s worsening crises, and what can be done to maximise the potential sustainability of the LHSP’s work at community level. Also assess where CSSF has comparative advantage and adds value on community stability, in conjunction with Humanitarian and Development Team programmes. This should be informed by research to produce a counterfactual for the LHSP’s interventions, and a formative evaluation during implementation.
- Facilitate learning between LHSP and IJMAA and evaluate the degree of complementarity or duplication of their work as an input to future programme design.