Annual Review - Summary Sheet

PROGRAMME TITLE: Morocco CSSF Programme
Country and Region:	Morocco, Middle East and North Africa
IATI Unique ID:	CSSF-06-000007
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £13.8m			Non-ODA: £0
Budget this FY	ODA: £7.m			Non-ODA: £0
Spend this FY	ODA: £5.98m			Non-ODA: £0
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs:					Score
Young women, men and Micro, Small and Medium Enterprises (MSMEs) are supported with education and/or economic opportunities.					A+
Citizens, through their organisations, supported to increase capability and motivation to hold public officials and service providers to account with non-violent, evidence-based strategies.					A+
Selected national and regional institutions (government and parliament) supported to increase service delivery capacity and responsiveness to citizens.					B
Overall output score					A
Outcome Assessment:
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score		B	A	B	B	A	A	A
Risk Rating - low/medium/high	N/A	Medium	High		High		Medium
*output/outcome scores
How has the programme changed during this period?			Over the past few years, the programme substantially reduced the number of projects, focusing on fewer, more flexible projects with larger multilaterals and implementing partners to promote sustainability and catalytic change. This year, the programme’s investment in monitoring and learning has resulted in increased capacity within the team to monitor performance and support partners to deliver to high standards. A new civil society project was designed and contracted that is strategic and focussed on advocacy and action.

What support did the UK provide in FY 19/20?

The UK provided support to strengthen relationships and trust between citizens and the state in Morocco through funding projects in the fields of inclusive governance, education and economic development. Governance work focused on participatory democracy, accountable and responsive institutions, predominantly working with the Regional Council of Tangier Tetouan Al-Hoceima (TTAH) and Parliament. Education and economic development focused on improving access to, and quality of, secondary education for marginalised young people and financial inclusion for Small and Medium-Scale Enterprise (MSME).

Key results for FY 19/20:

The programme continued to show good progress in promoting participatory democracy and open governance in the Tangier-Tetouan-Al Hoceima region, for example supporting the Regional Council to apply to the Open Government Partnership and inclusive development of a regional Gender and Social Inclusion Strategy. Westminster Foundation for Democracy (WFD) supported Parliament to strengthen citizen engagement around petitions and communications, and to restructure oral question processes.

Through the secondary education project, the Life Skills and Citizenship Education framework was approved by the Ministry of Education, and 11 second chance schools (designed to combat the inability of traditional education to meet the needs of certain disadvantaged groups in society) started utilising the framework.

The programme continued to strengthen links between civil society and the state, including through the development of systems for citizen engagement in regional policy making in TTAH region and joint events involving civil society organisations, public officials and MPs.

Key Lessons:

Choosing the right partner and design/delivery model is crucial to success.

The Thinking and Working Politically approach taken within the programme was shown to be important and successful.

Both WFD and DAI Europe’s projects emphasised the importance of ensuring that relationships were institutional rather than being mainly reliant on individual’s networks, so that sustainable systems are put in place which overcome changes amongst individual officials or politicians.

The UK Embassy can and should play an effective convening and information sharing role with key stakeholders.

The right technical expertise is crucial to be effective in influencing multilateral partners.

Strong interaction and relationships with implementing partners helps ensure programme quality and accurate reporting to support CSSF requirements.

Summary of Recommendations for FY 20/21:

Ensure that the programme is better aligned to the UK’s objectives and country strategy.

The programme team should focus on making the most of the convening role the CSSF can play, bringing together partners and promoting coordination and collaboration.

The programme team should consider conducting a gender review of the programme and identify gaps for UK contribution to transformational change.

The programme team should provide further conflict sensitivity training and support for implementing partners.

The programme team should consider asking for more specific context reporting from partners.

Ensure improved linkages and co-ordination between the programme and the Technical Assistance Facility (a CSSF programme working across North Africa).

The programme team should provide training for all team members on managing risk and involve policy colleagues in reviewing Risk Registers, at both programme and project level.

The programme team should Increase beneficiary consultations as part of monitoring visits and keep records of all consultations with beneficiaries and stakeholders.

The programme team should Review asset management and explore whether further monitoring is required.