Annual Review - Summary Sheet

PROGRAMME TITLE: Tunisia Programme
Country and Region:	Tunisia, Middle East and North Africa
IATI Unique ID:	CSSF-06-000028
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £37.7m			Non-ODA: £0.3m
Budget this FY	ODA: £14m			Non-ODA: £0
Spend this FY	ODA: £12.76m			Non-ODA: £0
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
1.Training and technical assistance are provided to private and public actors to better implement economic reforms and to modernise the financial sector.					B
2. Support provided to education system to increase employability of young Tunisians					A
3.Support provided to strengthen state-citizen engagement, transparency and participation					A
4. Political access and influence (PAI) undertaken through Her Majesty’s Government (HMG) (including with and through implementing partners) delivering political engagement and lesson learning to evolve future programme adaptations.					A

Overall output score A
Outcome Assessment: On balance, the programme continues to deliver results against the outcome. The Annual Review found that across the board, our support to the Government of Tunisia and non-state actors is on course to meet its medium to long term objectives.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16**		2016/17**		2017/18* & **				2018/19*		2019/20*
Programme Score	A	A	A	A	B	B	B	A	A	A	A	A
Risk Rating - low/medium/high	Medium for both**		Medium for both**		Medium / (Security)		Medium (Economic & Governance)		Medium		Medium
*output/outcome scores ** Two programmes merged to one FY18-19
How has the programme changed during this period?					The programme for 19/20 was an evolution from the previous year, and also marked somewhat of a transition as preparations continued for a new multi-year approach. There was an increased focus on promoting equitable economic growth and a deeper focus on addressing economic and political exclusion and inequalities, particularly within marginalised regions.

What support did the UK provide in FY 19/20?

The UK provided funding and technical assistance in three areas: economic reform; education and employability; and strengthening relationships and trust between citizens and the state. Our projects included (but not limited to) support to the World Bank on several economic reform initiatives; British Council’s Teaching for Success programme; support to Non-Governmental Organisations (NGOs) on citizen - State engagement and Government Communication Services International (GCSI) Strategic Communications project. All projects directly contributed to the political and economic/prosperity objectives within the HMG Strategy for North Africa as well as indirectly contributing to security and irregular migration objectives.

Key results for FY 19/20:

Outcome One – Economic Opportunity:

In support of economic reforms and modernisation of the Tunisian financial sector, an agreement on reform objectives and priority actions (administration modernisation and civil service reform) has been reached and presented at the National Conference on Major Reforms.

For promoting digital finance, two fintech companies received a license to operate as Payment Institutions. The methodological guide for Payment Institutions licensing has been adopted by the Licensing Committee.

On Small and Medium-sized enterprises (SMEs’) access to non-banking finance, about 1000 SMEs have been reached through the national communication campaign and 232 SMEs registered online through the new IT platform. On access to markets, six month programmes were conducted for 20 companies in the agri-food, textiles and ICT sectors with over 50 sales meetings set up with UK buyers.

Polling issued by post following the COVID-19 outbreak, undertaken as part of a GCSI project to inform government campaigning on confinement measures, showed 82% of respondents thought that the government had implemented the right measures to fight COVID-19.

Outcome Two – Economic Participation:

British Council provided training on English language and soft skills and continuing professional development to +5,000 teachers, with around 96% of these reporting that a) they acquired new skills and b) they now feel more confident in teaching English to primary students. This training has contributed to the strategy of CENAFOP (the Ministry of Education body responsible for teacher training) and the Ministry’s emerging National Strategy for Distance Learning.

Introduction of English as a classroom subject was brought forward from year six to year four across the whole country.

The UNICEF Second Chance Education project tackling school drop-out and equipping young Tunisians with the required skills and training to access the job market, with key secondary benefits to lower irregular migration and radicalisation in Tunisia. A Decree-law was approved by the Parliamentary Steering Committee.

Outcome Three – Citizen-State Engagement:

Following the regional inequalities analysis, three local governance pilot projects were launched to strengthen participatory governance and the social contract across three governorates (Sousse, Tataouine and Sidi Bouzid).

Three Civil Society Organisations were involved in monitoring the implementation of the citizen charters in the three original pilot services (Béja, Sousse and Tozeur) to ensure the accountability of service providers.

Four media campaigns were delivered at a national and governorate level which encourage state-citizen engagement, transparency and participation.

A total of 16 police stations and local security committees in 10 Tunisian governorates have been set up and are working side by side with the internal security forces to curb crime and prevent violence particularly against women and children.

Improved political access to Tunisian senior security officials in the Ministry of Interior and Ministry of Defence and via the Prime Minister’s Office was facilitated, leading to UK prominence on key security issues, especially interoperability.

Key Lessons

Notable progress has been made against the last review’s recommendations. FY19-20 saw a more joined up and integrated approach across the Embassy with newly established cross-team ‘pillars’, and the establishment of a Programme Hub that supports programme delivery across the Embassy pillars of Security, Political/Governance and Prosperity. Significant progress has been made on the Monitoring & Evaluation (M&E) tools which have underpinned programme progress.

COVID-19 impacted on all project activities resulting in a redesign of the programme to help Tunisia cope with the impacts of the pandemic. One big success was the Government Communications Service International’s pivot to deliver strategic communications support to the Tunisian government’s public messaging on COVID-19. A series of public information campaigns were launched, detailing the Government of Tunisia’s measures to protect citizens during the pandemic. This was an effective initiative in reassuring the public that plans were in place to respond to the needs of citizens during the crisis.

Summary of recommendations for the next year

Build a new multi-year strategy taking into consideration changes in context, organisational structure at the Embassy and emerging HMG priorities on climate, open societies, resilience, and girls’ education.

Consider adapting the approach to state-citizen engagement, focussing more on the open societies agenda.

Consider a separate Policy Strategy Board and Programme Board to allow space for higher level strategic thinking. Embed Programme Hub within this governance structure.

Develop a Tunisia level stability tracker to track real time data and evidence.

Efforts should be made to diversify our partnership on the Integrated Strategic Planning project beyond the Prime Minister’s Office to the Ministry of Interior or Ministry of Defence.