Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Jordan CSSF: Defence and Borders
Country and Region:	Jordan, Middle East and North Africa
IATI Unique ID:	CSSF-06-000019
HMG Partners / (LEAD in bold)	Ministry of Defence (MOD) (initially Foreign and Commonwealth Office (FCO) was also an HMG Partner, but MOD became sole partner during Financial Year (FY) 19/20)
Total Budget:	ODA: £0			Non-ODA: £17.23m
Total Spend:	ODA: £0			Non-ODA: £24.87m
Original Programme Start Date: April 2016		End Date: March 2020
Outputs					Score
The Quick Reaction Force (QRF) training and operations facilities enable High Readiness activity.					C
Jordanian Armed Forces (JAF) integrate the FY18-19 gifted Border Force assets into their intelligence, surveillance, target acquisition, and reconnaissance capability to strengthen their border security from within Jordan (assets were gifted from Syria CSSF).					A
JAF capability directorate officers are able to develop military strategy and plans against a proven planning and development model.					C*
Overall output score:					B
Outcome Assessment: In FY 2019/20, the programme has recovered some momentum after slow progress in FY18/19. Permission to oversee smaller projects locally allowed several smaller infrastructure elements to be completed. The MOD/Defence Infrastructure Organisation (DIO) have now initiated a bespoke infrastructure delivery process to deliver the larger outstanding infrastructure works. Equipment delivery has also commenced albeit using an interim solution rather than the expected MOD/Defence Equipment & Support (DE&S) route.
Final Outcome Score: B			Risk: Medium

* Limited progress made against this objective before it was cut from the programme as JAF abandoned the reform plan it was linked to.

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A/B	A	A	B	C	C	B	B
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium		Medium	Medium
*output/outcome scores

What support did the UK provide?

The Jordan Defence and Borders Programme (D&BP) provides support aimed at increasing the Jordian Armed Forces effectiveness in protecting Jordan from internal and external threats. Support included equipment and infrastructure, in tandem with the provision of training and/or mentoring by embedded UK personnel or Short Term Training Teams funded by MOD. The programme has been merged with the Security and Stability programme from 31 March 2020 and there remain some outstanding infrastructure and equipment commitments.

What results did the programme deliver? Will they be sustained?

This programme demonstrates UK commitment to a secure Jordan. It has enabled the formation of new rapid reaction units, increased the capabilities of these units; facilitated improved interoperability and improved command and control mechanisms. The infrastructure and equipment provided through this programme reinforces continuing UK defence and security activity.

What lessons have been learned?
- The Jordan D&BP has become a pilot programme for MOD acting as an Infrastructure and Equipment implementing partner. MOD’s Defence Infrastructure Organisation (DIO) delivery of infrastructure is viable, but it is not fast and vulnerable to reprioritisation in response to external pressures on the UK MOD. CSSF tasks must be communicated early to DIO and championed at an appropriate level to reduce the risk of reprioritisation.
- Future infrastructure and equipment projects, depending on the scope and scale, must factor in that circa two years is the minimum timeline from proposal to completion. This is dependent upon the prioritisation given to the task.
- Local expectations must be managed accordingly. To mitigate JAF disappointment at the pace of delivery the Defence Section prudently increased UK military training and exercise commitments.
- Complex MOD and CSSF project management and reporting processes need to be better aligned, understood and communicated early by all concerned.
- The need for a properly constituted MOD Portfolio Management Office (PMO), staffed with experienced infrastructure and equipment procurement specialists, remains necessary. In limited circumstances the delegation of financial and commercial authority, to specific nominated individuals at Post, is an effective tool to ensure timely procurement of appropriate equipment and services.