Annual Review - Summary Sheet

PROGRAMME TITLE: North Africa Technical Assistance Facility (TAF) Programme
Country and Region:	Morocco, Egypt, Tunisia, Algeria and Libya, Middle East and North Africa
IATI Unique ID:	CSSF-06-000022
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £11m			Non-ODA: £0
Budget this FY	ODA: £4.6m			Non-ODA: £0
Spend this FY	ODA: £5.87m			Non-ODA: £0
Original Programme Start Date: June 2017		Planned End Date: March 2021
Outputs					Score
High quality, relevant, demand-led, conflict and gender sensitive technical assistance (TA) is delivered through the NATAF					A
The NATAF generates learning on how technical assistance can bring about change and shares this across North Africa Good Governance Fund (NAGGF) programmes					B
Overall output score					A
Outcome Assessment: NATAF holds sufficient and reliable evidence to demonstrate milestone targets were met or exceeded against the Outcome Statement, “Institutions in partner countries commit to, invest in, and start to implement reform, and HMG scales up programmes and increases its political access and influence”.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*			2018/19*		2019/20*
Programme Score	N/A	C	A		A/B	A	B	A	A
Risk Rating - low/medium/high	N/A	Medium -High	Medium - Low			Moderate		Medium
*output/outcome scores
How has the programme changed during this period?				NATAF has seen an uptick in Technical Assistance focused on Climate Change, as an emerging priority for both CSSF and HMG approaching COP26.

What support did the UK provide in FY 19/20?

- NATAF is one of two regional programmes under the North Africa Good Governance Fund (NAGGF), managed by the North Africa Joint Unit in London, and financed by the Conflict, Security and Stability Fund (CSSF). It provides short and medium-term technical assistance in line with NAGGF and CSSF strategic priorities, and regional National Security Council (NSC) objectives.
- In FY19/20 the North Africa Technical Assistance Facility continued to play a central role in the delivery of UK objectives across North Africa through the provision of specialised, timely, demand- driven technical assistance designed to focus on the long-term drivers of instability. Technical assistance was provided to HMG internally across North Africa, and the Governments of, and selected partners within, Egypt, Libya, Tunisia, Morocco, Algeria, and at the regional level.
- The NATAF supported more accountable, responsive and inclusive governance; growing inclusive economies, increasing jobs and investments; and improving security and access to justice. NATAF harnessed expertise to support reform and unlock private sector growth; supported the needs of marginalised groups and regions; created opportunities for greater cross-border dialogue on shared challenges; supported technical expertise in the disbursement of international financing and enhanced UK influence with stakeholders able to address the long-term barriers to development and stability.
- The NATAF has continued to prove a flexible mechanism to scale programming up or down, to evolve operational approach within a shifting context, and to react to emerging policy needs at short notice.
- Tetra Tech International Development (formally Coffey International Development) is the lead supplier on the NATAF, providing technical assistance either using its own personnel or through sub-contracts, including consultants embedded in partner institutions.

Key results for FY 19/20
- Results from the NATAF are tracked through Quarterly reporting and Bi-Annual Reviews provided to the North Africa Joint Unit, which are then tested and interrogated for accuracy. Within this reporting period the NATAF has contributed to 29 significant changes in policy or practice within North African country institutions in line with HMG strategy for North Africa and contributed the development of 35 new relationships with North African partner ministries and institutions. There have now been 9 identifiable instances of partner governments or other donors committing to - or investing in - wider reform that builds on NATAF Technical Assistance. Some examples of technical assistance include:
- In Libya, key results include i) economic advisory expertise to Deputy-Special Representative of the Secretary General (D-SRSG) and United Nations Support Mission in Libya (UNSMIL) Economic Policy Unit leading to the establishment of the Libya Expert Economic Commission Secretariat, a key element of the UN- led Berlin Peace Process; ii) technical assistance provision to the Libya Investment Authority (LIA) has contributed to improving the LIA’s compliance with the Santiago Principles.
- In Morocco, key results include i) expertise provided to the Moroccan government’s Anti-Corruption Unit, including through benchmarking against the UK government’s equivalent institution, the Joint Anti-Corruption Unit in the Home Office; ii) technical assistance to improve the educational outcomes, governance and wellbeing of remote boarding schools for girls.
- In Tunisia key results include i) the establishment of a Private Sector Crisis Support Unit within the Government of Tunisia to respond to the economic fallout of C-19, ensuring the Government of Tunisia retain foreign direct investment during the crisis; ii) Strengthening Tunisian trade through support to SMEs in some of Tunisia’s most economically marginalised regions to take part in Market Acceleration Programmes (MAPs), including targeted assistance to women-led SMEs.
- In Egypt key results include technical assistance to: i) the Ministry of Social Solidarity on Violence Against Women and Girls (VAWG) to establish an effective Monitoring, Evaluation and Learning System to strengthen the provision of women’s shelters in light of increased rates of Gender Based Violence (GBV); ii) reform Public-Private Partnerships (PPP) in Egypt, to strengthen international finance revenues and better utilise domestic PPP expertise.

Key Lessons

The end of FY19/20 highlighted acutely the flexibility and adaptability of the NATAF as the programme adapted at pace to respond to the impact of the C-19 pandemic, both in terms of delivery model and the technical content of requirements from partner ministries. Two key early lessons emerged over the course of the immediate period of the pandemic on continuing to deliver projects through severe disruption:
1. Investing in local delivery partners/consultants maintains momentum on the ground when international consultants cannot travel;
2. Investing in additional resources and techniques can help ensure counterparts are engaged and benefit from online sessions. For example, as part of Public Banks Monitoring Unit delivery (PBMU) in Tunisia, 89% of participants who attended online training had done the pre-reading and pre-viewing to prepare for the session in light of ongoing travel disruption, implemented by LIBF, which strengthened overall engagement and learning. This learning could be applied to wider CSSF or HMG programming in the context of C-19 as travel restrictions continue.

An internal effectiveness review of the NATAF was completed in September 2019, with the purpose of informing the design of the next phase and learning key lessons from the NATAF’s experience to date.

A sustainability review and bi-annual review were also completed this FY. Lessons from both reviews are listed below, and the recommendations that are possible to implement within the remaining timeframe of the contract have been introduced.

The importance of engaging with multiple actors to drive real change is crucial to ensure policy reform is taking the correct path and further investment is reaching the most vulnerable. Understanding elite-level concerns, the role and needs of civil society, as well as business and trade unions are crucial to a holistic approach to CSSF aims.

As CSSF remains the primary source of ODA in north Africa, it is important new technical assistance proposals are scrutinised to ensure they meet with core CSSF aims.

Summary of Recommendations for FY 20/21

1. Amend the Programme Completion Review, Activity Proposal and Concept Note templates to include space for stronger consideration of technical assistance sustainability, most appropriate model of technical assistance, human rights, and social inclusion. Space to capture the nature and details of the role and responsibilities of the Country Leads on each individual project should also be included going forward.
2. Work to increase demand for projects classified as primarily focused on Gender (Gender Score of Gender Equality Marker (GEM) 2) within NATAF projects across each country, working closely with the MENA Regional Gender Advisor to cultivate generation of demand through greater understanding of need and impact.
3. Monitoring, Evaluation and Learning products should focus on creative forms of learning, to increase practical uptake of learning for HMG and externals, for example, interactive webinars over long written reports.
4. Increase focus on Disability.
5. Improve engagement with multiple actors to facilitate change that is rounded by multiple stakeholder views, such as civil society.