Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Jordan: UK-Jordan Partnership Facility Programme
Country and Region:	Jordan, Middle East and North Africa
IATI Unique ID:	CSSF-06-000033
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for International Development (DFID), Department for Education (DFE), HM Revenue and Customs (HMRC), Office of National Statistics (ONS)
Total Budget:	ODA: £2.02m			Non-ODA: £0.17m
Total Spend:	ODA: £0.89m			Non-ODA: £0
Original Programme Start Date: April 2019		End Date: March 2020
Outputs					Score
Establish a mechanism that will rapidly respond to requests for assistance from the Government of Jordan (GoJ) to emerging needs that demonstrate the UK’s whole-of-government approach and enhance UK influence					B
Pilot bilateral engagements from a range of UK departments and the private sector					A
Measuring UK impact on Stability in Jordan and the role of Fusion Doctrine underpinning the UK-Jordan partnership					B
Overall output score					B
Outcome Assessment: / The programme proved flexible and able to exploit new opportunities for public and private sector partnerships. Strong relationships have been built through a handful of partnerships, others have yet to be approved or given time to fulfil their potential. The results framework did not keep pace with changes in the programme design and implementation, which restricted the evidence base against which activities could be scored. Its move to become part of a larger political programme in FY20-21 is appropriate.
Final Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*	2019/20*
Programme Score	N/A	N/A	N/A	N/A	B	B
Risk Rating - low/medium/high					Medium
*output/outcome scores

What support did the UK provide?

The UKJPF is designed as a three-year programme commencing in FY19/20 to support the long-term relationship between the UK and Jordan, building on HMG’s commitment to the ‘partnership’ in 2017 and the outcomes of the London Initiative event in 2019. It is envisaged as a novel, responsive and flexible programme to enable a whole-of-government approach in the delivery of HMG’s commitment, in line with UK National Security Council (NSC) objectives. Support includes building multiple peer-to-peer relationships between UK government and its Jordanian counterparts; the provision of technical assistance on energy reforms and debt management; boosting the capability of the National Assistance Fund (NAF); and enhanced monitoring and evaluation of the UK NSC strategy.

The UKJPF followed on from the previous CSSF Economic Sustainability Programme. The facility subsequently merged with the Political Stability Programme (PSP) to form the Political and Economic Resilience Programme (PERP) from April 2020. This document therefore summarises a Programme Completion Review, with recommendations for projects carried over to the PERP.

What results did the programme deliver? Will they be sustained?:

The programme piloted, expanded and sustained peer-to-peer relationships between international experts and the Government of Jordan (GoJ). The technical support provided to the NAF increased its capacity to provide financial support to an additional 55,000 of Jordan’s poorest families and provided catalytic input and UK influence ahead of a new DFID £100m Social Protection Programme. Specialist assistance supported the GoJ and the IMF on debt issues. Through this, the UK strengthened key relations with the Ministry of Finance, enabling in-depth conversations to push key objectives within the economic pillar of the NSC strategy. The partnership between HMRC and the Income and Sales Tax Department is strengthening Jordan’s implementation of the international Automatic Exchange of Information (AEOI) protocol; developed transfer pricing; and influenced GoJ subscription to the Global Forum on Tax Transparency, avoiding possible EU sanctions on development assistance.

While project level results were achieved inside of 12 months, stronger programme governance and an investment in programme management resource will increase the prospect of the partnership achieving long-term impact.

The programme initiated an evaluation of the cross-government ‘Fusion’ approach. Implementation of this work was underway at the end of the review year but was not completed until September 2020, in part due to Covid-19 restrictions. The programme team provided evidence that one output of that work – a framework for enhancing and measuring integrated HMG delivery - has been well received by Joint Funds Unit and Cabinet Office colleagues as they take forward the Integrated Review.

What lessons have been learned?

- When designing a multi-year technical assistance facility, adopt best practice in strategic planning and implementation. Consider a phased approach to inception / proposal development, piloting and implementation, with a clear set of criteria against which performance can be assessed.
- Even small-scale activities require significant investment in programme and implementing partner management, which may best be provided by a dedicated technical assistance facility (TAF) team rather than relying upon programme staff with competing responsibilities.
- Project monitoring and results frameworks for adaptive programming such as the UKJPF need to be actively managed, flexible and responsive. They must both inform programming decisions and reflect changes in strategic direction.
- Smaller TAFs may fit better under larger multi-strand programmes that strengthen their purpose and increase their capacity for delivery.
- Such work must be demand-led, as well as delivering against UK interests, and utilising the capacity and expertise of UK government departments.
- If such work is to be replicated elsewhere, some other UK Government Departments will need to be better set up to work internationally. Government Partnerships International (GPI) can help with this. Delivery should encompass commercial partners when appropriate.
- Recognise the nature of political access and influence and find ways to embed the political capital built up through personal relationships into stronger institutional relationships that are resilient to changes in personnel.