Annual Review - Summary Sheet

PROGRAMME TITLE: Yemen Programme
Country and Region:	Yemen, Middle East and North Africa
IATI Unique ID:	CSSF-06-000013
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MOD)
Total Budget:	ODA: £19.62m			Non-ODA: £1.1m
Budget this FY	ODA: £6.42m			Non-ODA: £0.2m
Spend this FY	ODA: £5.4m			Non-ODA: £0.22m
Original Programme Start Date: April 2015		Planned End Date: March 2022
Outputs					Score
1. Technical assistance provided to and embedded in the UN Special Envoy for Yemen's Office					A
2. More political/conflict actors are represented and are participating in Track II and III processes, with women playing a prominent role					A
3. Governorate-level groups working on safety/security identified and functioning in Marib, Hadhdramaut, Shabwah and Al-Mahrah, with a focus on cross-governorate learning					A
4. Options for coordinated international approach to stabilisation identified with international stakeholders bought in.					B
5. Support provided to the Central Bank of Yemen and other key economic stakeholders in Yemen					A
Overall output score					A
Outcome Assessment: Substantial progress was achieved in implementing the CSSF Yemen programme in 2019-20. With the exception of outcomes 1 and 4, which have been partly achieved, all other outcome areas are either on track or advancing ahead of expectation. / This has been achieved despite a lack of real progress towards a political settlement and in a conflict context that has remained both protracted and at times dynamic. The early effects of the COVID-19 pandemic overlapped with the end of the financial year and had begun to negatively affect delivery. It is expected that the full impact of COVID-19 will not be known until the time of the 2020-21 Annual Review.
Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	A	B	B	A	B	A	A
Risk Rating - low/medium/high	High	High	High		High		High
*output/outcome scores
How has the programme changed during this period?			A new results framework was established in September 2019 following an HMG Yemen team planning workshop. This included new lines of effort on economic stabilisation.

What support did the UK provide in FY 19/20?

The Yemen CSSF programme supports the UK’s priorities and objectives for the country including: supporting the UN-led peace process, including exploring creative approaches; making a greater bilateral contribution to stabilisation; and building on UK influence in the region to help bring an end to the conflict alleviating the humanitarian situation and supporting economic stabilisation with technical advice to the Central Bank of Yemen.

The programme supports the UN to deliver a durable and sustainable peace process through official channels (Track I) as well as supporting a more inclusive political dialogue through non-governmental and civil society led processes (Track II and III) which include marginalised groups including women. The programme also contributed to local stabilisation through supporting conflict mitigation and prevention, as well as service delivery and improved governance.

Key results for FY 19/20:

The programme has delivered:

Good progress on inclusion, with a change in understanding and approach in Office of the Special Envoy of the Secretary–General for Yemen on gender in particular.

Successful implementation of conflict management and peacebuilding projects in 6 governorates.

Successful pilot projects analysing the war economy generated significant involvement from international counterparts, specifically engaging Kingdom of Saudi Arabia on stabilisation support demonstrated the UK’s added value. In parallel, piloting the development of the Yemen Conflict Sensitivity Platform was effective and good value for money.

Provision of quality technical assistance to support the Central Bank of Yemen (CBY) programme of reforms. Research and analysis on economic aspects of stabilisation.

Better programme management with improved and regularly updated results framework, a conflict sensitivity audit, gender mainstreaming with gender specific outputs and indicators and an increase in Monitoring and Evaluation (M&E) and stabilisation capacity/capability.

Key Lessons

Technical Advice (TA) can be an important contribution. However, its effectiveness is conditional on the political will of conflict participants to help create the environment in which it is used. UK TA to the Office of the Special Envoy of the Secretary-General for Yemen (OSESGY) is of high quality. It is not currently being fully utilised as the political process has not matured sufficiently. Consider making TA more flexible, and both proactive and responsive to context.

The importance of more qualitative roles for women in dialogue processes is becoming recognised and UK funded support has been instrumental. There is a continued need for UK advocacy and a co-ordinated UK gender strategy.

Track II work has been coordinated more effectively and has beenmade more coherent, however more needs to be done. The range and quality of potential partners and the issues tackled through Track II has been inappropriate to the requirements of the wider external context. Where the UK has led, this has had results, without UK leadership it impetus needs to be maintained.

The private sector and the economic stability are increasingly important in the context of ongoing state fragmentation. Finding ways of encouraging active engagement with peace-making and contributing to economic stabilisation is important and can be achieved.

Working across the country can have valuable benefits in terms of contributing towards dialogue and helping to identify issues and areas of common interest and concern. CSSF activity will look to work across both Houthi and Government controlled areas.

Summary of Recommendations for FY 20/21

Continue to adapt/flex the CSSF programme based on latest evidence and conflict analysis to ensure the programme remains responsive and able to adapt to changes in the external context.

Assess the UK’s role leading international donor engagement in Yemen on conflict and stability issues and look for burden sharing with other donors if beneficial.

Identify areas of UK value-added and consider ways of increasing CSSF contributions, including reactivating the Saudi/UK dialogue on stabilisation. Prioritise the establishment of the Yemen Stabilisation Fund, focussing on innovation and responsiveness.

Consider outreach activities to engage Yemen’s southern populations – including extending the Strategic Thinking Initiative and support to the OSESGY Aden office.

Broaden programming to align with UK policy objectives, including security, preventing/ countering violent extremism and countering Iranian influence.

Further develop support for economic stabilisation, where possible building on the successful partnership with USAID in support of the CBY.

Reformulate the Results Framework, grouping outputs and reducing number of outcomes.

Ensure that research and analysis by project partners is circulated in accessible form to the wider Yemen team. Consider regular updates and specific products that can input into policy or programme review processes.