Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Jordan: Political Stability Programme (PSP)
Country and Region:	Jordan, Middle East and North Africa
IATI Unique ID:	CSSF-06-000016
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £20.97m			Non-ODA: £0
Total Spend:	ODA: £21.49m			Non-ODA: £0
Original Programme Start Date: April 2018		End Date: March 2020
Outputs					Score
1. Increased sustainable capability in campaigning by Government of Jordan (GoJ) ministries and agencies involved in the Vocational Training Council (VTC) campaign					A+
2. The opportunity for citizens to hold GoJ institutions accountable is increased					A
3. Local government councils understand community needs and priorities					A
4. Local government is technically and financially more capable of delivering services					A
5. Sustainable infrastructure in target locations meets the needs of the community					B
6. Community leaders in target locations are better at conflict resolution.					A+
7. Youth, women and refugees have more opportunities to engage politically					A
8. Tensions and underlying drivers of conflict within Jordan are tracked and understood					A
9. New interventions scoped, and research and lesson learning conducted					A
10. Gender sensitivity, conflict sensitivity and sustainability embedded in programme activities					A
Overall output score					A
Outcome Assessment: The programme was successful in meeting most of its outcome indicators, making progress in several key areas. However, the success of the programme relied heavily on well-established projects while new projects struggled to move forward on the two central elements of governance and rule of law. This was due to implementation delays.
Final Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	N/A	N/A	N/A	A	B	A	A
Risk Rating - low/medium/high	N/A	N/A	N/A		Medium		Medium
*output/outcome scores

What support did the UK provide?
The programme contributed to a World Bank multi-donor trust fund that builds capability and accountability of Municipal Authorities, including through a local job creation fund (Innovation Fund). Technical assistance on strategic communications supported the Government of Jordan (GoJ) spokespeople to help deliver the Jordanian Prime Minister’s economic reform road map and communication plan. Conflict-management training and infrastructure provision to areas most at risk of inter-communal disputes helped reduce community tensions and strengthen citizen-government dialogue. Technical assistance and capacity building supported implementation of the Royal Court Commission’s legal reform recommendations and the Government of Jordan’s Judicial Sector Strategy. Both the central government and vulnerable communities benefitted from additional support on good governance.

What results did the programme deliver? Will they be sustained?:

- The Social Cohesion project showed good impact-level effect on reducing community tensions through a blended delivery approach of infrastructure and conflict management training. These two components are mutually reinforcing, allowing the programme to show immediate, tangible outcomes whilst addressing longer term conflict drivers.
- In Salt a ‘One Stop Shop’ for local government services was introduced that provides information and services across a range of local government issues. Lessons learnt will be used by the GoJ to inform further the outreach of ‘One-Stop-Shops’ in 2021.
- 21 participating municipalities completed more than 128 public consultations to identify and prioritise municipal investment needs. 46 infrastructure sub-projects were approved for implementation, of which 31 are complete and eight are under implementation.
- Capacity building in nine municipalities enabled them to develop competitive bids for the Innovation Fund, resulting in 13 projects approved with full operational and maintenance plans.
- Six new local infrastructure projects completed and handed over to municipal authorities. Central ministries or community-based organisations will administer as ‘final owners’. A final owner ‘Sustainability of Community Projects’ workshop held for 120 people to reinforce sustainability plans.
- The National Network continued to grow with 81 new community leaders this year (48% female) bringing the total to 650. It showed evidence of the potential for creating national dialogue at the grass-roots level and this was a clear outcome-level success.
- Government officials gained the skills and confidence to plan proactively and develop an engaging, coherent and transparent communications campaign. There is anecdotal evidence from GoJ that this helped collaboration between the Prime Minister’s Office and the National Crisis Centre on communications during the initial crisis response to the COVID-19 pandemic.
- Scoping for a new rule of law project were finalised, commercial implementer competitively selected and inception report complete.
- Local Political and Economic Analysis completed and the initial stages of a Social Norms Study also completed, which will help inform the design of the Inclusive Accountable and Governance Project.

What lessons have been learned?

1. Without absolute clarity on the processes and criteria for progressing CSSF projects through the central approvals in the FCDO, some impact will be lost between funding cycles.
2. Delivery partners operating in the same municipalities must ensure their work is aligned with the overall programme theory of change and understand where they fit in when working towards shared objectives.
3. Activity should focus more on being “adaptive” rather than “reactive”.
4. Where activity in peer-to-peer support to the GoJ has mixed results and increases reputational risk the programme team should undertake risk mitigation measures.
5. Alignment between HMG policy aims and programming could be improved and translated into an agreed set of policy aims, notably on political reform, bearing in mind lessons from previous CSSF programming in this area.
6. Awareness of Embassy outreach visits could be improved through better communications.