Annual Review - Summary Sheet

PROGRAMME TITLE: Lebanon: Security Programme
Country and Region:	Lebanon, Middle East and North Africa
IATI Unique ID:	CSSF-06-000005
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Ministry of Defence (MOD)
Total Budget:	ODA: £25.25m			Non-ODA: £35.7m
Budget this FY	ODA: £8.15m			Non-ODA: £7.7m
Spend this FY	ODA: £8.08m			Non-ODA: £6.83m
Original Programme Start Date: April 2019		Planned End Date: March 2022
Outputs					Score
Lebanese Armed Forces (LAF) company groups trained and able to plan and conduct proactive, effective and conflict and gender-sensitive urban operations that are compliant with International Humanitarian Law (IHL) and the Law of Armed Combat (LOAC).					A
LAF Land Border Regiments (LBR) trained and able to plan and conduct proactive and intelligence-led land border operations using: 1) a validated doctrine, 2) concept of operations, and 3) standard operating procedures, that together make effective use of the capabilities provided.					A
Community Policing Model based on police-public partnerships mainstreamed at Police of Beirut HQ and 1st Territorial Company.					B
Build institutional preparedness for improved response to security incidents by the Internal Security Forces (ISF) in coordination with the LAF.					B
Vulnerable youth (including men, women, boys and girls) – empowered and supported to be positive elements in their societies. The focus will be in Tripoli, Beirut and the Palestinian camps					B
Grow the religious discourse by raising awareness on the contradiction between extremism and faith, and promoting the values of democracy, citizenship and human rights.					B
Overall output score					B
Outcome Assessment: / Support to the LAF has clearly contributed to its increased effectiveness in maintaining external and border security. The LBRs have demonstrated increased effectiveness in border protection and operations. Whilst public perception surveys indicate good levels of trust in the LAF generally, and among border communities, it remains important to continue to maintain and improve the programme’s conflict sensitivity offer. / Support to the ISF has helped produce improvements in policing at a community level. There are currently no processes in place to measure crime levels in Beirut (the target). The scheduled survey of public trust in the ISF has been delayed. These factors, combined with a weak results framework, mean that it is impossible to judge the likelihood of achieving the outcome of maintaining effective internal security during FY19-20. / In specific locations and in the context of localised events, the quality of activity in increasing the resilience of vulnerable groups is high, however the reach is low in terms of numbers of people impacted.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	A	A	B	A	A	B	B
Risk Rating - low/medium/high	High	High	High	High	High	High	High	High
*output/outcome scores
How has the programme changed during this period?			The activities across the programme's different components adapted to COVID-19 in a multitude of ways, from trainings moving online as lockdowns restricted movement, and people in vulnerable communities starting the production of limited Personal Protective Equipment (non-medical grade) as a short-term income generation measure, to working with civil defence and other state or community actors to deliver COVID-19 related public health messages.

What support did the UK provide in FY 19/20?

The CSSF Lebanon Security Programme has:
- Supported the LAF to secure the Lebanese border with Syria, and improved the LAF’s internal security role and function;
- Improved the ISF’s effectiveness and accountability to make it into a more responsive and responsible security provider;
- Engaged vulnerable youth to become positive elements in their societies and provided alternative religious narratives through the use of influencers on and offline, as well as the production and use of supporting digital content for use online.
Key results for FY 19/20:

Completed the construction and delivery of the final border towers for the LBR and supported a series of test exercises delivered by the LAF, demonstrating that regiments are achieving the necessary standards that the CSSF-funded training sought to instil.

The ISF formally adopted a new Public Order Manual, a key component in the CSSF’s long-term goal of improving security responses. The ISF’s response to public protests and public order incidents during and after the October 2019 protests was assessed to be more proportionate than may have been the case previously. CSSF had focused on non-violent public order management, with improved performance observed throughout.

In Beirut, the CSSF’s refurbishment of police stations, new recruitment, including of female officers, and new data management systems have contributed to an increase in members of the public using the police stations and reporting crime.

In Palestinian refugee camps support to civil society organisations enabled issues of public interest to be resolved non-violently, with additional added value provided by the promotion of transparent and collaborative approaches between communities, thereby reinforcing resilience through the promotion of new governance norms. These activities were supported by an online platform that was used to promote positive alternative messaging and raising awareness of social stability threats in the camps, reaching 30,000 followers.

Work with religious leaders culminated with a forum in February 2020 and led to the promotion of the religious leaders’ own online narrative, with the inclusion of articles and videos.

Key Lessons:

- The programme has achieved successes in gender equality - such as increasing women’s involvement in, and access to, the police – and now needs to develop deeper knowledge of how women experience security differently to extend this from the police to the ISF/LAF.
- UK support over nearly ten years to Lebanese security forces has resulted in a significant increase in land border security. Moving forward, to continue increasing the effectiveness of these forces requires allocating a greater proportion of resources to security sector governance and accountability.
- Effective security sector governance and accountability requires both top-down and bottom-up momentum: engaging senior security and political leaders to ensure robust processes for holding soldiers and police to account are in-place and working with the media and civil society to report on the security forces’ conduct.

Summary of Recommendations for FY 20/21

- Review and update the programme’s Results Framework.
- Assess and improve current gender analysis and reporting; provide gender training to current implementors and at the start of new projects; consider conducting a full gender audit.
- Work with the LAF project implementer to develop a more detailed and robust conflict sensitivity plan; ensure there is a system for monitoring progress and implementation.
- Consider the relationship between the LAF and the ISF and how CSSF funded interventions with both institutions can better reinforce one another, for example using a joint public perceptions survey.
- Develop and facilitate more regular communications between the implementing partners and identify ways where sharing analysis and collaboration between projects could be beneficial.
- Build on the existing work and entry points on security sector governance and accountability, making this an even stronger emphasis of the programme going forward.
- Explore what longer-term and more sustainable support can be offered to residents of Palestinian camps.
- Where an activity is about changes in attitude, consider funding the tools and training so that influencers can understand whether attitudes are changing and take further action if attitudes do not change as needed.