Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Migration: Eastern Route (Greece) Programme
Country and Region:	Greece
IATI Unique ID:	Border Force Cutters programme: CSSF-01-000008 / Greece programme: CSSF-01-000020
HMG Partners / (LEAD in bold)	Home Office (HO), Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: / Greece: £1.52m / Cutters: £3.30m			Non-ODA:
Total Spend:	ODA: / Greece: £1.50m / Cutters: £3.30m			Non-ODA:
Original Programme Start Date: April 2017		End Date: March 2020
Outputs					Score
Vulnerable migrants access appropriate care and support services					A
Children are provided with temporary protection					A
Emergency and winter provision of urgent non-food items is distributed					A
Cutters are deployed in line with European Border and Coast Guard Agency (FRONTEX) requirements to assigned areas of operation					A
Cutters’ crew gain awareness and knowledge of protection measures/procedures to treat at-risk migrants					A
Overall output score					A
Outcome Assessment: A
Final Outcome Score: A			Risk: Low

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score: Cutters			A	A	A	A
Risk Rating - low/medium/high			Medium/High		Medium/High
Programme Score: Greece (RIS)					A	A**	A	A
Risk Rating - low/medium/high					Medium		Low
*output/outcome scores
Please note that the programme scores are not ‘like for like’ meaning that the projects under this financial year are different to those of the previous years. / ** Please note that the score of A/A and the overall risk rating of medium for the 2018/19 Greece Programme refers only to the Reception and Identification Services (RIS) project in the previous Eastern Route Programme Annual Review.

What support did the UK provide?

The overarching purpose was to provide immediate humanitarian support through effective management of migration in Greece. And in doing so, to improved the humanitarian conditions for (vulnerable) migrants.

This review brings together two programmes – the Greece Programme and the Border Force Cutters Programme which both operate in the Greece region and have a shared purpose.

The programme was comprised of the following activities:
1. Providing interpreters to the Greek Reception and Identification Service (RIS). The interpreters worked on the Greek island hotspots, facilitating vulnerable migrants to access essential services including medical and psychosocial care.This aimed to move them through the registration and asylum processes faster. This served as an interim measure while Greek authorities stood up their own sustainable solution.
2. Funding for a shelter, providing protection for the most vulnerable unaccompanied children on Samos. This demonstrated to Greek authorities that similar facilities should be funded by Greek National Programme/EU funding in future.
3. Urgent in-year funding in December 2019 for the purchase of essential winter supplies to improve conditions for vulnerable migrants on the Greek island hotspots. The project was delivered by the International Organization for Migration (IOM), working closely with RIS.
4. The Border Force cutter programme received funding to combine immediate protection and humanitarian assistance through humanitarian search and rescue (SAR) operations in the Aegean Sea, working alongside national coastguard resources to improve domestic skills in these activities.

What results did the programme deliver? Will they be sustained?

- The interpreters provided much needed support to migrants. In FY 19-20 (based on three quarters because of Covid-19 related disruptions in Q4), interpreters regularly assisted migrants in large numbers. For example:
  - Intepreters assisted unaccompanied minors on 1,077 occasions, single-parent families on 417 occaisions and over 65s on 255 occaisions;
  - Interpreters assisted in 5,026 medical assessments and 1,166 psychosocial assessments;
  - Interpreters assisted in 2,886 information kiosk services and 12,151 other services;
  - Interpreters indirectly contributed towards 7,944 vulnerability assessments.
- Children deemed to be most vulnerable were given much needed shelter. All were enrolled in education and received psychosocial support and had access to recreational facilities.
- The UK provided emergency non-food items to improve conditions for (vulnerable) migrants, including accommodation and office space for staff working directly with the refugees.
- Border Force Cutters conducted humanitarian search and rescue operations in the Aegean. In FY 2019-20, 1,584 individuals were rescued by HMC Valiant, and HMC Valiant patrolled for a total of 1,424 hours and completed 145 search and rescue (SAR) missions.

What lessons have been learned?

- The quality and skill of the interpreters and the cutter crew was paramount to the programme’s success. Many went beyond their role while dealing with highly stressful situations which occasionally involved violence, self-harm and suicide.
- While pastoral care for UK personnel was provided, more psycho-social and decompression support was needed. This was important particularly for the interpreters, many of whom were working in challenging humanitarian situations for the first time, where the environment had a substantial emotional and psychological impact.
- The highly demanding nature of humanitarian work in this context, where a range of competing urgent priorities were being met, led to issues collecting regular and accurate data. Subsequent data verification was also difficult.