Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Multilateral Strategy Championing our Values
Country and Region:	Multilateral Strategy Fund - CSSF
IATI Unique ID:	CSSF-01-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MOD)
Total Budget:	ODA: £24.19m			Non-ODA: £0
Budget this FY	ODA: £5.1m			Non-ODA: £0
Spend this FY	ODA: £5.08m			Non-ODA: £0
Original Programme Start Date: 1 April 2016		Planned End Date: 31 March 2021
Outputs					Score
1.0 Increase in number of women participating in and informing decision-making processes and responses related to conflict prevention and peacekeeping. UN targets: women form 15% of deployed military and 20% of police by 2028 in peace operations.					A
3.1 Strengthened coordination between all UN departments and agencies on response to victims of Sexual Exploitation and Abuse (SEA)					A
3.3 Office of Victims' Rights Advocate (OVRA) / Department of Peace Operations (DPO): Survivors of SEA are offered information about recourse and adequate and effective local level assistance when reporting SEA to authorities/UN.					A+
3.4 Conduct and Discipline Service (CDS): Accountability of all UN personnel on SEA issues is strengthened through the enhanced capacity for the implementation of the Secretary-General’s programme of action on prevention, enforcement and remedial action.					A
Overall output score					A
Outcome Assessment: / Owing to Covid-19, this Annual Review focuses on a sub-component of the Championing our Values (CoV) Programme, looking at work responding to Sexual Exploitation and Abuse (SEA) by UN peacekeepers and civilians, and at activities related to Women, Peace and Security (WPS). / There is evidence of progress across both outcomes, with new initiatives being set up and embedded, and political endorsement coming from the UN Secretary General (SG). SEA activity, in particular, has shown an improvement since the score of ‘B’ last year, whilst WPS work included establishing a new project, which lays the groundwork for future impact. However, there remain questions over the sustainability of outcomes, particularly on SEA where there is an ongoing question about funding sources and sustainability. This is likely to be constrained further owing to Covid-19. / Implementation of recommendations from the Annual Review of 2018/19 is partially complete. Policy engagement has increased but is still patchy. Reporting from partners is good. Other recommendations from AR 2018/19 are outstanding for a variety of reasons. As an example, increasing the programme’s footprint in NY has been difficult with headcount caps and uncertainty about future funding.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*	2019/20*
Programme Score	A	B	A	A	A
Risk Rating - low/medium/high	Medium	Medium	Medium	Medium	Medium
*output/outcome scores
How has the programme changed during this period?			At the end of 2019/20 it was agreed that SEA projects would be transferred to the Peacekeeping programme. The Elsie Project was fully operational from October 2019 and given a funding uplift for 2020. Policy engagement has increased. Impact is communicated to Ministers and external audiences more regularly and is a central plank of policy engagement at Post. Spend has been impacted owing to Covid-19 restricting international travel.

What support did the UK provide in FY 2019/20
This Annual Review focuses on four of the eleven projects under the Championing our Values Programme, in line with revised guidelines for conducting Annual Reviews during the Covid-19 pandemic. The four chosen include three oriented towards preventing Sexual Exploitation and Abuse (SEA) and the Elsie project, which aligns with the Women Peace and Security (WPS) objective.
- SEA: UN Department of Management Strategy, Policy and Compliance (DMSPC) - Conduct and Discipline Service (£0.5m).
- SEA: Promoting Redress for Victims of Sexual Exploitation and Abuse through the DPO (£0.3m).
- SEA: Office of Victims’ Rights Advocate (OVRA) (£0.2m).
- WPS: Elsie Initiative: Women and Peacekeeping (£1m).

Key results for FY 2019/20:
- Good coordination in delivering the SG’s programme of action, indicated by:
  - OVRA output level – this project achieved envisaged outputs;
  - CDS – the UN now has the tools it requires to be more systematic and is already putting these to good use; and
  - OVRA / DPO: Survivors of SEA are offered information more consistently about recourse measures available, and adequate, effective local level assistance when reporting SEA to authorities and/or the UN.
- The Elsie Trust Fund has established ‘proof of concept’, laying the groundwork for more systemic change.

Key Lessons
- Supporting SEA work requires a long-term commitment owing to growing needs and limited donor support. Genuine change involves culture change, which will take years or even a generational shift.
- Where government Policy Leads and Military Advisors have been involved directly in projects, there has been evidence of improved results. However, this can slip without continued engagement.
- While the SEA projects appear to be economic and efficient in delivering short-term changes in line with UK values, there is a difficult question for the Multilateral portfolio about how best to evidence and resource these projects to achieve long-term sustainable gains. Without this, there is a risk that projects will calcify without achieving strategic effect on the UN system.
- Monitoring: It is difficult to measure the value of these projects without a proper system to monitor and evaluate. There is some anecdotal/qualitative evidence of UK influence and leverage by funding these interventions at a larger scale than would have been possible bilaterally. There are also some positive results coming from reports in country, particularly around how SEA is being tackled by the UN. A feedback loop, which captures the positive results on the ground would help demonstrate value for money for the projects funded.
- Good SEA/GBV response requires looking at the whole community and addressing underlying vulnerabilities, potentially straying into more traditional humanitarian/development work. Drawing greater synergies here could improve sustainability.

Summary of Recommendations for FY 20/21
- The Programme Board should continue to condense the CoV portfolio into fewer projects with clearer alignment to a long-term strategy and explore how to better evidence value for money.
- MuSt Programme team should review its programme management resource to identify how to get the most from the opportunities CSSF projects create within given resources.
- MuSt Programme team should explore developing appropriate tools for tracking impact, particularly on influence and leverage.
- MuSt Programme team should explore multi-year programming options with JFU/FCDO Finance, recognising that HM Treasury makes funding decisions.
- The Multilateral Portfolio Board should ensure programmatic activity is aligned with HMG policies on our voice in the UN and our bilateral engagement, aiming at maximising project outputs (e.g., communication products for SEA) and mitigating risks of SEA activities being deprioritised owing to lack of interest from UN Member States.
- Covid-19: The programme will need to continue to adapt projects and respond to Covid-19 challenges.