Annual Review - Summary Sheet

PROGRAMME TITLE: Migration: Eastern Route (Turkey) Programme
Country and Region:	Turkey
IATI Unique ID:	CSSF-01-000006
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Home Office (HO)
Total Budget:	ODA: £8.52m			Non-ODA: £0.13m
Budget this FY	ODA: £2.13m			Non-ODA: £0
Spend this FY	ODA: £2.06m			Non-ODA: £0
Original Programme Start Date: 1 April 2017		Planned End Date: 31 March 2022
Outputs					Score
Syrian schoolgirls take part in pilot research programme of targeted interventions that will assess their school attendance and provide evidence-based policy tools to the Ministry of National Education, enabling sustained attendance. Research done in a gender and conflict sensitive way.					A
Nationwide systems set up to increase the return of irregular migrants from Turkey to their countries of origin.					A
Increased knowledge of irregular migration by Directorate General for Migration Management (DGMM) Central and Provincial Staff.					A
Establishment of cooperation mechanisms between Turkey and Countries of Origin to allow for productive engagement on migration issues.					A
Turkish Coast Guard Command gain greater knowledge on irregular migration, legal frameworks and migrants' rights issues including gender sensitivity.					A
Overall output score					A
Outcome Assessment:
Outcome Score: A			Risk: Low/Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	Amber/Red	B	B	A	A	A	A
Risk Rating - low/medium/high	N/A	High	Medium		Medium		Low/Medium
*output/outcome scores
How has the programme changed during this period?			With the onset of Covid and resulting lockdowns, engagement with key stakeholders became virtual and a number of programme deliverables had to be paused during Q4.

What support did the UK provide in FY 19/20?

The programme was delivered through eight projects during the financial year 2019/20. The programme supports the delivery of all pillars and strands of the National Security Council’s (NSC) Illegal Migration Strategy. It also supports the Migration and Organised Immigration Crime (OIC) strand of the NSC’s Turkey Strategy.

Drawing on a refreshed Theory of Change (ToC) with inputs from other HMG departments and partners in Turkey, the programme pursued outcomes that seek to give Turkish beneficiaries the tools and evidence necessary to take more coherent and strategic decisions in the field of migration management. It continued to support the strengthening and capacity building of Turkey’s frontline migration institutions (principally the Directorate General of Migration Management (DGMM) and the Ministry of Family, Labour and Social Services (MoFLSS)) to enhance capacity on combating human trafficking and supporting Assisted Voluntary Returns (AVR) through developing Turkey’s national AVR mechanism (N-AVR). It also initiated several new projects, including a pilot intervention research project with the Turkish Ministry of National Education (MoNE). Focussing on refugee schoolgirls, this seeks to contribute towards the delivery of a more inclusive education system, which promotes greater social cohesion. Other work included a training programme for the Turkish Coast Guard; and building monitoring and evaluation (M&E) capacity for Turkish government stakeholders working on migration.

Key results for FY 19/20:

As host to the world’s largest number of refugees and irregular migrants, Turkey is a key destination and transit country for those seeking safety and opportunities outside of their own country. While the majority are Syrian refugees, there are a significant number of migrants of other nationalities including Afghans, Iraqis, Somalis and Pakistanis. Movement out of Turkey towards Europe escalated dramatically in 2015. While the subsequent EU-Turkey Statement agreed in 2016 led to a reduction in flows across the eastern Mediterranean route, significant challenges remain in Turkey’s capacity to sustainably absorb migrants through promoting social cohesion. The refreshed Theory of Change has adapted to this context.

The 19/20 project bid was written prior to the Covid-19 pandemic, which had an impact on Q4, albeit one that has been well managed. Furthermore, due to delays because of the pandemic, this Annual Review took place mid-way through the 20/21 programme year. The timing is reflected in this review, which focuses on the 19/20 programme, but touches upon the 20/21 programme where relevant.

The review focused primarily on four projects: Strengthening migration management; a pilot intervention research on refugee schoolgirls in Turkey; building M&E capacity for partners; and reinforcing the Turkish Coast Guard’s capacity. The rationale for this choice is that all of these projects are ongoing in the current FY (20/21), and three of them are new projects. Between them, they also cover the different implementing partners running these programmes. The following key results relate to these four projects:

- A national AVR mechanism has been established under Turkey’s Directorate General of Migration Management (DGMM). The N-AVR should soon be operational and, as Turkey's first national AVR mechanism, represents a significant achievement.
- The programme led to the strengthening of engagement between Turkey and Countries of Origin (CoO); co-ordination with Pakistan and Afghanistan was particularly successful.
- An action research project on the integration of Syrian schoolgirls in Turkey carried out by a research team from a Turkish university is underway, endorsed by the Ministry of National Education (MoNE) and working in collaboration with the EU-funded PICTES project (Promoting Integration of Syrian Children into Turkish Education System). All the indicators suggest that the building blocks are in place for an ongoing policy discussion with MoNE on emerging findings which promote inclusion of Syrian schoolgirls within the Turkish education system.
- A new M&E project was implemented to help key government migration institutions develop the capacity to design their own sustainable projects making them less reliant on donor assistance.
- A programme of training on irregular migration, legal frameworks and migrants' rights issues including gender sensitivity was initiated with the Turkish Coast Guard (TCG).
Key Lessons

The current programme has put significant investment in internal review processes, critical reflection and consolidation as a result of previous ARs. As a result, it has become increasingly focused, aligned and informed. The following lessons are a summary of some of this achievement.

- Strong local knowledge leads to projects with clear buy-in from government and implementing partners (IPs), and ‘richer’ insight and programming results.
- There are significant benefits derived from having staff with strong institutional knowledge, who have been in the role for a number of years and who have built up their expertise through training in key aspects of programming (such as gender and M&E).
- Training has most impact when implementing partners are flexible and adaptive to the context. The quality of IPs is crucial in this regard.
- The complex and long-term challenge of creating social cohesion demands going beyond training and incorporating other methodologies and approaches, such as action research.
- Strong partnerships across the programme – within the Embassy, across-HMG, with government actors and implementing partners – leads to a more impactful programme.
- Ongoing monitoring through close contact with IPs and beneficiaries has significant value and importance in achieving and articulating results.
- Recognising the complexity of the political environment and ensuring strong connections between policy and programme, drawing on robust local understanding, is critical.

Summary of Recommendations for FY 20/21

- Continue to concentrate on social cohesion as a core focus of the programme and develop a deeper understanding of sustainable programme interventions that can be used to help to tackle this complex challenge. Continue to communicate the impact of the programme to London and beyond, including to other posts with migration programmes.
- Continue to diversify IPs in order to ensure sufficient choice to respond to the challenges that the programme is trying to meet.
- Work with IPs who are invested in making a change and impact, and therefore are willing to adapt and go beyond their remit.
- Ongoing recognition needs to be made of the importance of local staff. Therefore, strive for continued engagement and employment of local staff for this programme and ensure sufficient investment in staff.
- Give sufficient time to think through ideas for future programming, including a focus on migrants who are not eligible for refugee status.
- Think beyond Turkey and explicitly incorporate both regional and ‘whole of route’ thinking into future programming.
- Ensure ongoing awareness of political and cultural factors that have the potential to hinder programme outcomes and outputs and continue to recognise the importance of careful negotiation around these.