Annual Review - Summary Sheet

PROGRAMME TITLE: Multilateral Strategy Peacebuilding CSSF Programme
Country and Region:	Multilateral
IATI Unique ID:	CSSF-01-000002
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £33.2m			Non-ODA: £0
Budget this FY	ODA: £9m			Non-ODA: £0
Spend this FY	ODA: £9m			Non-ODA: £0
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs: The outputs in 2019/20 have been assessed according to the performance of individual projects.					Score
DPPA Multi-Year Appeal					A+
Joint UNDP - DPPA Building National Capacities for Conflict Prevention					A+
UN Global Programme on Strengthening the Rule of Law and Human Rights to Sustain Peace and Foster Development					A+
Outcome Assessment: The Multilateral Strategy (MuSt) Peacebuilding Programme has adapted to deliver results amidst a challenging global context, scoring an A at the outcome level – mostly exceeding, but in some cases failing to attain, targets for each outcome indicator.
Outcome Score: A			Risk: Medium

Summary of Peacebuilding Programme Performance
Year	2015/16	2016/17		2017/18*		2018/19*		2019/20*
Programme Score	A	A		A+	A+	A+	A+	A	A+
Risk Rating - low/medium/high	Medium	Medium		Moderate		Moderate		Moderate
*output/outcome scores
How has the programme changed during this period?			During the 2019/20 financial year, all three projects under the MuSt peacebuilding programme were forced to adapt significantly owing to limitations on international travel and person-to-person engagement caused by the Covid-19 pandemic.

What support did the UK provide in FY 2019/20?
The overall agreed budget disaggregated by each key component of the programme is as follows:
PROJECT/COMPONENT	LEAD DEPT	IMPLEMENTING ORGANISATION	BUDGET	FY 2019	START	END
DPPA Multi-Year Appeal	DFID	DPPA	£11.2m	£2.8m	April 2016	March 2020
Joint UNDP - DPPA Building National Capacities for Conflict Prevention	DFID	UNDP, DPPA	£3.75m	£2m	April 2016	March 2020
UN Global Programme on Strengthening the Rule of Law and Human Rights to Sustain Peace and Foster Development	DFID	UNDP	£1.2m	£0.5m	April 2016	March 2020

SUMMARY OF PROGRESS AND KEY RESULTS FOR FY 2019/20:
Department of Political Affairs and Peace Building Affairs (DPPA) - Multi Year Appeal (MYA): DPPA endeavoured to adapt the MYA to respond to the changed global environment under Covid-19 and did so with some success. They adapted in-person training, conducting online support on conflict analysis for Political Affairs Officers. The Mediation Support Unit was used to help conflict actors find appropriate ways of maintaining dialogue. DPPA published its 2020-22 Strategic Plan, which the UK was able to influence significantly, highlighting the political nature of conflict prevention and the importance of ‘sustaining peace’. The MYA enabled DPPA to play an important role in conflict mediation, supporting disputed electoral processes and politically sensitive referendums including in Sudan, Bolivia, and Papua New Guinea.

Global Programme on Strengthening the Rule of Law and Human Rights for Sustaining Peace and Fostering Development (Global RoL-HR Programme): Key results included the deployment of experts, who provided assessments and strategic advice on justice, corrections and gender approaches to community policing in Cameroon, Mali, Liberia, and Burkina Faso. The programme supported the Central African Republic (CAR) in consolidating its Special Criminal Court and a joint rule of law programme. The Global Focal Point (GFP) provided critical support during transitions from UN peacekeeping to political missions, co-ordinating well with UN country teams. On gender, the GFP provided technical assistance to strengthen women’s access to justice and to support the development of mechanisms aimed at addressing sexual and gender-based violence in Central African Republic, Liberia and Malawi.

United Nations Development Programme (UNDP) and DPPA - Joint Programme, Peace and Development Advisers: This period saw the deployment of 15 Peace and Development Advisers (PDA) and an increase in total PDAs from 49 to 54, with 20 teams (increased from 17) of mixed specialists and national PDAs, enhancing impact. PDAs supported targeted initiatives including electoral scenario planning with the Guatemalan Supreme Electoral Tribunal and support to the UN Country Team in Tunisia as it developed an evidence-based and risk-assessed Common Country Analysis, bringing in over 250 Tunisian experts to contribute.

LESSONS LEARNED/ACTIONS TAKEN SINCE LAST REVIEW
The following actions have been taken in 2019/20 following the last annual review.
At the programme’s instigation, DPPA engaged external consultants to explore new means for capturing value for money of the MYA. DPPA has developed a 2020/22 Strategic Plan, having consulted extensively with UN Member States (including the UK) and other international partners.
- The MuSt team took action to improve coordination between Security and Justice policy teams in DFID and the FCO. M&E reporting and processes have been strengthened by broadening participation in decision-making including in the GFP technical and steering committees.
- We assess that extra-budgetary funding mechanisms for DPPA, such as the MYA, will be necessary for as long as the core budget support is (i) insufficient to cover core costs; and (ii) not sufficiently flexible to enable a rapid and high-quality response to sustain peace.
- Reporting continues to focus on inputs or outputs, more than transformational impact. However, DPPA is making progress in determining metrics that quantify benefits in time and effectiveness in how the MYA extra-budgetary funding mechanism responds to emerging crises.
- The strength of the UNDP/DPPA Joint Programme and specifically the effectiveness of the PDAs relies on the quality of the PDAs themselves, and on the enabling environment created by a strong, responsive and flexible Secretariat.

SUMMARY OF KEY RECOMMENDATIONS FOR THE NEXT YEAR
- All programmes: The UK should continue to play a leadership role in convening international partners to support the DPPA MYA and the UNDP/DPAA Joint Programme. Activities funded through the MYA rely heavily on successful application and adoption of technology and innovation.
- DPPA MYA: The UK should look to make un-earmarked contributions wherever possible for the next year, to enable rapid and effective conflict prevention response in fragile states deemed a low priority by MYA’s other donors. A more “bottom-up” analysis-driven approach would be more effective in identifying top global priorities for peacebuilding and conflict prevention.
- Global Focal Point: To continue progress on monitoring and evaluating, greater co-ordination is needed to ensure coherence across the UK’s support for security and justice and encouragement of GFP implementers and partners to strengthen their M&E procedures.
- UNDP-DPPA Joint Programme: The Secretariat should ensure a sensible balance on national monitoring to ensure it does not constrain activity with an over-emphasis on reporting. Monitoring can be done also through regular engagement with UN Resident Coordinators (RCs) and PDAs.