Annual Review - Summary Sheet

PROGRAMME TITLE: UN Reform
Country and Region:	CSSF Multilateral Strategy (MuSt)
IATI Unique ID:	CSSF-01-000019
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget:	ODA: £8.1m			Non-ODA: £1.6m
Budget this FY	ODA: £3.1m			Non-ODA: £0.6m
Spend this FY	ODA: £2.7m			Non-ODA: £0.29m
Original Programme Start Date: Apr 19		Planned End Date: Mar 22
Outputs					Score
1. DATA CUBE					A
2. STRENGTHENING GOOD GOVERNANCE AT THE SENIOR LEADERSHIP LEVEL					A
3. INDEPENDENT SYSTEM WIDE EVALUATION					A
4. ONE HUMAN RESOURCES (One HR)					B
5. ACTION FOR LEARNING CONFLICT ANALYSIS					A
6. FLEET MANAGEMENT & COMMON PREMISES					A
7. FINANCING PEACEKEEPING TRANSITIONS					A
8. HUMANITARIAN DEVELOPMENT PEACEBUILDING & PARTNERSHIP FACILITY					B
9. INTEGRATING CONVENTIONAL ARMS CONTROL INTO CONFLICT PREVENTION					B
10. RESIDENT COORDINATOR OFFICE (RCO) SUPPORT					B
Overall Output score					A
Outcome Assessment: / The first year of the UN Reform programme has faced challenges owing to the programme team’s capacity, being drawn away from programme management to provide support to Brexit and the Covid-19 response. However, despite projects being implemented for only six months by the end of FY 2019/20, collectively the ten projects within the UN Reform programme are starting to achieve a broader catalytic effect through experiential testing and proving concepts. The narratives and evidence presented within some of the project-level quarterly reports was of a high standard. The programme could be managed more coherently to demonstrate this effect at the programme level. / It is clear that the projects within the UN Reform programme are led by innovative and enthusiastic implementers, who are genuinely passionate about reform. Whilst Covid-19 hit at the end of FY19/20 and there were capacity issues in both programme and policy teams, due consideration must be given to how the programme documentation and reporting processes guarantee that projects contribute to Political Access and Influence (PAI) and Value for Money (VfM) objectives.
Outcome Score: C			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	N/A	N/A	N/A	N/A	N/A	A	C
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	N/A	N/A	Low	Medium
*Output/Outcome scores
How has the Programme changed during this period?			This was the first year of the UN Reform programme.

What support did the UK provide in FY 19/20?

Peace and Security Architecture Reform
1. Integrating Conventional Arms Control and Conflict Prevention: Funding contributed towards dedicated research aimed at better integrating conventional arms control and conflict prevention.
2. Support to Empower Resident Coordinator Offices (RCOs): Funding contributed towards supporting the RCO in Liberia. Whilst the proposal was to support a select number of RCOs, Liberia was the only RCO to submit a proposal that aligned with CSSF objectives.
3. Financing Peacekeeping Transitions: Funding contributed to the project “Principles for Development Finance to Support Transitions from Peacekeeping Missions”. This project aimed to help cultivate principles for development finance to mitigate against potential negative economic impacts of drawdown and the withdrawal of UN peacekeeping missions.

Development Reform
1. Action for Learning Conflict Analysis (ALCA): Funding contributed to a study into existing conflict analysis tools used by the UN Office for the Coordination of Humanitarian Affairs and its partners. The aim was to produce more practical training materials and to design a better-tailored training course for humanitarian practitioners in the field.
2. Independent System Wide Evaluations (ISWE): Funding contributed towards a secondee within the UN Transition team to undertake a review of UN development system capacity and to scope the feasibility of an Independent Evaluation Unit.
3. Humanitarian Development Peacebuilding & Partnership facility (HDPP): This Facility aims to provide advisory support and grant funding to UN Country Teams, helping them establish strategic and operational frameworks with partners across the humanitarian, development and peace nexus in crisis-affected situations. The aim is to enable UN operations to leverage partnership with the World Bank so as to increase impact on the ground.
Management Reform
1. Fleet Management & Common Premises, Business Innovation Group (BIG): Funding contributed to the UN Secretary General (SG) initiative to deliver business operations reforms that have a direct and positive effect on Country Office operations and large savings in providing logistical support.
2. Reform of UN Human Resource Procedures (One HR): This funding contributed to the SG’s initiative aimed at bringing UN agencies onto the UN’s One HR programme. The funding assisted expansion of the service lines of One HR to include a centralised recruitment portal for the UN system.
3. UN Transparency and Accountability ‘Data Cube’: This project aims to break down data siloes and improve data systems, bringing internal and external transparency to UN system-wide resources. This in turn aims to drive stronger UN accountability, coherence and impact. The project has three core elements: data strategy; dataset on UN system financial statistics; and a transparency portal.
4. Strengthening Good Governance at the Senior Leadership Level: Funding contributed to the UN Department of Operational Support’s delivery of an integrated capacity development package for UN senior leaders to exercise their delegated authority and to drive strong governance and resource stewardship in implementing mandates.

Summary of Recommendations for FY 2020/21

1. UN Reform Theory of Change (ToC) and Results Framework (RF): The UN Reform ToC and RF must be reviewed and rewritten to ensure that the indicators/milestones more closely align to the three pillars of UN Reform, and to link the project outputs to the programme outcomes.
2. Reform Pillar Stakeholder Board: The programme would benefit from a ‘Reform Pillar Stakeholder Board’ held at a suitable time within the UN reporting calendar, to allow implementers, policy leads and programme management to discuss the progress of projects and identify complementary work.
3. M&E tool for Political Access and Influence (PAI): The programme requires a mechanism for capturing PAI continuously over time, even if this is recorded through anecdotes and qualitative methods such as outcome harvesting.
4. Interoperability in UN Reform and wider MuSt Programme Portfolio: Projects within both the UN Reform programme and the wider MuSt portfolio should be reviewed to find opportunities to link individual UK-funded projects to help amplify their effect in the multilateral environment.
5. Virtual Communication Plan: Capitalising on the increased use of digital communications, a structured communication plan needs to be created to ensure the programme team, policy leads and implementers are consistently engaging, updating and identifying opportunities.
6. Quarterly Reviews: Quarterly Reviews need to be completed. Evaluation, oversight and scrutiny of the programme needs to inform the programme management board, challenge ToC assumptions, and identify constraints and opportunities.
7. Value for Money (VfM) Evaluation: The programme would benefit from a VfM evaluation, which would lead to a VfM framework. This would help to capture the ‘added value’ and positive effects that projects are producing and ensure greater transparency.
8. Policy Lead engagement: Throughout all the projects, it is clear that a more engaged policy lead will ensure that UK support to UN reform is understood through greater communication of the UK’s contributions and project successes. Advocacy would help ensure the UK’s contribution gains recognition within HMG and the UN.