Annual Review - Summary Sheet

PROGRAMME TITLE: Security Capacity Building CSSF Programme
Country and Region:	Multilateral Strategy - CSSF
IATI Unique ID:	CSSF-01-000004
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD)
Total Budget:	ODA: £5.8m			Non-ODA:£4.1m
Budget this FY	ODA: £1.9m			Non-ODA:£2m
Spend this FY	ODA: £1.7m			Non-ODA:£2.1m
Original Programme Start Date: April 2016		Planned End Date: 31 March 2021
Outputs					Score
NATO
Strategic Communications (NATO Voluntary National Contribution - VNC)					A
Strategic Communications - Western Balkans (NATO VNC)					B
Cyber (NATO VNCs)					A
Hybrid threats (NATO VNC, European Centre of Excellence)					A
Defence Capacity Building (NATO VNC)					A
CT (NATO VNC) - Not reviewed					N/A
China (NATO VNC)					A+
Counter Proliferation
IAEA Joint Comprehensive Plan of Action (JCPoA)					A
OSCE Conflict Prevention Centre, Small Arms & Light Weapons (SALW) and Stockpiles of Conventional Ammunition (SCA)
Organisation for the Prohibition of Chemical Weapons (OPCW)					A
World Health Organisation (WHO)					A
Countering Violent Extremism (CVE)
CVE OUTPUT 2 – UNDP					B
Strat Comms – Not reviewed					N/A
Counter-Terrorism OUTPUT 3 – UN Office of Counter Terrorism (secondment)					A
CVE OUTPUT - CommSec CVE Unit					A

Overall output score					A
Outcome Assessment:
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	Not Applicable	B	A	A	A	A	A	A
Risk Rating - low/medium/high		Medium	Medium	Medium	Medium	Medium	Medium	Medium
*output/outcome scores
How has the programme changed during this period?			Projects with the EU ended, and CVE/CT was added. There was a change of emphasis, namely by taking on JCPOA and OPCW work.

What support did the UK provide in FY 2019/20?
The Security Capacity Building (SCB) programme aims to develop the capacity and capability of multilaterals to respond to and counter growing threats in National Security Secretariat and Strategic Defence and Security Review priority areas, including hybrid threats, violent extremism, and chemical, biological and nuclear threats. The programme attempted to achieve these objectives through a mixture of secondments and funding, for example through support to the editorial process for the World Health Organisation as it updated its biological threats guidance.

Key results for FY 2019/20:
- First baseline assessment of China for NATO. NATO’s first ever China programme was then approved by all 29 Allies.
- The OPCW Investigation and Identification Team (IIT) report issued on 8 April 2020, citing reasonable grounds to believe the Syrian Air Force was responsible for three chemical weapons attacks in Ltamenah in March 2017.
- Creation of the NATO Trust Funds and extra-budgetary funds’ overarching guidance, which was approved by the North Atlantic Council in September 2019.
- Economic Community of West African States (ECOWAS): Roles and responsibilities for all national and regional chemical emergency functions have been clearly defined and linked to a national emergency response system and a regional response framework.
- Support to Trinidad and Tobago to create processes for managing the return, prosecution, rehabilitation and reintegration of terrorist fighters and their families.

Key Lessons
- Covid-19 limited the results achieved in quarter 4 of FY 2019/20 owing to international and in country travel constraints and activities being restricted.
- The Theory of Change articulates a strong logic for the programme, but the Results Framework does not reflect that maturity of thinking. Reporting is predominantly qualitative and does not seem to relate to the indicators or the milestones.
- Better coherence and coordination are required between the programme team, secondees, delivery partners, policy and mission teams.
- Specific guidance is needed on applying gender sensitivity principles in a multilateral environment with a security focus.

Summary of Recommendations for FY 2020/21
- The programme would benefit from clearer articulation of the strategic reasoning for each project, particularly for those involving secondees. These should be reviewed periodically. Reviews should also be conducted for those projects where the strategic fit is not clear.
- Support is needed on identifying gender sensitivity/equality opportunities for projects that are not already incorporating this (NATO, IAEA). Gender sensitivity guidance needs to be contextualised in a practical manner to give direction to secondees and policy leads. This could start with a high-level conversation to identify feasibility and potential opportunities before investing in expert advice.
- Secondees should be given policy sponsors in Whitehall, who are able both to provide up to date insights on HMG’s strategic priorities and use the information provided by the secondee. This point of contact needs to be sufficiently senior to provide a strategic view and to champion actionable insights from the secondee. The Programme teams should brief seniors on secondees’ roles.
- To improve role inductions, these should include background information on the multilateral’s structure, purpose and ways of working, clear duty of care responsibilities, options for training and career support, and a point of contact for support in the Embassy and Whitehall’s policy teams.
- Ensure future projects have a conscious consideration of the balance between political and technical content.