Annual Review - Summary Sheet

PROGRAMME TITLE: Organised Immigration Crime Taskforce (Project INVIGOR)
Country and Region:	UK, Europe, Africa (North, West and East), Turkey
IATI Unique ID:	CSSF-01-000007
HMG Partners / (LEAD in bold)	National Crime Agency (NCA), Home Office (HO), Crown Prosecution Service (CPS), Immigration Enforcement (IE), Immigration Enforcement International (IEI), Border Force (BF)
Total Budget:	ODA:			Non-ODA:
Budget this FY	ODA: £4.5m			Non-ODA:£10m
Spend this FY	ODA: £3.8m			Non-ODA: £9.5m
Original Programme Start Date: June 2015		Planned End Date: March 2021
Outputs					Score
UK1: Intelligence Collection					U
UK2: Intelligence Analysis					U
UK3: Social Research and Campaigning					B
UK4: Cross-Agency Learning, dissemination of best practice, harnessing innovation					B
UK5: Provide niche and specialist capability					A+
UK6: Mechanisms for cooperation and coordination set up					A+
OP1: Build Technical Capability					A
OP2: Build Investigation Skills					A
OP3: Build Command and Control Capacity					A
OP4: Provide Interpreters support to operations					A
OP5: Provide guidance and support to prosecutors and investigators					A
OP6: Build, maintain and leverage our relationships with key host institutions					A
OP7: Raise awareness and capacity on Organised Immigration Crime and promote legislative changes					A
OP8: Encourage and facilitate cooperation with or between partner countries and Private					A
OP9: Promote the UK approach and best practice, influence other countries doctrinal approach					A
Overall output score					A
Outcome Assessment: / The review found positive evidence that the programme is on course to meet the following intended outcomes: / Initiate, lead or support successful investigations in the UK and overseas, resulting in more prosecutions and convictions of criminals involved in organised immigration crime (OIC). / Develop, expand and sustain capability and capacity in host countries to exploit intelligence, enabling the initiation of operations against OIC actors. / Influence, build political will and mobilise host governments to take action against the OIC and Modern Slavery and Human Trafficking (MSHT) threat
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	A	A	U	U	U	A	A
Risk Rating -low/medium/high							Medium
*output/outcome scores
How has the programme changed during this period?			The programme has seen a significant change over this reporting year. Programme management has been improved through a strengthened Theory of Change and Results Framework.

What support did the UK provide in FY 19/20?
The Organised Immigration Crime (OIC) Taskforce provides staff to improve the capability of source and transit countries to tackle OIC; develop and enrich the intelligence picture of the threat of OIC; identify and investigate those involved; disrupt the use of enablers by organised criminals in facilitating OIC; and identify and recover illicit finances. This support is delivered through a combination of mentoring within partner countries, conducting joint operations in source and transit countries, providing training and facilitating the flow of information (between both UK agencies and the UK and partner agencies) relating to the OIC threat, debriefing migrants and offering criminal justice (including prosecutorial) assistance.

Key results for FY 19/20:

Targeted use of intelligence and services of the Research, Information and Communications Unit (RICU) and Europol to identify and disrupt actors using the internet to offer migration services.

The programme strengthened the response to the threat from small boats crossing the English Channel with migrants, by redeploying resources and developing joint working with France. This demonstrated the programme’s ability to work in an agile way close to the UK, responding to a clearly defined threat.

1. Provision of specialist capability to overseas partners, including training of investigators.
2. Activity in support of Operation Melrose following up the death of 39 Vietnamese nationals in Thurrock.

Key Lessons

Recruitment and Agility
The programme requires a workforce model that is as flexible and skilled as possible, and operational partners work hard to recruit and retain staff in overseas posts. This remains challenging given the specialist area of work, training, security and other recruitment tensions. There are gaps in the programme-wide tracking of posts which may lead to finance control failures in the future if not corrected.

The programme can respond rapidly to new threats and there is some good evidence of NCA and CPS overseas posts being re-deployed into other areas to support activity. However, the delivery of changes can take quite some time to enact. A more sustained funding commitment and work to develop a different recruitment model for taskforce posts may well help alleviate some of the challenges.

Communication and Learning
In a changing landscape brought by COVID 19, more robust communication methods or platforms may be needed. Developing a single INVIGOR knowledge-sharing and conferencing facility will significantly help the Taskforce to remain connected. This will also improve the sharing and learning that can be afforded through the programme. It is evident that effective learning and sharing is taking place within each of the operational partner organisations. However, cross-agency learning within the programme as a whole, is less evident.

Summary of Recommendations for FY 20/21
- Continued development of a more detailed Theory of Change
- Continued development of the Results Framework and indicators
- Develop the assessment and response to conflict sensitivity and gender equality.
- Implement learning from the Financial Management review of 19/20
- Review the recruitment models used to fill posts within the taskforce to identify how this may be impeding the agility of the programme. The review should consider recommendations to help improve recruitment into Taskforce posts
- Improve Governance and Programme Support
- Ensure that the Programme Board has sufficient engagement with/from operational partners and the right reporting lines into the other connected boards
- Develop communications internally within the INVIGOR team to share learning and update on activity
- Enhance the activity in Prevent, such as pro-active messaging campaigns as identified within the RICU paper.