Annual Review - Summary Sheet

PROGRAMME TITLE: Multilateral Strategy Peacekeeping CSSF Programme
Country and Region:	CSSF Multilateral Strategy (MuSt)
IATI Unique ID:	CSSF-01-000003
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD), Stabilisation Unit
Total Budget:	ODA: £10.85m			Non-ODA: £8.2m
Budget this FY	ODA: £1.5m			Non-ODA: £2.1m
Spend this FY	ODA: £1m			Non-ODA: £1.45m
Original Programme Start Date: April 2016		Planned End Date: Mar 2021
Outputs					Score
1.1 STRATEGIC PLANNING AND IMPLEMENTATION: Improve integrated strategic planning through operational support					B
1.2 DEPARTMENT OF PEACE OPERATIONS (DPO) FUNDING COORDINATION: Strengthened UN planning capabilities for UN missions delivered through greater value for money.					A
1.3 STAFFING PRINCIPLES AND PARAMETERS: Strengthened UN planning capabilities for UN missions.					A+
1.4 PRIORITISATION AND SEQUENCING OF ACTIVITIES: A study of prioritisation and sequencing of peacekeeping mandates in the past, identifying patterns, good practices and lessons to be drawn to inform strategic-level planning and analysis.					B
2.1 PLEDGES: Current and emerging capability requirements are identified and disseminated					B
3.1 DEPLOYMENTS: Demonstratable contribution of UK expertise to the performance of pre-deployment training and field missions.					A
3.2 TRAINING: All newly appointed sector commanders and Head of Mission commanders trained on Intensive Orientation Courses.					B
4.1 PEACEKEEPING INTELLIGENCE POLICY: Situational awareness in relevant Peacekeeping Operations (PKOs) is significantly enhanced through functioning intelligence systems.					B
6.1 ENHANCING PROTECTION OF CIVILIANS (POC) MANDATE: Selected field offices have a structured plan to engage communities to address local conflicts and POC threats (Civil Affairs).					B
6.2 LOCAL CONFLICT DYNAMICS: UN Guidance on PKOs response to operating in complex environments produced, strengthening operational response.					B
7.1 ANALYTICS TOOLKIT: Analysis and mandate implementation is improved through enhanced evidence-driven processes and strengthening of key data tools and methodologies.					A+
7.2 COMPREHENSIVE PERFORMANCE ASSESSMENT SYSTEM: designed to assess the effectiveness of a mission’s performance and utilizes an information technology platform by tracking and storing data on performance activities in a database.					B
7.3 MILITARY CAPABILITY STUDY: assess the suitability and utilisation of the capabilities for the Mandated objectives, tasks, phasing and most importantly the threat environment.					A
Overall output score					B
Outcome Assessment: / The system by which projects are identified and selected is working. They are framed and delivering in line with the 3Ps (Planning, Performance and Pledges), and there is clear evidence that projects complement each other. But this is not reflected nor reported in a way that demonstrates their contribution to stated Outcomes. However, as reflected in the reccomendations going forward, the envisaged Outcomes for the Peacekeeping Programme and its current Theory of Change (ToC) do not currently reflect the practical contribution that the outputs are making. The programme can better capture and articulate the cumulative effect of the projects and their outputs, which are significant. The programme combines projects to enable systemic change within the UN, as well as tactical level approaches and there is evidence that these are better linked and informed.
Outcome Score: B			Risk: Low

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	B	A	B	A	A	B	B
Risk Rating - low/medium/high	Low	Low	Low	Low	Low	Low	Low	Low
*output/outcome scores
How has the programme changed during this period?			In 2019/20, funding for projects related to comms and leadership was redistributed to planning projects.

What support did the UK provide in FY 2019/20?
The Peacekeeping Programme has provided support to projects in its three priority areas for Peacekeeping reform that are key to modernising UN peacekeeping operations, namely Planning, Pledges and Performance (3Ps), to military staff officer deployments and to police support.

Key results for FY 2019/20
- Missions using the Comprehensive Performance Assessment System are showing evidence of strengthened integrated planning with field offices, and mission resource allocation bodies can make more informed decisions.
- Through the UN Organisation Stabilisation Mission in the Democratic Republic of Congo (MONUSCO) Military Capability Study (MCS) and implementation strategy a ‘military concept of operations in a context of transition and exit was developed’, leading to the revision of several guidance documents.
- Support for implementation of the UN’s Peacekeeping Intelligence Policy, which helps peacekeeping missions have greater situational awareness.
- Instigation of an improved command and control structure for specific peacekeeping missions, which has leveraged analysis and planning expertise from within the mission to strengthen linkages between threat analysis and operational decision-making.
- Improvement in missions’ understanding of local conflict dynamics, in mapping of stakeholders and in prioritising interventions. Studies highlighted the need to understand contextual challenges and advantages in managing local conflict dynamics, often with individual mission complexities.
- The Strategic Force Generation Cell (SFGC) continued to improve evaluation of military units and new processes to facilitate feedback to troop and police contributing countries (T/PCCs) including identifying ways to improve performance.
- Enhanced understanding within the SFGC of the readiness and preparedness of Member States’ capabilities pledged to UN Peacekeeping, enabling a more informed selection of units for deployment and better performance once deployed.

Summary of Recommendations for FY 2020/21
- Theory of Change (ToC) / Results Framework (RF). The ToC and Results Framework (RF) for the Peacekeeping programme require significant work. The Programme Team and the Portfolio Team should consider a thorough review of the way the team seeks to achieve programme objectives.
- Project identification/sifting. The mechanism for sifting projects is working well and in line with the 3Ps. Project identification and sifting would benefit from a Standing Operating Procedure.
- UK Added Value. There is clear evidence that UK embeds and deployed personnel are making critical contributions. The programme should look to capture case studies and impact of deployments.
- Police. Systemic issues prevent the UK from doing what it set out to do through police deployments. Work is in hand to review this activity. Consideration should be given to deploying where risks are lower, to maintain UK influence and build experience for future HQ deployments.
- Reporting. It is recommended that a quarterly ‘harvest’ is conducted by the programme team or
an external actor to assure the reporting. This would capture additional value or case studies of the UK’s contribution, beyond that which is captured in the RF.
- Deployed personnel – Pre-Briefing. UK-funded projects that enhance planning and performance are highlighted in briefings of those being deployed. This practice will be formalised by including the programme manager at the pre-brief.
- Value for Money assessment. This needs to capture project efficiencies and put in place a value for money framework so that a new Evaluability Study can be implemented.
- MOD connectivity/linkage. Whilst working with embedded MOD staff within the Peacekeeping Joint Unit ensures cross-pollination, it is strongly recommended that this connectivity is captured and evidence gathered on wider benefits. This would potentially support Political Access and Influence work within the Evaluability Study.