Annual Review - Summary Sheet

PROGRAMME TITLE: Reintegration and Support for Returnees Programme
Country and Region:	Afghanistan, Pakistan
IATI Unique ID:	CSSF-01-000005
HMG Partners / (LEAD in bold)	Home Office (HO), Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £7m			Non-ODA: £0m
Budget this FY	ODA: £1.16m			Non-ODA: £0m
Spend this FY	ODA: £0.46m			Non-ODA: £0m
Original Programme Start Date: April 2017		Planned End Date: March 2021
Outputs					Score
Individuals returning from UK to Afghanistan and Pakistan are provided with post arrival and long-term sustainable reintegration assistance.					A
Overall output score					A
Outcome Assessment:
Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	Amber/Red – / Outputs moderately did not meet expectation	B	B	B	B	A	A
Risk Rating - low/medium/high	N/A	High	Medium	Medium	Medium	Medium	High	High
*output/outcome scores
How has the programme changed during this period?			The programme is now geographically focussed, providing sustainable reintegration support to returnees from the UK. Two pilot projects are established and are ready for alignment with the Home Office’s overall returns effort, moving away from CSSF funding.

What support did the UK provide in FY 19/20?
In 2019/20 the programme comprised of two pilot projects. Both provided post-arrival and long-term sustainable reintegration assistance to individuals returning from the UK to Afghanistan and Pakistan. Reintegration activities included job placement or creation, education and training, accommodation and referral to relevant local organisations and amenities.

Key results for FY 19/20:
- Together, the projects assisted approximately 60 individuals. This number was lower than foreseen due to delays in the selection and contracting of an implementing partner in Pakistan.
- The programme demonstrated that ODA-eligible, sustainable reintegration can be delivered overseas by intergovernmental, not-for-profit, and commercial partners. This work should now be integrated within HMG’s overall approach to returns, led by the Home Office.

Key Lessons
- Regular and detailed engagement with implementers in country played a key role in developing and improving the service provided to returnees.
- Reintegration is an important part of the UK’s wider returns effort, and to achieve good results and ensure value for money, these pilots should be integrated within HMG’s overall approach to returns, led by the Home Office.

Summary of Recommendations for FY 20/21
- Reintegration is an important part of the UK’s wider returns effort, and to achieve good results and ensure value for money, should be integrated in future years within HMG’s overall approach to returns, led by the Home Office.
- Project leads in country should maintain regular engagement with implementing partners, making clear the level of service required and encouraging innovation in service delivery methods.
- Covid-19 will continue to have a severe impact on the UK’s ability to make returns, so project leads should have regular honest conversations with implementers and look to save costs where project activity is likely to be limited.
- The programme should define its risk appetite as part of its wider risk management approach.
- Consideration should be given to awarding multi-year contracts in future, where implementers have proved their competence and there is a strong value for money case.
- When regular returns re-start, project leads should make use of tailored and independent monitoring and evaluation to give greater confidence in the success of the reintegration being delivered.