Annual Review - Summary Sheet

PROGRAMME TITLE: Upstream Programme
Country and Region:	Africa- Eritrea, Niger and Nigeria
IATI Unique ID:	CSSF-01-000018
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Home Office (HO)
Total Budget :	ODA: £9.05 million			Non-ODA: £0
Budget this FY	ODA: £0.95m			Non-ODA: £0
Spend this FY	ODA: £0.92m			Non-ODA: £0
Original Programme Start Date: 1 April 2017		Planned End Date: 31 March 2022
Outputs					Score
Border Management Information Niger and Nigeria					A
Capacity building on human trafficking in Eritrea					B
Overall output score					A
Outcome Assessment: The Collaboration Against Trafficking and Smuggling between Niger and Nigeria (CATS NN) Programme began in FY19/20 as part of the wider Upstream programme which began in 2017. It aims to achieve better border management capabilities in Niger and Nigeria. This review captured the very early stages of Phase 1 of the programme and the outputs are in line with current expectations. The longer-term outcomes are anticipated to be delivered later in the programme, during Phase 2. For example, work on joint investigations cannot begin until Phase 1 fully establishes the appropriate technical platform – the Migration and Immigration Data Analysis System (MIDAS) through which data will be shared. / Agreement of new domestic legislation and regulations to enable the countries to share information as envisaged has been slower than originally envisaged. The existing timeframe of the programme may need to be amended. Mitigations are in place for the programme implementer, International Organisation for Migration (IOM) to accelerate work on the regulatory frameworks, by exploiting the positive political will that exists in both countries at present. In the meantime, the Economic Community of West African States (ECOWAS) data protection laws provide an indicative framework. HMG is engaging with key stakeholders, who remain enthusiastic about delivery and are confident that the system remains fully achievable. / The review was asked to focus on CATS NN as the project in Eritrea was ending. The main reason for the B scoring was due to the difficult operating environment, low beneficiary engagement due to Covid challenges and a lack of permanent presence of the implementing partner in country.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score			A	C	B	B	A	B
Risk Rating - low/medium/high			High	High	Med	Med	Med	Med
*output/outcome scores
How has the programme changed during this period?			The Strategic Communications strand ended in 2019/20. There was a move towards a more evidence-based approach with CATS NN Programme, ensuring wider collaboration between HMG actors and regional posts.

What support did the UK provide in FY 19/20?
- In January 2018, HMG and the French Government agreed to work in partnership on migration issues, including by addressing human trafficking and smuggling concerns in upstream countries. These are countries which are the source of large numbers of illegal migrants who end up at European borders including between the UK and France. The CATS NN Programme is an example of an Anglo-French partnership on upstream migration in the border area of Niger, where France has greater reach and Nigeria, where the UK has significant national interest.
- Unsafe and illegal migration puts lives at risk, while transnational criminal and non-state armed groups take advantage of weak border controls and infrastructures. CATS NN is a key component of HMG efforts tackling unsafe and illegal migration. It also helps to strengthen regional security and stability. Enabling Nigerien and Nigerian authorities to better collect and manage border crossing information fosters cooperation, improving border management and counter-trafficking efforts along their shared border. This will directly impact on the main migrant and trafficking route from Nigeria via the Mediterranean and on to the EU and UK.
- CATS NN complements DFID’s £75m Safety, Support and Solution Phase II (SSSII) programme that provides immediate protection and humanitarian assistance to migrants moving through the Sahel. CATS NN will provide added value by protecting migrants from the risks of trafficking and smuggling at key points along this route. It adopts a multi-pronged strategy, strengthening the capacity of Nigerien and Nigerian authorities to detect victims and criminals and engaging border communities to address factors that facilitate and support criminal activities.
2019-20 was the first year of the CATS NN programme. Activities (relating to one output) only commenced in October 2019 and mainly comprise assessments. The UN Office on Drugs and Crime (UNODC) in Eritrea, focussed on building Eritrean capacity to tackle trafficking in persons and smuggling of migrants. This was in line with international standards, delivered through technical assistance and training. The project ended in March 2020.
The CATS NN programme will assist Nigerian and Nigerien authorities to build robust border management procedures through new technology, training and increased collaboration, benefitting security and stability in the region. It will also assist the victims of people trafficking and smuggling in the region, helping to better integrate development and security work in West Africa.

Key results for FY 19/20:
- The planning phase for the three Nigerien border posts to be rehabilitated were completed through successful identification of the posts by Direction de la Surveillance du Territoire (DST). These were considered to be the most strategic and confirmed by an assessment of the locations by surveyors and MIDAS technicians. Rehabilitation plans were completed and included construction of dedicated female accommodation and detention cells.
- The Nigerien Ministry of Interior established an Ad Hoc Monitoring Committee on Institutional and Legal Data Management as a national focal point on information sharing and data management. The Committee will monitor the implementation of new data management arrangements at the borders. The creation of this oversight committee will ensure that data collected by Niger will be done in accordance with international standards and norms, making the sharing data across borders simpler and more secure.
- In Niger, the country’s first legal provision on protection of personal data was validated by the Nigerien High Authority for Personal Data Protection (HAPDP). Formalising data protection legal frameworks provides confidence to the Nigerian side that Niger will handle personal and sensitive data appropriately and is key to the success of the collaboration envisaged.
- Thirty Nigeria Immigration Service (NIS) officers were trained to use and maintain the MIDAS system. This training will ensure that NIS officers collect and record data in accordance with international standards, making it fit for sharing with counterparts in Niger and beyond. The training of trainers will ensure that MIDAS training is sustainable beyond the lifetime of the programme.
- CSSF Gender and Conflict Sensitivity Training in Abuja was attended by senior representatives of key Nigerien and Nigerian border agencies. The knowledge acquired by the main recipient agencies under CATS NN will help ensure that they operate in a way which is more gender inclusive, particularly given their historical and cultural difficulties in posting female officers to the border zone.
- In Eritrea a training course on illicit financial flows relating to trafficking in persons was attended by the Minister of Justice, who requested further training for banks to ensure sustainability. Basic IT equipment was also provided to enhance facilities at the Eritrean Police Force Training Centre.

Key Lessons
Conflict Sensitivity and Gender training helped raise awareness among beneficiaries, programme staff, implementers and achieve a common understanding of important issues and risks at an early stage of CATS NN. This is worth repeating as implementation progresses. Programme leads learned from recipients of the difficulties they have in posting female officers to the border zone, which in turn helps understand and better focus related Gender issues with senior leadership of DST and NIS.
Staying engaged with the Government of Eritrea helped HMG and UNODC build trust and facilitated a new UNODC partnership agreement and longer-term follow-on EU programme. No other organisations or donors were able to deliver any activity focused on migration capacity building in Eritrea in 2019/20.

Summary of Recommendations for FY 20/21
- The theory of change should be refreshed to ensure that each activity, output and outcome contributes to the delivery of the planned impact in a logical way, and that delivery of a framework for data sharing between Niger and Nigeria is realistic within the current life span of the programme.
- Both DST and NIS have difficulty posting female officers to the border zone due to cultural, religious and societal reasons. This has operational consequences on the ground making it more difficult to identify female victims of trafficking whilst treating them in a gender sensitive and culturally appropriate way. The Programme should leverage the training provided, the provision of female quarters and sanitation facilities at the rehabilitated border command posts, and existing relationships to attempt to address this gap. Although gender is not the main purpose of CATS NN programme, it should ensure efforts go beyond female participation in training activities and seize every opportunity to enhance the role of women in both the DST and NIS.