Annual Review - Summary Sheet

PROGRAMME TITLE: National Security Communications Team
Country and Region:	United Kingdom (EMEA)
IATI Unique ID:	CSSF-01-000021
HMG Partners / (LEAD in bold)	Cabinet Office (CO), Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD), Home Office (HO), Department for Digital, Culture, Media and Sport (DCMS)
Total Budget :	ODA: £0			Non-ODA: £2,625,000
Budget this FY	ODA: £0			Non-ODA: £2,625,000
Spend this FY	ODA: £0			Non-ODA: £2,614,262
Original Programme Start Date: April 2018/19		Planned End Date: Ongoing
Outputs					Score
Countering Hybrid Threats (CHT) strand results framework did not include output statements or indicators; therefore, it is not possible to provide a formal output score. However, there was evidence of output delivery, which contributed to certain outcomes being achieved.					C
Overall output score					C
Outcome Assessment: Both work strands evidenced clear progress and successes in elements of their work. However, whilst a Theory of Change and Results Framework were developed, these were not consistently used throughout the year, meaning it is unclear how the programme outcomes link to desired impact or outputs (there were no outputs recorded in the Results Framework). As such the programme cannot be scored any higher than a C.
Outcome Score: C			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score							C	C
Risk Rating - low/medium/high							Medium
*output/outcome scores
How has the programme changed during this period?			This is the first year the NSCT programme has had a formal Annual Review. In 2018/19, a rapid review was completed which did not have a mark associated with it.

Summary of Programme
The National Security Communications (NSCT) CSSF programme was created following recommendations in the 2018 National Security Capability Review to develop the UK’s ability to deliver strategic communications in the national security sphere. The 2019/20 programme document describes NSCT as working with national security departments across Whitehall, continuously delivering a challenging programme of strategic communications, that aims to deliver significant impact for UK national security interests.

The priorities for NSCT in FY 2019/20 were: Countering Hybrid Threats (CHT), Serious Organised Crime, Insights, Capability Building. Given the variety of priorities this generated a large number of outcomes. Given Annual Review time constraints it would not have been possible to review each outcome, therefore the Annual Review focused on CHT. These two priorities were chosen to review as they had the largest budget allocation and work has continued in these areas in FY 2020/21.

What support did NSCT provide in FY 2019/20?

Countering Hybrid Threats (CHT) Workstrand
The CHT strand spent £749,000 on:
- £500,000 to continue its existing successful countering disinformation work.
- £250,000 to explore pilot activity through innovative means to increase UK public resilience to hybrid threats.

This broke down into the following projects:
- £442,000 Don’t Feed the Beast’ Disinformation Campaign – with an additional £25,000 provided for a COVID-19 campaign.
- £200,000 Tracking disinformation in foreign languages (Hindi, Punjabi and Polish).
- £70,000 Develop online RESIST toolkit.
- £9,000 Defending Elections guide and Deterrence Communications training manual
- £3,000 Joint partnership with Swedish government to deliver against four work streams: election guidance, communications war game, information sharing and secondments.

Key results for FY 2019/20:

CHT
- The team has done well to deliver a prioritised set of activities given the significant challenges they faced throughout the year. This includes the movement of policy responsibility from the Cabinet Office to the Department for Culture, Media and Sport (DCMS), the fact that policy objectives were being developed during the delivery phase of the programme and the impact of COVID-19 on resources.
- The team has consistently added value to the delivery of the CHT strand including using communications expertise to assess creative aspects of campaigns, review costs and ensure that suggested timelines were realistic.
- The CHT team has taken steps to improve their approach to financial management and monitoring and evaluation. This year saw the development of a results framework for the strand.
- The ‘Don’t Feed the Beast’ campaign stands out for its success in increasing understanding of hybrid threats to the UK (specifically disinformation) and adoption of resilient behaviours in 18–35-year-olds.
- The programme flexed to accommodate new challenges in the CHT space, including approving new campaign activity to counter disinformation amongst a broader audience group, to respond to the risk of disinformation narratives around COVID-19.
- The programme funded Digital RESIST training in development to improve domestic capability. This training has now been rolled out as part of Government Communications Service (GCS) core training, thereby contributing to the programme’s objective of building the capability of an HMG national security communicators’ cadre.

Key Lessons
- Monitoring and Evaluation (M&E) needs to be improved across the programme. Whilst some metrics evidenced impressive outcomes, as there was no consistent M&E, it was difficult to accurately measure the success of these work strands. Credit may not have been given where it was deserved, and the programme cannot be scored any higher than a C because of this.
- A system of logging and monitoring output is required in order to evidence activity and progress.
- More rigour is required around key decision making. Without a properly documented process, it is difficult to assign responsibility or accurately reflect on progress/lessons learned.

Summary of Recommendations for FY 2020/21
- Conduct a rapid review of the programme Theory of Change and Results Framework, making sure it accurately reflects what the programme is trying to change, and the outcomes/outputs/indicators required to be achieved to enable that change. Using an M&E advisor for this is highly recommended.
- Assess and realign the team’s focus around fewer priorities and explicitly link these to the newly developed Theory of Change.
- Develop a governance structure that includes key programme and policy individuals. The aim of this is to inform and document key decision making, recognising synergies at a programme level, whilst enabling workstream leads to consistently ensure workstream objectives link to the wider programme outcomes.