Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Ascension Island Programme
Country and Region:	Saint Helena, Ascension and Tristan da Cunha, South Atlantic Ocean
IATI Unique ID:	CSSF-07-000006
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £0.00m			Non-ODA: £5.00m for the lifetime of the programme.
Budget This FY[1]:	ODA: £0.00m			Non-ODA: £1.85m
Spend This FY[2]:	ODA: £0.00m			Non-ODA: £1.76m
Original Programme Start Date: March 2018		End Date: March 2020
Outputs					Score
1. Prioritised Critical Island Infrastructure (CII) is assessed for need and subsequent planning for investment over next five years. Plan is created and signed off by Ascension Island Government (AIG) and CSSF Programme Board.					B
2. Identified CII projects with HMG funding to be delivered and projects are complementary to the AIG CII delivery and maintenance plan					A
3. Increased capacity and resilience across the Territory with increased ability for Ascension Island Government to deliver improvement using local resources.					B
4. Provision of infrastructure and fixed assets planning and support for AIG. Produce long-term recovery and maintenance strategy.					A
Overall output score					A
Outcome Assessment: / The programme has delivered key upgrades and investment to Ascension Island’s critical infrastructure improvements and supported AIG in delivery and long-term planning to address management of these assets in the long term. The ambitious programme did not complete its initial plan of projects, although it adapted and addressed several major risks to life and risks to operations projects, despite delays and uncertainties. For the programme to have maximum impact, long term planning and clarity on future funding and the outcome of the Future of Ascension Review is required.
Final Outcome Score: A			Risk: Medium
[1] FY 19/20
[2] FY 19/20

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19*		2019/20*
Programme Score	N/A	N/A	N/A	A	A	A	A
Risk Rating - low/medium/high	N/A	N/A	N/A	Medium	Medium	Medium	Medium
*Output/outcome scores

What support did the UK provide?
The programme provided funding for the second year of critical island infrastructure projects to reduce the risk of single points of failure and risk to life from existing infrastructure and equipment unfit for purpose. A Project Manager (PM) post within AIG was funded by the UK; this person arrived on Ascension in February 2019, at the end of the programme’s first year. The PM role led on planning, delivery, and implementation of projects under the programme and was responsible for financial management, contracting, and supplier relationships to ensure the programme remained effective and efficient. Finally, the programme provided support for implementing the actions and recommendations of the previous Annual Review.

What results did the programme deliver? Will they be sustained?
In financial year 19/20, the main activities undertaken included: marine infrastructure works, installation of corrosion control shelters, procurement of equipment including a forklift, rewiring materials, pier head refurbishment, asset management tool development, a hospital feasibility study and property review surveys. These activities have addressed Ascension Island’s critical infrastructure improvements and supported AIG in the discharge of its responsibilities. A significant percentage of the necessary work remains to be undertaken, however.

The asset management system has been populated; further detail from recent works (condition surveys) will make it even more effective. Further work on long term planning is required to ensure the effects of the project are sustained. This will provide AIG and FCO with a better sense of the pipeline of critical activity.

Finally, management of the programme on Ascension has been improved through the appointment of an AIG Project Manager at the end of the first year. This post holder remains on Ascension for work beyond the initial two-year programme.

What lessons have been learned?
- The need to focus on project aspects (such as procurement of equipment) at early stages of the financial year, to ensure complicated purchases can be completed within the year and is more resilient to unforeseen delays. Access remains an issue, which can only be mitigated by advance planning and supply chain monitoring. Providing specific capability (or funding to do so) should be considered in order to maximise funding to critical local need.
- Having a dedicated resource on island and involvement of all major stakeholders throughout the programme has proved successful, in particular when stakeholders have a shared interest or need that will be affected by a specific element of the programme.
- The need to prioritise critical projects and determine what can be achieved within the allocated timescale and within the limitations of the programme and its funding. The need to understand how other related projects (such as the Future of Ascension Review) will affect those prioritised projects.

Note: At its inception, this programme was given a set budget for a two-year period. This programme Completion Review marks the formal end of that period. However, as a substantial amount of work remained to be done on the territory, additional funding was found to continue the programme beyond March 2020.