Annual Review - Summary Sheet

PROGRAMME TITLE: Anguilla Programme (AP)
Country and Region:	Anguilla, Caribbean, UK Overseas Territories (OTs)
IATI Unique ID:	CSSF-07-000005
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £0.00m			Non-ODA: £60.00m
Budget this FY:	ODA: £0.00m			Non-ODA: £15.38m
Spend this FY:	ODA: £0.00m			Non-ODA: £15.67m
Original Programme Start Date: April 2018		Planned End Date: March 2023
Outputs					Score
Education infrastructure restored to pre-Irma level and built back better.					B
Health facilities restored to pre-Irma levels of functionality but with greater hurricane resilience.					A
The majority of Government of Anguilla (GoA) officials to be in appropriate, safe and hurricane resilient accommodation realising financial savings by co-locating and reducing of amount of rented accommodation.					A
Prioritised elements of National Infrastructure returned to full functionality but built back stronger.					B
IT systems underpinning revenue strengthening.					B
Overall output score					B
Outcome Assessment: / The programme had a very good 19/20 responding to the lessons learned from the conceptual stage, increasing capacity and creating a platform for sustained delivery across the remaining years of the programme. Governance arrangements between the key entities (GoA, FCO and consultants WYG) were reviewed and improved. Although delays were encountered, and timelines in some cases had to be extended, these were not in themselves events that would be unexpected in a major infrastructure programme, particularly in an environment where there has been little investment in infrastructure over the last few years. Beneficiaries were unanimous in their praise for the progress made in the year.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	N/A	N/A	N/A	B	B	B	B
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	High	High	Medium	Medium
*output/outcome scores
How has the programme changed during this period?			The programme has almost entirely moved from concept and design stage, through commercial tendering, into construction. Some projects have been completed entirely within year, one remains to be tendered.

What support did the UK provide in FY 19/20?

The UK has provided funding for a range of projects focused on rebuilding Anguilla’s critical national infrastructure, with enhanced resilience to hurricanes, as an enabler for progress towards sustainable economic development and self-sufficiency. Aside from providing the capital funding for the programme, the UK has provided additional advice covering governance, deliverability, procurement, legal advice, project management best practice, monitoring and evaluation, and financial management. This annual review does not include additional HMG support provided to Anguilla in the immediate aftermath of Hurricane Irma.

Key results for FY 19/20:

All but one project strand progressed to construction stage of the project lifecycle with significant construction beginning within the financial year. The programme developed better understanding of roles and responsibilities across three delivery entities: GoA, Governor’s Office and the technical advisers.

Education
The Vivian Vanterpool primary school project was completed, and construction began on Orealia Kelly, Adrian T Hazell, Morris Vanterpool and Valley primary schools. For the secondary school project, the programme completed renovation of the existing Campus B, signed off a business case for the site option for the new secondary school, and began phase one of construction.

Health
The programme procured an ambulance, mobile dental and oxygen generator units, incinerator and dialysis pumps for the hospital. Construction of the hospital boundary wall was completed and work on roof extensions and storage units have progressed well. The procurement of the Health Authority’s IT system was also completed and work on Phase 1 implementation started.

Access
The Combined (Fire and Air Traffic Control) Services Building was completed and is in use.

Revenue Strengthening (Taxation and Land Registry systems)
The programme procured IT systems integral to the revenue strengthening projects and wider public financial management reforms - implementation of these projects is on track.

Key Lessons:

- Earlier confirmation of HMG agreement to extend this programme would have allowed more accurate forecasting of future spend and programme scheduling.
- HMG prepayment rules on the CSSF do not facilitate multiyear infrastructure programmes.
- To prevent future delays, it will be necessary to clearly articulate the differing ways of working, construction standards between the stakeholders and the differentiation between on island and UK support.
- Early and consistent communication with key stakeholders, both delivery partners and beneficiaries, is necessary, particularly where scope reduction decisions are needed.
- Innovative contracting strategies and communication with contractors have mitigated their attempts to add premiums to the projects, due to their perceived risk associated with utilising an unfamiliar contracting process (labour and materials as opposed to just labour), to deliver the largest publicly funded infrastructure programme in Anguilla’s history.

Summary of Recommendations for FY 20/21

- Appreciation of local contractor capability, contract structure and inflationary effects of significant concurrent projects on island construction should be factored into future projects and programmes.
- Continue to update and revise the results framework as appropriate.
- All prepayment exercises (which are necessary to mobilise contractors on such programmes) to be scrutinised and agreed with both the Joint Funds Unit and central finance.
- To support the value for money (VfM) of the programme, timeframes should continue to be reviewed and revised where necessary. The programme needs timelines that deliver benefits to recipients in a timely manner, but do not compromise VfM and quality.
- Continue to monitor deferred project elements that could be restarted.
- Seek further funding for the renewable energy aspects of the building projects, which will not be possible to complete within the current programme envelope and are outside of the current remit.
- Phase 4b Technical Block of the Secondary School is the priority. This is rolled over from the previous annual review. Work has been undertaken to address this, but it should remain as further projects complete.
- To consider the governance arrangements for any successor programmes that may be approved for Anguilla, where the Governor’s Office and SRO have reduced leverage between client (GoA) and contractor.
- To begin a dedicated “lessons learned” exercise to capture the key issues in year – to inform the FCO and wider CSSF – given the atypical nature of the Anguilla Programme.
- Seek written commitment from the GoA that it will identify a small recurrent capital budget following the completion of the programme, to support aspects of the whole-life cost of the assets procured or built by the programme.
- Continue to press GoA to fulfil their obligations on reporting and maintenance established under the terms of the Memorandum of Understanding.