Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Justice, Security and Governance
Country and Region:	UK Overseas Territories (OTs)
IATI Unique ID:	CSSF-07-000004
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), National Crime Agency (NCA), Ministry of Defence (MOD), Home Office (HO), Crown Prosecution Service (CPS), Government Partnerships International (GPI), Commonwealth Parliamentary Association (CPA), Department of Health and Social Care (DHSC), Public Health England (PHE)
Total Budget:	ODA: £2.77m			Non-ODA: £20.32m
Budget this FY:[1]	ODA: £1.64m			Non-ODA: £9.29m
Spend This FY:[2]	ODA: £1.12m			Non-ODA: £6.94m
Original Programme Start Date: April 2018		End Date: March 2020
Outputs					Score
1.1 OT Security & Justice actors are supported to increase capacity, capability and competency.					B
1.2 Inter-agency collaboration to address crime and safeguard vulnerable and minority groups is enabled and enhanced through technical equipment and advice.					A
2.1 Public sector standards and public service delivery brought in line with international standards and obligations, particularly in relation to child safeguarding and health.					B
2.2 Capability and accountability in public financial management lead to greater confidence in international investors.					B
3.1 OT preparedness to respond to 'all hazards' is supported and sustained through organizational development and capacity building in security, justice and related sectors.					A
3.2 Long-term risks, including in respect of public health and economic security, are mitigated through UK support.					A
Overall output score					A
Outcome Assessment: The Justice, Security and Governance Programme is important to the OTs as the UK is committed to provide security for the OTs and safeguard its citizens. The context for delivery was challenging with the programme team, UK delivery partners and local stakeholders’ capacity impacted by Covid-19 (reprioritisation), EU Exit and hurricanes (in some OTs) respectively. / It is difficult to assess whether the programme’s Theory of Change was delivered as it has not been updated since the conception of the programme, and the programme has undergone two iterations since then. While the results framework has been updated, the last update was in October 2018. This is the reason the programme is graded as a B: insufficient and incomplete Theory of Change and evidence to demonstrate likely contribution to outcome.
Final Outcome Score: B			Risk: Medium
[1] This relates to financial year 19/20
[2] This relates to financial year 19/20

Summary of Programme Performance
Year	2015/16	2016/17		2017/18*	2018/19*	2019/20*
Score	N/A	A (SGGDM)[3] / A (SDIO)[4]	A	A	B	B
Risk	N/A	Medium (SGGDM) / Low (SDIO)		Medium	Medium	Medium
[3] Security, Good Governance and Disaster Management
[4] Sovereignty, Defence and International Obligations

What support did the UK provide?

The Justice, Security and Governance Programme (JSG) aimed to ensure the UK Overseas Territories (OTs) were resilient to a range of security threats including natural and manmade disasters, economic insecurity, crime and public health threats. It aimed to ensure they are governed by effective and transparent government agencies and institutions compliant with key international conventions.

Security and Justice

The programme provided law enforcement support to improve the competency, capability and capacity of OTs to prevent, investigate and prosecute serious and organised crime. This has included measures to meet specific security needs following an independent OT-wide (2016) assessment. For example, the programme provided a Montserrat patrol vessel legally registered, operational and ready for international audit by the Marine & Coastguard Agency. It also delivered support for legislative and risk-management frameworks for decision-making on passports, visas and citizenship.

Assistance in criminal justice was delivered through training, equipment and advice to justice actors to improve the functionality and equality of justice systems and legislation. The programme also provided support to prisons to achieve UK-inspired, OT-tailored, international human rights-compliant standards, with sufficient and competent personnel and safe, resilient infrastructure.

Governance

The programme provided child safeguarding support through improved OT security, justice and public service structures as a result of institutional, personnel and technical assistance. It also delivered support to improve public sector management and accountability, including through advice and training on financial and legislative reform. The programme worked to increase capacity and capability in public health (including mental health) and compliance of OTs with international health regulations. Finally, it provided support for sustainable economic development of the Falkland Islands, through diversification of the economy.

What results did the programme deliver? Will they be sustained?

Security and Justice
- Legislation developed across OTs to bring them more in line with international standards.
- Increased OTs and inter agency collaboration facilitated, bringing people and agencies across the OTs together through training and establishing new infrastructure, such as the Cayman Islands IBIS (Integrated Ballistic Identification System) Hub, which helps to gather evidence and link cases to prosecute violent crime. In the Sovereign Base Areas, a Control Room is under construction. This will bring police and customs officials together; TCI also produced their first inter-agency criminal justice strategic plan, endorsed by all actors in the criminal justice system.
- Operational needs assessment on maritime security and borders conducted Feb-April 2020 by MoD and Border Force, providing an up-to-date threat assessment of the Caribbean OTs and recommendations for future support.

Governance
- New safeguarding legislation developed in Anguilla. Bermuda updated its child protection legislation increasing the protection available for under 18s. Cayman has introduced updated offences to protect children from online offending and has introduced sexual offence prevention orders. Each of the territories now has the independent capability and capacity to deal with Child Sexual Abuse and Exploitation (CSAE) threats.
- Increased inter-agency capacity on safeguarding due to the establishment of multi-agency safeguarding hubs operational on Cayman Islands and TCI, where police, medical professions and social workers are co-situated to support vulnerable victims and improve rates of prosecution.
- Strengthened compliance with International Health Regulations, such as improved regional coordination across the territories.
- Technical assistance and training provided to strengthen Public Sector Reform, such as on the Digital Transformation work stream in BVI.
- Public Financial Management strengthened by building the capacity of OT audit offices and public account committees (PACS).

Disaster Management
- Key disaster response kit provided, such as emergency radio systems for Anguilla and St. Helena; post-hurricane repair and reconstruction work provided to prisons.
- Training needs assessment conducted on disaster management and capacity being built through training for all OTs.
- Strengthened prison infrastructure post-hurricane to improve resilience and security to future incidents e.g. external fencing and locks in BVI and Anguilla.

The programme achieved good sustainability, but whether change is long lasting depends on the project. The drafting of new legislation is essential, however for some projects support may be needed to ensure new policies are tailored to local circumstances. In some projects, capacity building was done well, such as when peer-to-peer or “train the trainer” methods were adopted, but training fell short when local buy-in was missing or it adopted an approach with little follow up. The programme had more meaningful, long-term success in fostering relationships between key officials and agencies in the OTs to facilitate lesson sharing identify synergies and improve effectiveness.

What lessons have been learned?

The importance of flexibility: the programme has undergone many revisions since its design, to reflect a context that has changed drastically. This has highlighted the importance of the programme being adaptive in nature to respond quickly to events as they change on the ground.

Less breadth and more depth: the programme has projects in many thematic areas, and could benefit from focusing on fewer areas with more depth, such as strengthening public sector delivery. This is of particular importance with regards training courses, where train the trainer style activities are much more successful.

Capability of partners across HMG: one strength of the programme was how closely it worked with other HMG partners (e.g. Ministry of Justice, Ministry of Defence, Home Office), many of whom were directly responsible for delivery. The programme team managed multiple stakeholder relationships well, identified their value-add and ensured the UK could provide the OTs with a ‘full suite’ of UK support.

The importance of the UK’s relationships with the OTs and key stakeholders: many of the most effective activities were facilitated by strong relationships between the implementing partner and local stakeholders. Good relationships with the OTs is vital for delivery, to ensure buy-in and long-term sustainability.