Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Maritime Governance and Environment (MGE)
Country and Region:	UK Overseas Territories (OTs)
IATI Unique ID:	CSSF-07-000008
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for the Environment, Food and Rural Affairs (DEFRA), Maritime and Coastguard Agency (MCA) / UK Hydrographic Office (UKHO), Marine Management Organisation (MMO) / The Centre for Environment, Fisheries and Aquaculture Science (CEFAS), Animal and Plant Health Agency (APHA), Joint Nature Conservation Committee (JNCC)
Total Budget:	ODA: £7.53m			Non-ODA: £17.53m
Budget this FY[1]	ODA: £4.37m			Non-ODA: £7.83m
Spend this FY:[2]	ODA: £4.43m			Non-ODA: £7.75m
Original Programme Start Date: 1 April 2018		End Date: 31 March 2020
Outputs					Score
1. Maritime Obligations					A
2. Search And Rescue (SAR) Capability					A
3. Pollution Response					A
4. Seabed Mapping					A
5. Boundary Delimitations					A
6. Natural Capital in BVI					A
7. Biosecurity & Invasive Species					A
8. Blue Belt					A
9. Coral Reefs in Montserrat and Pitcairn					A
Overall output score					A
Outcome Assessment: Outcomes are clearly delivering effect in line with the National Security Council (NSC) strategy for the OTs, the Programme Impact Statement (“The programme will deliver improved safety of life at sea, protection of the marine environment and development of the blue economy”) and the programme is achieving the milestones set out in the results framework.
Final Outcome Score: A			Risk: Medium
[1] Budget figures are for financial year 2019/20.
[2] Spend figures are for financial year 2019/20.

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	N/A	A	A	A	A	A	A
Risk Rating - low/medium/high	N/A	N/A	Medium		Medium		Medium
*Output/outcome scores

What support did the UK provide?
The MGE programme delivers against the first and fourth pillars of the NSC Strategy[3]. The programme is split into three principal areas of focus:
[3] NSC Pillar 1: UK sovereignty upheld and OTs meet international obligations. NSC Pillar 4: Improved prosperity and economic development moves OTs towards financial independence.
- Meeting the UK’s responsibility to ensure the OTs are capable of complying with their international obligations as flag, port and costal states (III Code, Security Needs Assessment, Search and Rescue (SAR), seabed mapping, hydrographic charting);
- Increasing environmental resilience across the OTs;
- Delivering HMG’s ‘Blue Belt ‘commitment to provide long term protection to over four million km2 of marine environment.

What results did the programme deliver? Will they be sustained?

The programme achieved the following results:
Maritime Obligations and SAR: SAR equipment was provided for all the Central Alerting Posts (all five Caribbean OTs and St Helena). Significant increase in SAR networking has been achieved. Legislation packages for Bermuda, British Virgin Islands (BVI) and Falklands are largely complete for compliance with III Code. Initial packages of III Code legislation drafted for Anguilla, Montserrat, St Helena and The Cayman Islands and in varying stages of iteration with the respective Attorney Generals. The III Code sets out the audit standard for maritime compliance and the mandatory IMO audit will cover compliance in the UK and OTs, as part of the UK flag state. The UK flag State needs to meet international standards on shipping to uphold its position at the IMO and its international negotiating position and credibility.
Pollution Response: response equipment for minor incidents (Tier 1) was procured and now delivered to all OTs. All pollution-response capability reports were drafted. Training packages delivered to 60+ personnel in Bermuda, Caribbean OTs and St Helena. There is a greater understanding of international obligations on oil pollution response, risks, the need for additional equipment, training, and better planning.
Seabed Mapping: Seabed mapping surveys have been completed in eight OTs. This data is being used to update the navigational charts and support the marine environment. All five Caribbean OTs have received Maritime Safety Information (MSI) Capacity Building. The programme provided Montserrat with hydrographic surveying equipment, training and support enabling local capacity to collect seabed-mapping data for a wide range of purposes to assist in the management of their marine estate. Twelve new navigational charts of Antarctic waters have been produced which will improve navigation and in this environmentally sensitive area and decrease the risk of a maritime incident.
- Natural Capital in BVI: a new programme focused on development and use of environmental and natural capital indicators for national reporting and disaster preparedness in BVI. Significant changes to BVI’s disaster resilience model were made, including automation, data updates and an application developed to enable BVI Officers to explore the effects of flood risk.
- Biosecurity and Invasive Species: biosecurity plans were developed for 15 OTs to reduce the risk of new introductions of invasive non-native species. These were underpinned by the development of a biosecurity toolkit and training in basic entomology, rodent biology and control, biosecurity, pest risk assessment, and contingency planning for wildlife diseases. Through Blue Belt, the programme supported designation of a Marine Protected Area (MPA) covering 404,000 km2 in Ascension. It also supported agreement of a marine protection strategy across the entire Exclusive Economic Zone (EEZ) of Tristan da Cunha in 2019. UK OTs have also benefitted from a centralised surveillance and intelligence service.
- Coral Reef action plans for Montserrat and Pitcairn: Montserrat’s Action Plan is now owned by the Government of Montserrat (GOM) and its publication will follow GOM sign-off. Agreement has been reached that the Pitcairn action plan is not needed as human activities have a minimal impact on the marine environment and the Pitcairn Government is already developing a marine plan.

Sustainability of results will be addressed in the short term through continued programming in all of these areas. Noting the diverse range of projects within the programme, a decision has been taken to split this programme, and the complementary Justice, Security and Governance Programme into four separate programmes: Environment, Sustainability and Climate Change (ESCC); Governance; Justice; and Border Security. This will ensure scrutiny of inputs, outputs and outcomes will be more focused on tighter objectives. Nevertheless, long-term sustainability will require continued UK efforts to stress the importance of the areas covered by these programmes.

What lessons have been learned?

- A regular theme across programme components was the need for continued support as initial programming on these broad themes has highlighted a significant number of areas where further work is needed. This support could take the form of increased programming led by the FCO, as a successor programme to this one, or by targeted attempts to share capability across OTs. The programme has demonstrated the value of targeted technical expertise that is cognisant of each OT and its circumstances. Any successor programme should seek to increase and expand this approach.
- Important to involve OT Governments and Governors offices in the design and implementation of the project and build strong partnerships.
- Increase visibility of programme outputs to the wider FCO network, NGOs and territory governments and citizens.