Annual Review - Summary Sheet

PROGRAMME TITLE: British Virgin Island Territory Programme (BVITP)
Country and Region:	British Virgin Islands (BVI), Caribbean, UK Overseas Territories (OTs)
IATI Unique ID:	CSSF-07-000007
HMG Partners / (LEAD in bold):	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £0.00m			Non-ODA: £10.00m
Budget this FY:	ODA: £0.00m			Non-ODA: £3.60m
Spend this FY:	ODA: £0.00m			Non-ODA: £1.84m
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
Recovery and Development Agency (RDA) established & delivering hurricane recovery work.					B/C
The Government of The Virgin Islands (GOVI) supported to stabilise territory wide security.					B
Transitioned UK early recovery support to BVI-led long-term recovery.					B/C
Overall output score					B/C
Outcome Assessment: / The delivery pace of the programme continued to be slow for FY19/20. This was due to the newly elected government’s reassessment of recovery priorities and corresponding below, expected engagement with the RDA. This led to significant delays in delivery. Other planned outputs have failed to deliver due to lack of buy-in by local stakeholders.
Outcome Score: B/C			Risk: Medium-high

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	N/A	N/A	N/A	B	B	B	B
Risk Rating	N/A	N/A	N/A	N/A	Medium/High		Medium/ High	Medium/High
*Output/outcome scores
How has the programme changed during this period?			A challenging year which was due to focus on the delivery of projects, stalled due to the new government’s reassessment of priorities and a subsequent revised Recovery and Development Plan (RDP). As a result, towards the end of the FY, the BVITP strategy shifted towards supporting the Governor’s Constitutional responsibilities.

What support did the UK provide in FY 19/20?
The programme provided financial support (operating costs) for the RDA, which delivers public infrastructure projects in line with BVIG’s priorities as set out in the five-to-seven-year revised RDP. This funding also enabled the RDA to provide capacity building, mentoring, training to BVI business and to host secondees from Government Ministries to learn and take back skills. The programme also provided funding for recovery projects that were identified as critical priorities for the resumption of normal security & justice activities, disaster preparedness, and contingent liabilities (the constitutional responsibility of the Governor of the British Virgin Islands).

Key results for FY 19/20:
The programme delivered the following results under its main projects:

RDA
The RDA operated with a full headcount and clear accountability and transparency. Capacity building has been mainstreamed.

Security and Justice
Several infrastructure projects have been delivered, including the Magistrates Court and Road Town Police Station projects. The security and justice project also provided technology, equipment and capability building, enabling law enforcement and judicial services to operate more effectively.

Disaster Management
GOVI achieved its benchmark disaster readiness self-assessment score of better than 36%, however this demonstrates further CSSF programming work is required, including in building capability and asset management.

Key Lessons:
- Lack of buy in from local stakeholders and prolonged resistance of fully utilising the RDA’s expertise and capacity, resulted in slow delivery and reduced scope of projects through most of the financial year. A major shift in engagement and delivery became evident in early 2020 and is likely attributed to changes in leadership of the RDA.
- Setting up a new independent agency (the RDA) for delivery of hurricane reconstruction consumed a lot of energy, resource and money. Ultimately, this has had limited success. An alternative approach may have delivered better results with improved value for money.
- Best practise modelled by the RDA in terms of transparency and accountability has helped engender a cultural shift in BVI, with media and bloggers increasingly calling for GoVI to follow similar standards.
- The Governor’s Office should take a more active role in the welfare of newly embedded advisors or contractors. In addition, they should explore ways to support new arrivals, e.g., through more comprehensive pre-arrival engagement and country briefing. They should also ensure local partners are fully involved in the recruitment process.

Summary of Recommendations for FY 20/21
- To ensure GOVI buy in, the remainder of the programme should focus on projects which directly link to the Governor’s Constitutional responsibilities, and which the Governor’s Group are able to implement.
- To enable this, there should be a holistic review of the BVITP to determine where the remaining funds should be allocated. This review should draw in relevant development expertise to shape the portfolio and shift the strategy. This should align with priorities as set out in the BVI country plan, including more of a focus on security, justice and good governance, on which the Governor has a clear mandate.
- Given the lower-than-expected delivery of projects and questions around value for UK taxpayers’ money, the UK funding of operational costs should stop in March 2021, as planned, and the RDA should transition to GOVI and alternative sources of funding.
- The Results Framework indicators should be overhauled to make outputs and milestones clearer and more specific, so that they can be better measured for all outcomes.
- More broadly, a third-party team should conduct an evaluation of the approach taken in terms of setting up an independent entity to deliver post-disaster recovery and development. This should include its successes and failures and provide an assessment of what alternative approaches may have been more effective and offer better value for UK taxpayers’ money. This should also explore why the RDA did not achieve its potential and draw on regional comparators as appropriate. This could draw from other similar initiatives in the region (e.g., Climate Resilience Execution Agency Dominica. These lessons could then be applied to future natural disasters in BVI, or Overseas Territories and Small Island Developing States.
- More support should be offered to external advisors who are deployed to BVI, including a series of pre-departure briefings and regular ‘check-ins’ once in country. The Programme Manager is primarily responsible; however, the Head of the Governor’s Office should also take an active and visible role in this. They should intervene when necessary to ensure appropriate support is provided.